## List
Project Status | Responsible | Property | kWp | Prob. FID | Main blocker | Next action
In operation (COD) |  | Bjørnstjerne Bjørnsons gate 110
In operation (COD) |  | Johan Follestads vei 24
In operation (COD) |  | Espehaugen 49
Sold |  | Svinesundsveien 336
In operation (COD) |  | Ingeniør Rybergs gate 99 (Padel)
In operation (COD) |  | Jeksleveien 51
In operation (COD) |  | Orkidéhøgda 3 (Vita)
In operation (COD) |  | Orkidéhøgda 3 (Validus/Medivatus)
In operation (COD) |  | Johan Follestads vei 7 (stort)
In operation (COD) |  | Johan Follestads vei 27
In operation (COD) |  | Fiboveien 8
In operation (COD) |  | Fiboveien 12C
In operation (COD) |  | Fiboveien 12D
In operation (COD) |  | Fiboveien 14A (XXL)
In operation (COD) |  | Fiboveien 14B (Jula)
In operation (COD) |  | Lundedalen 51
Signed - awaiting Sales | Johan | Wirgenes vei 12 (XL-Bygg) | 442 | 10% | Avventer PPA med XL-bygg. Byggeier ønsker ikke installasjon med mindre XL-bygg er med på laget. På vent forløpig. | Johan følger opp etter at WV14 er driftsatt - est juni
Cancelled |  | Skeievegen 76
Cancelled |  | Mjåvannsvegen 128
In operation (COD) |  | Vekstveien 5B (Generator Solutions)
In operation (COD) |  | Johan Follestads vei 25
In operation (COD) |  | Vekstveien 5A (Scala Bad)
In operation (COD) |  | Longhammarvegen 24
In operation (COD) |  | Smemyrveien 1
In operation (COD) |  | Jeksleveien 47 (Kominox)
In operation (COD) |  | Jeksleveien 47 (Antra)
In operation (COD) |  | Jeksleveien 100
In operation (COD) |  | Jeksleveien 55
Cancelled |  | Jeksleveien 59 (Biovac)
In operation (COD) |  | Johan Follestads vei 6
In operation (COD) |  | Jeksleveien 36 (Bulk Wood)
Cancelled |  | Grenseveien 99
In operation (COD) |  | Nordbyveien 98
In operation (COD) |  | Professor Birkelands vei 36
In operation (COD) |  | Nordre Kullerød 5
In operation (COD) |  | Smalvollveien 61-63
In operation (COD) |  | Stubberudveien 8
In operation (COD) |  | Vollaveien 19
In operation (COD) |  | Vollaveien 20A
In operation (COD) |  | Skjærdalen 2
In operation (COD) |  | Industrigata 1
In operation (COD) |  | Barstølveien 19
In operation (COD) |  | Holmestrandsveien 117
In operation (COD) |  | Stemmane 6
In operation (COD) |  | Grudevegen 2
In operation (COD) |  | Ingeniør Rybergs gate 99 (Rush)
In operation (COD) |  | Lysaker Torg 6-10
In operation (COD) |  | Orhusveien 77
In operation (COD) |  | Nensetbakken 27-29
In operation (COD) |  | Bjørnerudveien 14
In operation (COD) |  | Fossveien 43
In operation (COD) |  | Fiboveien 12E
In operation (COD) |  | Hoffsveien 10
In operation (COD) |  | Gjennestadtunet
In operation (COD) |  | Jeksleveien 50
In operation (COD) |  | Hvittingfossveien 117
In operation (COD) |  | Kanalvegen 12
In operation (COD) |  | Stokkamyrveien 11
In operation (COD) |  | Hålandsvegen 27
In operation (COD) |  | Sjøvegen 16
In operation (COD) |  | Strømsveien 258
In operation (COD) |  | Larkollveien 4
In operation (COD) |  | Høgdaveien 1
In operation (COD) |  | Kolonivegen 43
In operation (COD) |  | Myhrersvingen 12
In operation (COD) |  | Stasjonsvegen 26-30
In operation (COD) |  | Stokkamyrveien 5
In operation (COD) |  | Almedalsveien 6 (Maxbo)
Under deployment |  | Snipetjernveien 3A
In operation (COD) |  | Snipetjernveien 9
In operation (COD) |  | Årvollskogen 65
In operation (COD) |  | Deliveien 6
In operation (COD) |  | Storgata 38
In operation (COD) |  | Industrivegen 55
In operation (COD) |  | Skytterheia 3
In operation (COD) |  | Industriparkveien 35
In operation (COD) |  | Selbuvegen 715
In operation (COD) |  | Lindebergveien 10
In operation (COD) |  | Lagårdsveien 78-80
In operation (COD) |  | Tiltaksvegen 22
In operation (COD) |  | Tjøllingveien 45
In operation (COD) |  | Gamle Ringeriksvei 34
Under deployment |  | Lilletuneveien 3
Cancelled |  | Varnaveien 30
In operation (COD) |  | Smibakken 10
In operation (COD) |  | Mellomriksvegen 4869 (Rema 1000/Europris)
Signed - awaiting Sales | Johan | Havet 45 | 512 | 5% | Venter RIB. | Johan jobber med RIB avklaring. Ser ikke bra ut pt, men vi forsøker
In operation (COD) |  | Semsvegen 40A (Rema 1000)
In operation (COD) |  | Vestsidevegen 6 (Rema 1000)
In operation (COD) |  | Johan Falkbergets veg 2 (Rema 1000)
In operation (COD) |  | Torpavegen 2 (Rema 1000)
Signed - awaiting Sales | Johan | Søndre Industrivegen 50 | 517 | 5% | Venter RIB. | Johan jobber med RIB avklaring. Ser ikke bra ut pt, men vi forsøker
In operation (COD) |  | Sentrumsveien 40 (Rema 1000)
Under deployment |  | Hognestadvegen 90 (Rema 1000)
Cancelled |  | Betzy Kjelsbergs vei 9 (Rema 1000)
On hold | Jonas | Kurillvegen 8 | 2225 | 10% | ? | Hva er blocker her Jonas?
In operation (COD) |  | Høvågveien 199
Signed - awaiting Sales | Jonas | Jeksleveien 120 | 371 | 20% | Venter OK fra Bulk/KLP til å kunne bygge. Kan bygge uten PPA. | 13.04: Jonas snakker med Rune i Bulk.
Signed | Kjetil | Brokelandsheia 31 (Europris) | 160 | 50% | Venter beslutning Europris/Ragde. Vi kan byggge uten PPA. | Nytt møte med Lars fredag 17.04. Håper på beslutning da.
In operation (COD) |  | Havnegata 16
Ready to build | Kjetil | Kinnlimarka 20 | 986 | 50% | NTE godkjennelse - ikke presentert. | 14.04: Purret i dag på garantibekreftelse fra Ecosol som må på plass for at APA kan presenteres til NTE.
In operation (COD) |  | Fiboveien 12B (Jysk)
Signed | Kjetil | Fiboveien 4 (Europris) | 194 | 50% | Venter beslutning Europris/Ragde. Vi kan byggge uten PPA. | Nytt møte med Lars fredag 17.04. Håper på beslutning da.
Signed | Kjetil | Furuholtet 10 (Rema 1000) | 198 | 80% | Får kun bygd på deler av taket pga skader på taket. Undersøker om anlegget blir stort nok for å få utbetalt Enova-støtte (forutsetning fra gårdeier). | 14.04: Geir har fulgt opp med Erik.
Signed | Kjetil | Ryggeveien 375A (Rema 1000) | 157 | 20% | Sameie. | 08.04: Spurt kunde om kontaktinfo til sameie. 15.04: Kjetil purret på Erik.
Cancelled |  | Gangveien 10
Signed | Kjetil | Pans veg 2 (Rema 1000) | 161 | 100% | Addendum mellom AKA+Rema1000.
In operation (COD) |  | Fossumveien 70 (Maxbo Sentrallager)
In operation (COD) |  | Nordre Bliksrud vei 2 (Maxbo Bjørkelangen)
In operation (COD) |  | Per Krohgs vei 2 (Maxbo Karihaugen)
Signed | Kjetil | Våleveien 1 (Rema 1000) | 198 | 100% | Addendum mellom AKA+Rema1000.
In operation (COD) |  | Holmaveien 19 (Maxbo Teknikk bygget)
Under deployment |  | Deliveien 10
In operation (COD) |  | Ringeriksveien 191C
Signed | Kjetil | Vesterveien 737 (Rema 1000) | 145 | 100% | Addendum mellom AKA+Rema1000.
Signed | Kjetil | Braarudveien 7 (Rema 1000) | 171 | 100% | Addendum mellom AKA+Rema1000.
In operation (COD) |  | Almedalsveien 6 (E-motive)
In operation (COD) |  | Vollaveien 17
In operation (COD) |  | Vollaveien 15
In operation (COD) |  | Vollaveien 20B
Signed | Kjetil | Iseveien 8 (Rema 1000) | 239 | 100% | Addendum mellom AKA+Rema1000.
In operation (COD) |  | Semsvegen 46B (Jysk)
In operation (COD) |  | Hegnasletta 6
In operation (COD) |  | Henrik Bulls veg 100
Signed | Kjetil | Frøyas gate 1 (Rema 1000) | 190 | 100% | Addendum mellom AKA+Rema1000.
In operation (COD) |  | Gaupeveien 21
In operation (COD) |  | Johan Follestads vei 7 (lite)
In operation (COD) |  | Majorvegen 8
Under deployment |  | Stamveien 1
In operation (COD) |  | Stasjonsvegen 28 (Bøsenteret)
To be installed (FID) | Kjetil | Sandumveien 2 (Rema 1000) | 207 | 100% | Addendum mellom Haber+Rema1000. | 14.04: Geir har fulgt opp med Erik.
To be installed (FID) | Kjetil | Mausetvegen 4 (Rema 1000) | 121 | 100% | Addendum mellom Haber+Rema1000. | 14.04: Geir har fulgt opp med Erik.
Signed - awaiting Sales | Ole-Bjørn | Mjåvannssløyfen 244 (Sørlandschips) | 1448 | 70% | Venter avtale mellom gårdeier og leietaker. | 10.04: OB sendte en betryggende e-post til kunde vedrøende lekkasje, forsikring osv.
On hold | Rikard | Edvard Griegs veg 45 | 1000 | 5% | Rebuild of roof / new cooling systems. Warbo to come back to us when progress with tenants | Avventer tilbakemelding fra kunde. Response from Warbo / OSSC. 09.04.26: from Kjetil: Can we build without PPA? We can defo get a price below 5 kr/W.
Signed | Rikard | Billingstadsletta 11 (Rema 1000) | 207 | 10% | Sameie. | S&R har møte med Ragde i dag (13.04) Alt. 1: Rikard sent e-post til Lars (9 April 2026) med proposition til sameiene der vi gir X% i rabatt på strøm til fellesforbruket og/eller vi kan tilby eks. installasjon av ladepunkt for gjesteparkering el. Alt. 2: Om Lars ikke vil ta kontakt, så tar Rikard diretkte kontakt NB! Sameiene har GF og styremøte i disse dager, så dette HASTER.
In operation (COD) |  | Snipetjernveien 3C
Signed | Rikard | Stasjonsgata 32 (Europris) | 245 | 10% | Sameie. | S&R har møte med Ragde i dag (13.04) Alt. 1: Rikard sent e-post til Lars (9 April 2026) med proposition til sameiene der vi gir X% i rabatt på strøm til fellesforbruket og/eller vi kan tilby eks. installasjon av ladepunkt for gjesteparkering el. Alt. 2: Om Lars ikke vil ta kontakt, så tar Rikard diretkte kontakt. Alt. 3: Rikard kansellerer. NB! Sameiene har GF og styremøte i disse dager, så dette HASTER.
Signed | Rikard | Vestmovegen 5 (Europris) | 167 | 50% | Venter beslutning Europris/Ragde. | S&R har møte med Ragde i dag (13.04) Rikard skriver forslag til epost Jonas kan sende til Europris. Alex forsøker å få avtale med Ishavskraft lignende Bergen Synergy.
Signed | Rikard | Sandesletta 14-16 (Europris) | 235 | 10% | Venter beslutning Europris/Ragde. Sameie. | S&R har møte med Ragde i dag (13.04) Alt. 1: Rikard sent e-post til Lars (9 April 2026) med proposition til sameiene der vi gir X% i rabatt på strøm til fellesforbruket og/eller vi kan tilby eks. installasjon av ladepunkt for gjesteparkering el. Alt. 2: Om Lars ikke vil ta kontakt, så tar Rikard diretkte kontakt. Alt. 3: Rikard kansellerer. NB! Sameiene har GF og styremøte i disse dager, så dette HASTER.
Cancelled |  | Barstølveien 19 (Klondyke)
Signed | Rikard | Skreppestadveien 28 (Europris) | 149 | 50% | Venter beslutning Europris/Ragde. | S&R har møte med Ragde i dag (13.04) Rikard skriver forslag til epost Jonas kan sende til Europris. Alex forsøker å få avtale med Ishavskraft lignende Bergen Synergy.
In operation (COD) |  | Gneisveien 12
In operation (COD) |  | Stormåsan 19 (gammel)
In operation (COD) |  | Vogellund 35
In operation (COD) |  | Lysaker Torg 5
In operation (COD) |  | Lysaker Torg 15
In operation (COD) |  | Lysaker Torg 25
Under deployment |  | Grev Wedels plass 9
Cancelled |  | Barstølveien 52 (Sørlandstunet)
Signed | Rikard | Lasta 2 (Rema 1000) | 121 | 10% | Sameie. | S&R har møte med Ragde i dag (13.04) Alt. 1: Rikard sent e-post til Lars (9 April 2026) med proposition til sameiene der vi gir X% i rabatt på strøm til fellesforbruket og/eller vi kan tilby eks. installasjon av ladepunkt for gjesteparkering el. Alt. 2: Om Lars ikke vil ta kontakt, så tar Rikard diretkte kontakt. Alt. 3: Rikard kansellerer. NB! Sameiene har GF og styremøte i disse dager, så dette HASTER.
Signed | Rikard | Tornsangerveien 25 | 454 | 50% | Ragde vurderer salg av eiendom. | S&R har møte med Ragde i dag (13.04) 08.04.26: Rikard pushet Lars i går og nevnte verdien av å bygge disse uavhengig av salg. Rikard kontakter Lars og sier at vi kan bygge uten PPA der RS kommer på plass etter PPA er signert.
Signed | Rikard | Sarpsborgveien 9 | 318 | 10% | Sameie. | S&R har møte med Ragde i dag (13.04) Alt. 1: Rikard sent e-post til Lars (9 April 2026) med proposition til sameiene der vi gir X% i rabatt på strøm til fellesforbruket og/eller vi kan tilby eks. installasjon av ladepunkt for gjesteparkering el. Alt. 2: Om Lars ikke vil ta kontakt, så tar Rikard diretkte kontakt. Alt. 3: Rikard kansellerer. NB! Sameiene har GF og styremøte i disse dager, så dette HASTER.
Signed | Rikard | Henrik Bulls veg 102 (Jula) | 417 | 50% | Ragde vurdere å selge eiendom. | S&R har møte med Ragde i dag (13.04) Rikard pushet Lars i går og nevnte verdien av å bygge disse uavhengig av salg
Under deployment |  | Bedriftsvegen 76
Signed - awaiting Sales | Rikard | Vestbyveien 113-115-117 | 408 | 10% | Daimyo uncertain of value proposition given old roof | 14.04: Rikard må sette opp et møte med Fredrik
Ready to build | Siri | Ole Deviks vei 40 (Maxbo Ole Deviks Vei) | 448 | 80% | Var bestilt av Solcellespesialisten, men må nå signeres en PPA i tillegg til Maxbo for å få lønnsomhet (i hovedsak pga økt AC-kost). Johan er i dialog med Fagflis som er i samme næringsområde. | 13.04: venter på bekreftelse fra Bravida i dag på at de holder AC pris også i Q3. Alt. 1: Siri hører med Fossnes om marginen blir bedre med nedjustert anlegg. Alt. 2: Siri konkurranseutsetter på nytt. Forslag: Si en pris per Watt til installatør og at de får den om de kan levere på prisen.
In operation (COD) |  | Orkidehøgda 14
In operation (COD) |  | Måkeveien 1A
In operation (COD) |  | Wirgenes vei 2
In operation (COD) |  | Storgaten 2B
In operation (COD) |  | Hinderveien 2
Signed | Siri | Smibakken 2 | 1599 | 50% | Ragde må tekke om tak. Venter tilbakemelding på tidslinje. | S&R har møte med Ragde i dag (13.04) 07.04.26: Rikard asked Lars.
Signed | Siri | Rolvsøyveien 402 (Rema 1000) | 116 | 30% | Brannvegg skal etableres på taket før installasjonen. Venter tilbakemelding fra Ragde på fremdrift. | S&R har møte med Ragde i dag (13.04) 07.04.26: Rikard asked Lars.

## Raw data
🟡☢ Project status | 🔁 Full address | Blocker | 🟡❕☢ Des. kWp | 🟡❕☢ Est. FID | 🟡❕☢ Est. COD | 🟡❗☢ FID | 🟡❗☢ ISD | 🟡❗☢ COD | 🟡❗☢ Dep. kWp | 🟢 NTE status | 🔄 Days FID-COD | 🔄 Days FID-COD # | 🔄 Days FID-ISD | 🔄 Days FID-ISD # | 🔄 Days ISD-COD | 🔄 Days ISD-COD # | 🔄 Days RLA-COD | 🔄 Days RLA-COD # | 🔄 Days RLA-FID | 🔄 Days RLA-FID # | 🔄 Des./Dep. MWp | 🔄 Devex reporting | 🔄 FID check | 🔄 Fee '25 | 🔄 GoO period | 🔄 Insured check | 🔄 Month (COD) | 🔄 Month (ISD) | 🔄 Mrg. incl. ENOVA '25 | 🔄 Mrg/day (NOK) | 🔄 Mrg/day (kNOK) | 🔄 P&L % check | 🔄 Production (MWh) | 🔄 Production (kWh) | 🔄 Quarter (COD) | 🔄 Quarter (FID) | 🔄 Quarter (RLA) | 🔄 SP EG amount '25 | 🔄 SaaS Y.fee base | 🔄 SaaS fee '25 (ARR) | 🔄 SaaS fee '25 adj. | 🔄 Sales mrg. '25 | 🔄 Sales price '25 | 🔄 Sales price reporting | 🔄 Since COD | 🔄 W. SP EG amount '25 | 🔄 W. gross mrg. '25 | 🔄 W. mrg. incl. ENOVA '25 | 🔄 W. pot. mrg. | 🔄 W. sales price '25 | 🔄 W. tot project mrg. | 🔄 Weighted mrg. | 🔄 Weighted mrg. '26 | 🔄 Weighted mrg. (NOT IN USE) | 🔄 Weighted revenue | 🔄 Year (COD) | 🔄 Year (RLA) | 🔄 kWp diff | 🔄☢ Des./Dep. kWp | 🔄☢ Gross margin reporting | 🔄☢ Mrg. / Wp rep. | 🔄☢ Net margin reporting | 🔄☢ SP EG amount | 🔄☢ SP EG amount adj | 🔄❕ Est. mrg. | 🔄❕ Est. mrg/Wp | 🔄❕ Est. price/Wp | 🔄❕ Est. weighted margin | 🔄❕ Sum devex | 🔄❗ Margin MNOK (COD) | 🔄❗ Project mrg. | 🔄❗ Sales / MNOK | 🔄❗ Total margin rec. | 🔄❗☢ Sum devex | 🔄️ # of NoC | 🔄️ CAPEX MNOK (Ini. + final) | 🔄️ Delta margin/Wp | 🔄️ Sales price MNOK (Ini. + final) | 🔄️ Weighted est. mrg. to be rec. | 🔄️☢ CAPEX/Wp | 🔄️☢ Net margin / Wp | 🔄️❕ Est. CAPEX | 🔄️❕ Est. CAPEX/Wp | 🔄️❕ Est. EG to be rec. | 🔄️❕ Est. GoO to be rec. | 🔄️❕ Est. PPA earnout to be rec. | 🔄️❕ Est. mrg. to be rec. | 🔄️❕ Sum est. PPA earnout | 🔄️❗ MNOK CAPEX | 🔄️❗ MWp | 🔄️❗ Mrg. Enova | 🔄️❗ Mrg. GoO earnout rec. | 🔄️❗ Mrg. PPA earnout rec. | 🔄️❗ Price/Wp | 🔄️❗ Sum NoC | 🔄️❗☢ Final CAPEX | 🔵 ENOVA AD | 🔵 ENOVA documents | 🔵 ENOVA score | 🔵 Enova status desc | 🔵 SP EG share % | 🔵 SaaS package | 🔵 Sunday Box (SB) | 🔵 SundayOS onboarding | 🔵☢ EG applied | 🟠 Address | 🟠 Energy consultant | 🟠 Enova qul. | 🟠 Enova status | 🟠 Main fuse | 🟠 PO Group | 🟠 PPA signed | 🟠 Postnr. | 🟠 Poststed | 🟠 RLA contract | 🟠 RLA signed link | 🟠 SPV | 🟠 Sales rep | 🟠 Voltage | 🟠☢ Project model | 🟠❕ Signed kWp | 🟠❗☢ RLA | 🟡 AC contact | 🟡 Access to roof | 🟡 EPC | 🟡 EPC PM | 🟡 FDV Docs | 🟡 GoO applic. | 🟡 GoO end | 🟡 GoO pricing | 🟡 GoO reapply | 🟡 GoO start | 🟡 Grid application | 🟡 Grid owner | 🟡 Handover EPC | 🟡 Handover Sales | 🟡 Inspections | 🟡 Insurance | 🟡 Inverter models | 🟡 Issues | 🟡 Load check | 🟡 Meter from start | 🟡 PBE description | 🟡 PBE status | 🟡 Power Meter # | 🟡 RIB company | 🟡 RIB status | 🟡 Retrofit | 🟡 Roof type | 🟡 Roof year | 🟡 Solar modules | 🟡 Startup meeting | 🟡 TV mode | 🟡 Tinglysning com. | 🟡SundayBox delivery | 🟡☢ PM SP | 🟡❕ An.bid. | 🟡❕ Energy report | 🟡❕ Other devex | 🟡❕ PBE cost | 🟡❕☢ AC price | 🟡❕☢ DC price
In operation (COD) | Bjørnstjerne Bjørnsons gate 110, 3044 Drammen |  | 100.1 | 2023-03-01 | 2023-06-30 | 2023-03-01 | 2023-04-01 | 2023-06-30 | 100.1 | Transferred | 🟨 121 days | 121 | 🟩 31 days | 31 | 🟨 90 days | 90 | 🟥 455 days | 455 | 🟥 334 days | 334 | 0.1 | 0 | 🟩 All good | 25 | 🟩 914 days left | 💚 All good | 23 - Jun | 2304 | 0 | 428.945054945055 | 0.428945054945 | 🟥 SUM! | 78.8788 | 78,878.8 | 2023 - Q2 | 2023 - Q1 | 2022 - Q2 | 0 | 2,502.5 | 2,502.5 | 2,502.5 | 0 | 0 | 1,012,108 | ⌚ 1006 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0 | 100.1 | 195.17 | 1.94975024975 | 195.17 | 0 | 0 | 195.17 | 1.94975024975 | 10.110969030969 | 0 | 0 | 0.2 | 195.17 | 2026-01-01 | 195.17 | 0 | 🟩 NoCs: 0 | 0.82 | 0 | 2026-01-01 | 0 | 8.161218781219 | 1.949750249750 | 816.938 | 8.161218781219 | 0 | 33.89 | 0 | 33.89 | 0 | 0.82 | 0.1 | 0 | 0 | 0 | 10.110969030969 | 0 | 816.938 | [5 empty] | NTE | thing_d245a793-aaba-5202-9038-6b468ed12089 (https://www.notion.so/thing_d245a793-aaba-5202-9038-6b468ed12089-226a1d8f95598019a83ff6affd5bf929?pvs=21), thing_c668a9bb-e250-58bd-87fc-84a323e7f34b (https://www.notion.so/thing_c668a9bb-e250-58bd-87fc-84a323e7f34b-226a1d8f95598039aa94eb81c573f147?pvs=21) | N/A |  | Bjørnstjerne Bjørnsons gate 110 |  |  | Does not qualify | 1600A | Ticon Eiendom AS (https://www.notion.so/Ticon-Eiendom-AS-1a7a1d8f9559803a8632c82b4ce91e69?pvs=21) | Yes - all PPAs | 3044 | Drammen | Signed |  | Ticon Bangeløkka AS (https://www.notion.so/Ticon-Bangel-kka-AS-1a7a1d8f95598049b9dbea6d7b2710f1?pvs=21) | Not set | 230 V, 400 V | Solar as a Service | 279 | 2022-04-01 | Henning Kolstad (https://www.notion.so/Henning-Kolstad-1a5a1d8f9559805691c8edea660e4ba0?pvs=21) | På innsiden av byggene. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rino Ombudstvedt (https://www.notion.so/Rino-Ombudstvedt-1a5a1d8f955980218040c8e684568b18?pvs=21) | N/A | Approved | 2028-10-02 | Retrofit - GoO earnout | Retrofit not completed | 2023-06-30 | Done | GLITRE | Done | Completed | BB110 2024 (https://www.notion.so/BB110-2024-173a1d8f9559800f9cc2dd7bce73209a?pvs=21), BB110 2025 (https://www.notion.so/BB110-2025-206a1d8f955980dfb12bc57929a4df89?pvs=21) | Default | BB110 South: 1x Sungrow SG50CX (400V) BB110 North: 1x Growatt MAX 30KTL3 XL (230V) | Grid volt sample different alarm (https://www.notion.so/Grid-volt-sample-different-alarm-10224510422644ff8381cdca36bf0e3b?pvs=21), Some irregularity, grid volt, missing production (https://www.notion.so/Some-irregularity-grid-volt-missing-production-e85f44c998cd42f3ac5da5b34952c0af?pvs=21), Grid Volt Sample different (https://www.notion.so/Grid-Volt-Sample-different-050c5f0b595340c8a707654e43757546?pvs=21), Grid Volt Sample Different alarm (https://www.notion.so/Grid-Volt-Sample-Different-alarm-229a1d8f955980e48116ce4d8e2070c8?pvs=21), Grid Over Voltage (https://www.notion.so/Grid-Over-Voltage-24ea1d8f955980e8bf8cfda3d8492c22?pvs=21) | Roof OK | Retrofit |  | Not applicable | 7359992892892615 (https://www.notion.so/7359992892892615-11aa1d8f9559806fac3cef990ad5f7e7?pvs=21), 7359992902114652 (https://www.notion.so/7359992902114652-11aa1d8f9559800e9bc2ded555289687?pvs=21) |  |  | To be started | PVC | 2022 (nord) / 2018 (sør) | BB110 South: 144x455W Longi LR4-72HPH-455M BB110 North: 76x455W Longi LR4-72HPH-455M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 119.138 | 697.8
In operation (COD) | Johan Follestads vei 24, 3474 Åros |  | 113 | 2022-06-14 | 2022-07-07 | 2022-06-14 | 2022-06-13 | 2022-07-07 | 114.66 | Transferred | 🟩 23 days | 23 | ❌ ERROR / Check Date | -1 | 🟩 24 days | 24 | 🟩 189 days | 189 | 🟩 166 days | 166 | 0.11 | 0 | 🟩 All good | 25 | 🟩 768 days left | 💚 All good | 22 - Jul | 2206 | 0 | -97.063492063492 | -0.097063492063 | 🟥 SUM! | 94.0212 | 94,021.2 | 2022 - Q3 | 2022 - Q2 | 2021 - Q4 | 0 | 2,866.5 | 2,866.5 | 955.5 | 0 | 0 | 819.655 | ⌚ 1364 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 2021 | 1.66 | 114.66 | -18.345 | -0.159994767138 | -18.345 | 0 | 0 | -18.345 | -0.159994767138 | 7.253584070796 | 0 | 0 | -0.02 | -18.345 | 0.82 | -18.345 | 0 | 🟩 NoCs: 0 | 0.84 | 0 | 0.82 | 0 | 7.308564451422 | -0.159994767138 | 838 | 7.41592920354 | 0 | 38.257 | 0 | 38.257 | 0 | 0.84 | 0.11 | 0 | 0 | 0 | 7.148569684284 | 0 | 838 | [5 empty] | NTE | thing_7a4b6b3f-7a7f-52eb-aece-d153ed480029 (https://www.notion.so/thing_7a4b6b3f-7a7f-52eb-aece-d153ed480029-226a1d8f955980fe881ccfffb068ae98?pvs=21) | Done |  | Johan Follestads vei 24 |  |  | Does not qualify |  | Medvind Eiendom AS (https://www.notion.so/Medvind-Eiendom-AS-1a7a1d8f95598073832bc64c14b9038c?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Not set | 400 V | Solar as a Service | 135 | 2021-12-30 |  | Ingen tilkomst p.t. Fått OK fra gårdeier på å etablere permanent takstige. Bedt om tilbud fra Trygg Stiger AS (Terje). | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Robert Jernström (https://www.notion.so/Robert-Jernstr-m-1a5a1d8f95598025b2c3dbd0b8e68b6d?pvs=21) | N/A | Approved | 2028-05-09 | Retrofit - GoO earnout | Retrofit not completed |  | Done | NORGESNETT | Done | Completed | JF24 2024 (https://www.notion.so/JF24-2024-188a1d8f955980e5b344d1e3a515a104?pvs=21), JF24 2025 (https://www.notion.so/JF24-2025-218a1d8f95598063883ecf7dfe12acf0?pvs=21) | Default | 1x Sungrow SG110CX | No production (https://www.notion.so/No-production-dcc76b388d864269bc6dda14cdc822cf?pvs=21) | Roof OK | Retrofit |  | Approved | 5706567331884898 (https://www.notion.so/5706567331884898-11aa1d8f955980278d79e6bef8b8f349?pvs=21) |  |  | To be started | Papp | 2022 | 252x455W Longi LR4-72HP H-455M | Done | Not interested |  | Installed | Alex |  |  |  |  | 60.675 | 777.325
In operation (COD) | Espehaugen 49, 5258 Blomsterdalen |  | 145.8 | 2023-03-01 | 2023-10-18 | 2023-03-01 | 2023-03-21 | 2023-10-18 | 148.92 | Transferred | 🟥 231 days | 231 | 🟩 20 days | 20 | 🟥 211 days | 211 | 🟥 566 days | 566 | 🟥 335 days | 335 | 0.15 | 6.414 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 23 - Oct | 2303 | -6.414 | 348.809187279152 | 0.348809187279 | 🟥 SUM! | 109.4562 | 109,456.2 | 2023 - Q4 | 2023 - Q1 | 2022 - Q1 | 0 | 3.723 | 3.723 | 930.75 | 0 | 0 | 1,525,571 | ⌚ 896 days | 0 | 0 | -6.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 2026-12-03 | 148.92 | 203.84 | 1.368788611335 | 197.426 | 0 | 0 | 203.84 | 1.368788611335 | 10.463449931413 | 0 | 0 | 0.2 | 203.84 | 1.53 | 197.426 | 6.414 | 🟩 NoCs: 0 | 1.32 | -0.043070104754 | 1.53 | 0 | 8.875443190975 | 1.325718506581 | 1,321,731 | 9.06537037037 | 0 | 49.43 | 0 | 49.43 | 0 | 1.32 | 0.15 | 0 | 0 | 0 | 10.24423180231 | 0 | 1,321,731 | [5 empty] | NTE | thing_50f28727-8572-5cd4-a531-85f3b47e1da0 (https://www.notion.so/thing_50f28727-8572-5cd4-a531-85f3b47e1da0-24da1d8f955980aa80c0ebc8b416b76b?pvs=21) | Done |  | Espehaugen 49 |  |  | Does not qualify | 600A | Heldal Eiendom AS (https://www.notion.so/Heldal-Eiendom-AS-1a8a1d8f9559804f8ed8e46515aec87d?pvs=21) | Yes - all PPAs | 5258 | Blomsterdalen | Signed |  |  | Not set | 400 V | Solar as a Service | 222 | 2022-03-31 | Eivind Mosevoll (https://www.notion.so/Eivind-Mosevoll-1a5a1d8f9559800092b0e112d1c448bf?pvs=21) | Trapp på utsiden. Kodelås til trapp er 1234 | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Benny Danielsson (https://www.notion.so/Benny-Danielsson-1a5a1d8f95598040a3d3d607c085dc64?pvs=21) | N/A | Approved | 2029-01-15 | Retrofit - GoO earnout | Retrofit not completed | 2023-11-01 | Done | BKK NETT | Done | Completed | E49 2024 (https://www.notion.so/E49-2024-188a1d8f95598063a106c16195d962a1?pvs=21), E49 2025 (https://www.notion.so/E49-2025-200a1d8f955980da823fff14a994020f?pvs=21) | Default | 1x Sungrow SG125CX-P2 | Loss of data (https://www.notion.so/Loss-of-data-131a1d8f9559803abe8dd5adc951a8da?pvs=21), Wrong kWp in SundayOS (https://www.notion.so/Wrong-kWp-in-SundayOS-196a1d8f9559801abcabc7b0ce1c950a?pvs=21) | Roof OK | Retrofit |  | Approved | 6970631401345531 (https://www.notion.so/6970631401345531-11aa1d8f955980f49d94d574e76af9be?pvs=21) |  |  | To be started | Asfaltpapp | 2023 | 292x510W LONGi LR5-66HPH | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 121.85 | 1,199,881
Sold | Svinesundsveien 336, 1789 Berg i Østfold |  | 291 |  |  |  | 2022-06-19 | 2022-09-01 | 291.6 |  | ❌ FID date missing | 0 | ❌ FID date missing | 0 | 🟨 74 days | 74 | 🟩 93 days | 93 | 🟥 1401 days (ongoing) | 1401 | 0.29 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 2026-09-22 | 2206 | 0 | -9,759.63440860215 | -9.759634408602 | 🟥 SUM! | 0 | 0 | 2022 - Q3 |  | 2022 - Q2 | 0 | 0 |  |  | 0 | 0 | 1,093,650 | ⌚ 1308 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 2022 | 0.6 | 291.6 | -907.646 | -3.112640603567 | -907.646 | 0 | 0 | -907.646 | -3.112640603567 | 3.75824742268 | 0 | 0 | -0.91 | -907.646 | 2026-09-01 | -907.646 | 0 | 🟩 NoCs: 0 | 2 | 0 | 2026-09-01 | 0 | 6.863155006859 | -3.112640603567 | 2,001,296 | 6.877305841924 | 0 | 0 | 0 | 0 | 0 | 2 | 0.29 | 0 | 0 | 0 | 3.750514403292 | 0 | 2,001,296 | [7 empty] | N/A |  | Svinesundsveien 336 |  |  |  |  | GG Gruppen AS (https://www.notion.so/GG-Gruppen-AS-1a8a1d8f95598079ab43dc271f13d9a0?pvs=21) |  | 1789 | Berg i Østfold | Signed |  |  | Not set | 400 V | Solar as a Service | 437 | 2022-05-31 | Allen Carlsen (https://www.notion.so/Allen-Carlsen-1a5a1d8f9559800eb9dce1ad7bd5eadf?pvs=21) |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Anne Marte Minge Engh (https://www.notion.so/Anne-Marte-Minge-Engh-1a5a1d8f9559803f950ada0e8645b8e4?pvs=21) | Not uploaded | [5 empty] | Done | ELVIA | Done | Completed |  |  | 2x Sungrow SG110CX |  | Roof OK | TBD | [6 empty] | Papp |  | 648x450W Znshine ZXM6-NH144 | Done |  |  |  | Alex |  |  |  |  | 120 | 1,881,296
In operation (COD) | Ingeniør Rybergs gate 99, 3027 Drammen |  | 81.6 | 2023-03-01 | 2023-07-10 | 2023-03-01 | 2023-04-01 | 2023-07-10 | 81.6 | Transferred | 🟨 131 days | 131 | 🟩 31 days | 31 | 🟨 100 days | 100 | 🟥 320 days | 320 | 🟩 189 days | 189 | 0.08 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 23 - Jul | 2304 | 0 | 429.375 | 0.429375 | 🟥 SUM! | 63.1584 | 63,158.4 | 2023 - Q3 | 2023 - Q1 | 2022 - Q3 | 0 | 2.04 | 2.04 | 2.04 | 0 | 0 | 722.838 | ⌚ 996 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0 | 81.6 | 137.4 | 1.683823529412 | 137.4 | 0 | 0 | 137.4 | 1.683823529412 | 8.858308823529 | 0 | 0 | 0.14 | 137.4 | 0.72 | 165.026 | 0 | 🟩 NoCs: 0 | 0.59 | 0 | 0.72 | 0 | 7.174485294118 | 1.683823529412 | 585.438 | 7.174485294118 | 0 | 0 | 0 | 0 | 0 | 0.59 | 0.08 | 0 | 27.626 | 0 | 8.858308823529 | 0 | 585.438 | [5 empty] | NTE | thing_89accf8a-8074-53d9-b3bf-41db2b0019d2 (https://www.notion.so/thing_89accf8a-8074-53d9-b3bf-41db2b0019d2-1c0a1d8f9559803bb149e8e0f093d4b8?pvs=21) | N/A |  | Ingeniør Rybergs gate 99 |  |  | Does not qualify | 250A | Brække Eiendom AS (https://www.notion.so/Br-kke-Eiendom-AS-1a8a1d8f955980e98516e82f55b2e603?pvs=21) | Yes - all PPAs | 3027 | Drammen | Signed |  |  | Jonas | 230 V | Solar as a Service | 215.5 | 2022-08-24 | Allen Carlsen (https://www.notion.so/Allen-Carlsen-1a5a1d8f9559800eb9dce1ad7bd5eadf?pvs=21) | For å komme inn til tavle bruk kode 1349 på hoveddøren og kode 134212 til døren i andre etasje, som tar deg videre til teknisk rom. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Dragan Zoric (https://www.notion.so/Dragan-Zoric-1a5a1d8f955980878e29d59ffb12fb90?pvs=21) | N/A | Approved | 2028-11-13 | Retrofit - GoO earnout | Applied |  | Done | GLITRE | Done | Completed | IRG99 2025 (https://www.notion.so/IRG99-2025-209a1d8f9559806a8cfcf441a536d329?pvs=21) | Default | 1x Solis 60K-5G-LV | 50kW inverter instead of 60kW (https://www.notion.so/50kW-inverter-instead-of-60kW-df8390168152492daa61d1e6ed2e40d4?pvs=21), PV Ground Fault (https://www.notion.so/PV-Ground-Fault-a5b0b17b74504fcea19020f5f4f0ce7d?pvs=21), Production data seems too low (https://www.notion.so/Production-data-seems-too-low-b002fc857b4c40dfbff8125896d323ba?pvs=21), Ingeniør Rybers gate underperforming (https://www.notion.so/Ingeni-r-Rybers-gate-underperforming-9f80bed33237413aa0fdda66923a02e9?pvs=21), Inv 1: DC Over Voltage + PV Ground Fault (https://www.notion.so/Inv-1-DC-Over-Voltage-PV-Ground-Fault-e88e4b9de8964255b3fd0ed9b6bc7316?pvs=21), No data for drammen padel and rush (https://www.notion.so/No-data-for-drammen-padel-and-rush-138a1d8f95598003848fdad86806328c?pvs=21), No contact with inverter og MID meter (https://www.notion.so/No-contact-with-inverter-og-MID-meter-1b3a1d8f955980cfabb0df3cd6fcf8de?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992902115376 (https://www.notion.so/7359992902115376-11aa1d8f9559800fb03cc7587fb020c8?pvs=21), 7359992908383687 (https://www.notion.so/7359992908383687-306a1d8f955980218984fb28c5d6f90e?pvs=21) |  |  | Done | PVC | 2018 | 160x510W Longi LR5-66HPH 510M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 80 | 505.438
In operation (COD) | Jeksleveien 51, 2016 Frogner |  | 234 | 2023-05-02 | 2022-09-19 | 2023-05-02 | 2022-07-21 | 2022-09-19 | 234 | Transferred | ❌ ERROR / Check Date | -225 | ❌ ERROR / Check Date | -285 | 🟩 60 days | 60 | 🟩 138 days | 138 | 🟥 363 days | 363 | 0.23 | 0 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 2026-09-22 | 2207 | 0 | 990.347826086957 | 0.990347826087 | 🟥 SUM! | 186.732 | 186.732 | 2022 - Q3 | 2023 - Q2 | 2022 - Q2 | 0 | 5.85 | 5.85 | 5.85 | 0 | 0 | 2,038,148 | ⌚ 1290 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 2022 | 0 | 234 | 136.668 | 0.584051282051 | 136.668 | 0 | 0 | 136.668 | 0.584051282051 | 8.710034188034 | 0 | 0 | 0.14 | 136.668 | 2026-04-02 | 164.58 | 0 | 🟩 NoCs: 0 | 2026-09-01 | 0 | 2026-04-02 | 0 | 8.125982905983 | 0.584051282051 | 1,901,480 | 8.125982905983 | 0 | 0 | 0 | 0 | 0 | 2026-09-01 | 0.23 | 0 | 27.912 | 0 | 8.710034188034 | 0 | 1,901,480 | [5 empty] | NTE | thing_9e89fcb2-ee56-4227-ba2e-63f31fdb905b (https://www.notion.so/thing_9e89fcb2-ee56-4227-ba2e-63f31fdb905b-169ba12b3892492a82cba01bacd8941f?pvs=21) | Done |  | Jeksleveien 51 |  |  | Does not qualify | 400A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 51 AS (https://www.notion.so/KLP-Jeksleveien-51-AS-31fa1d8f9559804b953beb358fb015c1?pvs=21) | Not set | 400 V | Solar as a Service | 297 | 2022-05-04 |  | Stige på utsiden fra 2. etasje. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Siri Ørewall (https://www.notion.so/Siri-rewall-1a5a1d8f95598060b317ea989f1d26ed?pvs=21) | N/A | Approved | 2029-01-15 | Retrofit - GoO earnout | Applied |  | Done | ELVIA | Done | Completed | J51 2024 (https://www.notion.so/J51-2024-188a1d8f9559802bbb37c320699b94f2?pvs=21), J51 2025 (https://www.notion.so/J51-2025-213a1d8f9559803e85d8fa4f769d7eba?pvs=21) | Default | 1x Sungrow SG110CX, 1x Solis 110K-5G-PRO | Wrong kWp in SolarLog (https://www.notion.so/Wrong-kWp-in-SolarLog-12dea00ec96d48619a2ac6ea9700f62e?pvs=21), Wrong kWp in SundayOS (https://www.notion.so/Wrong-kWp-in-SundayOS-196a1d8f9559801abcabc7b0ce1c950a?pvs=21), No data in SundayOS (https://www.notion.so/No-data-in-SundayOS-21da1d8f955980938fd9c74c38c29b1a?pvs=21), SundayBox offline (https://www.notion.so/SundayBox-offline-224a1d8f955980e588b3d6f564410c61?pvs=21), 20% production deviation in June (https://www.notion.so/20-production-deviation-in-June-229a1d8f9559806288bbefdf9585771c?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992926668575 (https://www.notion.so/7359992926668575-11aa1d8f955980dd9277e8292d74f564?pvs=21), 7359992936318804 (https://www.notion.so/7359992936318804-159a1d8f955980bc9974d7ff37a956c9?pvs=21) |  |  | Done | PVC | 2022 | 520x450W Znshine ZXM6-NH14 4-450W | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 160.237 | 1,741,243
In operation (COD) | Orkidehøgda 3, 3050 Mjøndalen |  | 379.62 | 2023-07-06 | 2024-03-12 | 2023-07-06 | 2023-08-28 | 2024-03-12 | 379.62 | Transferred | 🟥 250 days | 250 | 🟨 53 days | 53 | 🟥 197 days | 197 | 🟥 515 days | 515 | 🟨 265 days | 265 | 0.38 | 0 | 🟩 All good | 25 | 🟩 1270 days left | 💚 All good | 24 - Mar | 2308 | 0 | 1,134.815533980583 | 1.134815533981 | 🟥 SUM! | 295.34436 | 295,344.36 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 9,490.5 | 9,490.5 | 16,608.375 | 0 | 0 | 3,106,200 | ⌚ 750 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 379.62 | 584.43 | 1.539513197408 | 584.43 | 0 | 0 | 584.43 | 1.539513197408 | 8.182392919235 | 0 | 0 | 0.58 | 584.43 | 2026-11-03 | 602.435 | 0 | 🟩 NoCs: 0 | 2.52 | 0 | 2026-11-03 | 0 | 6.642879721827 | 1.539513197408 | 2,521,770 | 6.642879721827 | 0 | 0 | 0 | 0 | 0 | 2.52 | 0.38 | 0 | 18.005 | 0 | 8.182392919235 | 0 | 2,521,770 | [5 empty] | NTE | thing_e991b105-9ed7-5e18-940e-6c8eab7a27b9 (https://www.notion.so/thing_e991b105-9ed7-5e18-940e-6c8eab7a27b9-226a1d8f955980359c6ff07f2035c81e?pvs=21) | Done |  | Orkidehøgda 3 |  |  | Does not qualify | 420A | Elena Holding AS (https://www.notion.so/Elena-Holding-AS-1a8a1d8f9559806d9a41fee197f18e43?pvs=21) | Yes - all PPAs | 3050 | Mjøndalen | Signed |  |  | Alex | 400 V | Solar as a Service | 277 | 2022-10-14 | Johnny Irby (https://www.notion.so/Johnny-Irby-1a5a1d8f955980cbb408d3bccc4f25f9?pvs=21) | Det er inspeksjonsstige montert til fasade med ryggsøyle opp til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | N/A | Approved | 2029-09-23 | Retrofit - GoO earnout | To be applied |  | Done | GLITRE | Done | Completed | O3 (Vita) 2025 (https://www.notion.so/O3-Vita-2025-224a1d8f955980ad8868e9ff6052c99b?pvs=21) | Default | 2x Solis 110K-5G-PRO, 1x Solis S5-GC60K | Missing FDV for AC (https://www.notion.so/Missing-FDV-for-AC-4cea8de6943942879f02e928143f2ff2?pvs=21), High temperature in AC cables (https://www.notion.so/High-temperature-in-AC-cables-1f4a1d8f9559805a9601d70b1c31b98a?pvs=21), Plant switched off due to retrofit of smart meter (https://www.notion.so/Plant-switched-off-due-to-retrofit-of-smart-meter-213a1d8f95598002bd1dd8d3ddbbd7b0?pvs=21), Consumption registered and invoice received from grid owner (https://www.notion.so/Consumption-registered-and-invoice-received-from-grid-owner-23fa1d8f95598058ae77ea512ec0b9ee?pvs=21), Underdimensioned fuse and cables (https://www.notion.so/Underdimensioned-fuse-and-cables-259a1d8f955980978917d3c0a65e4b62?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992892867200 (https://www.notion.so/7359992892867200-11aa1d8f955980b6804ed7ec31bdfb7e?pvs=21), 7359992930270849 (https://www.notion.so/7359992930270849-229a1d8f955980d09fa5ddcdaf67cd39?pvs=21) |  |  | Done | Papp og PVC | 2011 | 684x555W LONGi LR5-72HPH-555M | Done | Not started |  | Installed | Kjetil |  |  |  |  | 70 | 2,451,770
In operation (COD) | Orkidehøgda 3, 3050 Mjøndalen |  | 274.17 | 2023-07-06 | 2024-03-12 | 2023-07-06 | 2023-08-28 | 2024-03-12 | 274.17 | Transferred | 🟥 250 days | 250 | 🟨 53 days | 53 | 🟥 197 days | 197 | 🟥 515 days | 515 | 🟨 265 days | 265 | 0.27 | 0 | 🟩 All good | 25 | 🟩 1270 days left | 💚 All good | 24 - Mar | 2308 | 0 | 715.493203883495 | 0.715493203883 | 🟥 SUM! | 213.30426 | 213,304.26 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 6,854.25 | 6,854.25 | 11,994.9375 | 0 | 0 | 2,448,102 | ⌚ 750 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 274.17 | 368.479 | 1.343980012401 | 368.479 | 0 | 0 | 368.479 | 1.343980012401 | 8.929138855455 | 0 | 0 | 0.37 | 368.479 | 2.45 | 403.789 | 0 | 🟩 NoCs: 0 | 2026-08-02 | 0 | 2.45 | 0 | 7.585158843054 | 1.343980012401 | 2,079,623 | 7.585158843054 | 0 | 0 | 0 | 0 | 0 | 2026-08-02 | 0.27 | 0 | 35.31 | 0 | 8.929138855455 | 0 | 2,079,623 |  |  |  | Kvalifiserer ikke pga nybygg |  | NTE | thing_91b44343-dd37-5db1-a1e7-d13c3199cc21 (https://www.notion.so/thing_91b44343-dd37-5db1-a1e7-d13c3199cc21-226a1d8f955980eb9a34fc65f287383a?pvs=21) | Done |  | Orkidehøgda 3 |  |  | Does not qualify | 900A | Elena Holding AS (https://www.notion.so/Elena-Holding-AS-1a8a1d8f9559806d9a41fee197f18e43?pvs=21) | Yes - all PPAs | 3050 | Mjøndalen | Signed |  |  | Alex | 230 V | Solar as a Service | 441 | 2022-10-14 | Johnny Irby (https://www.notion.so/Johnny-Irby-1a5a1d8f955980cbb408d3bccc4f25f9?pvs=21) | Ut gjennom vindu i andre etasje. Stige er fastmontert for de to neste nivåene opp til hovedtaket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | Uploaded FDV | Approved | 2029-09-23 | Retrofit - GoO earnout | Applied |  | Done | GLITRE | Done | Completed | O3 (Validus) 2025 (https://www.notion.so/O3-Validus-2025-224a1d8f9559808eb2d1f8b3565c9c7b?pvs=21) | Default | 3x Solis 60K-LV-5G | Two inverters with No Grid (https://www.notion.so/Two-inverters-with-No-Grid-ce4b051d0e334863bd1f4918a804a59b?pvs=21), Missing FDV for AC (https://www.notion.so/Missing-FDV-for-AC-4cea8de6943942879f02e928143f2ff2?pvs=21), Fuse went out again (https://www.notion.so/Fuse-went-out-again-6da3695a36934b41a623e67e6d2bdeb9?pvs=21), No Grid (https://www.notion.so/No-Grid-12da1d8f9559805e8560ef9b825ce28e?pvs=21), Inverter offline (https://www.notion.so/Inverter-offline-1c2a1d8f9559800cbc87fe6e70d83256?pvs=21), INV1+INV3 not producing (https://www.notion.so/INV1-INV3-not-producing-1dea1d8f95598057ab4efffa74f26a3f?pvs=21), Fuse tripping regularly (https://www.notion.so/Fuse-tripping-regularly-1dfa1d8f955980d3b0c2dbff8ea16677?pvs=21), Grid No Grid (https://www.notion.so/Grid-No-Grid-23ba1d8f955980029c2be7ae3fa37f8a?pvs=21), Underdimensioned fuse and cables (https://www.notion.so/Underdimensioned-fuse-and-cables-257a1d8f95598094a382ce7cd6d73abd?pvs=21) | Roof OK | Retrofit | Generell henvendelse sendt uke 14.11.04: Søkt om unntak for søknadsplikt til PBE. Godkjent hos Drammen kommune. | Approved | 7359992895565172 (https://www.notion.so/7359992895565172-11aa1d8f9559808db7b8ddb506cebaec?pvs=21), 7359992894256286 (https://www.notion.so/7359992894256286-1f3a1d8f95598068af21d3ce3f89b1f7?pvs=21) |  |  | Done | Papp | 2020 | 494x555W LONGi LR5-72HPH-555M | Done | Not started |  | Installed | Kjetil |  |  |  |  | 335 | 1,744,623
In operation (COD) | Johan Follestads vei 7, 3474 Åros |  | 288 | 2023-06-15 | 2023-10-13 | 2023-06-15 | 2023-07-10 | 2023-10-13 | 288 | Transferred | 🟨 120 days | 120 | 🟩 25 days | 25 | 🟨 95 days | 95 | 🟥 378 days | 378 | 🟨 258 days | 258 | 0.29 | 0 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 23 - Oct | 2307 | 0 | 851.851851851852 | 0.851851851852 | 🟥 SUM! | 236.16 | 236.16 | 2023 - Q4 | 2023 - Q2 | 2022 - Q3 | 0 | 7.2 | 7.2 | 7.2 | 0 | 0 | 2,438,516 | ⌚ 901 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0 | 288 | 322 | 1.118055555556 | 322 | 0 | 0 | 322 | 1.118055555556 | 8.467069444444 | 0 | 0 | 0.32 | 322 | 2.44 | 342.155 | 0 | 🟩 NoCs: 0 | 2026-12-02 | 0 | 2.44 | 0 | 7.349013888889 | 1.118055555556 | 2,116,516 | 7.349013888889 | 0 | 0 | 0 | 0 | 0 | 2026-12-02 | 0.29 | 0 | 20.155 | 0 | 8.467069444444 | 0 | 2,116,516 | [5 empty] | NTE | thing_e59e7cc9-8b19-52d5-8279-5f86fe48d4c1 (https://www.notion.so/thing_e59e7cc9-8b19-52d5-8279-5f86fe48d4c1-226a1d8f955980679df5d741c4952e16?pvs=21), thing_5e794ff7-2dc9-54c5-b04e-b82870bb78a5 (https://www.notion.so/thing_5e794ff7-2dc9-54c5-b04e-b82870bb78a5-226a1d8f955980d3a8e6f2971779637c?pvs=21) | Done |  | Johan Follestads vei 7 |  |  | Does not qualify |  | Xania Group AS (https://www.notion.so/Xania-Group-AS-1a8a1d8f955980b8a252c1e587125d45?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Jonas | 400 V | Solar as a Service | 288 | 2022-09-30 | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Inspeksjonsstige på utsiden opp to nivåer og helt til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | N/A | Approved | 2029-01-15 | Retrofit - GoO earnout | Applied |  | Done | NORGESNETT | Done | Completed | JF7 2024 (https://www.notion.so/JF7-2024-188a1d8f955980f7a04bf9c16ef8eb30?pvs=21), JF7 2025 (https://www.notion.so/JF7-2025-213a1d8f955980339006e0f716fae369?pvs=21) | Default | 2x Solis S5-GC110K-5G | No data from Solar log (https://www.notion.so/No-data-from-Solar-log-86c6f5f480fd4c52a8428b4ee8075c66?pvs=21), Strange production curve (https://www.notion.so/Strange-production-curve-e74918f92ece4343bf75b45679cc83f7?pvs=21), No ‘plusskunde’ on AMS (https://www.notion.so/No-plusskunde-on-AMS-bd08900697c74709a83e0193889cd0a2?pvs=21), Issues retrofit AMS & SundayBox connectivity (https://www.notion.so/Issues-retrofit-AMS-SundayBox-connectivity-261a1d8f955980a5acece67955679afd?pvs=21) | Roof OK | Retrofit | Ferdigattest sendt. | Approved | 5706567291195447 (https://www.notion.so/5706567291195447-11aa1d8f955980c28c83c74cc41e73aa?pvs=21), 5706567337624184 (https://www.notion.so/5706567337624184-250a1d8f95598090bb29dcc0299e7246?pvs=21) |  |  | Done | Papp | 2012 (øst) / 2023 (vest) | 576x500W LONGi LR5-66HPH-500M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 120 | 1,996,516
In operation (COD) | Johan Follestads vei 27, 3474 Åros |  | 105.6 | 2023-07-06 | 2023-11-03 | 2023-07-06 | 2023-08-08 | 2023-11-03 | 105.6 | N/A | 🟨 120 days | 120 | 🟩 33 days | 33 | 🟨 87 days | 87 | 🟩 122 days | 122 | 🟩 2 days | 2 | 0.11 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 2026-11-23 | 2308 | 0 | 1,199.959016393443 | 1.199959016393 | 🟥 SUM! | 87.12 | 87.12 | 2023 - Q4 | 2023 - Q3 | 2023 - Q3 | 0 | 5.28 | 5,443.68 | 5,443.68 | 0 | 0 | 914 | ⌚ 880 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 0 | 105.6 | 146.395 | 1.386316287879 | 146.395 | 0 | 0 | 146.395 | 1.386316287879 | 8.655303030303 | 0 | 0 | 0.15 | 146.395 | 0.91 | 146.395 | 0 | 🟩 NoCs: 0 | 0.77 | 0 | 0.91 | 0 | 7.268986742424 | 1.386316287879 | 767.605 | 7.268986742424 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0.11 | 0 | 0 | 0 | 8.655303030303 | 0 | 767.605 | [5 empty] | Legacy |  | Done |  | Johan Follestads vei 27 |  |  |  |  | Medvind Eiendom AS (https://www.notion.so/Medvind-Eiendom-AS-1a7a1d8f95598073832bc64c14b9038c?pvs=21) | Not relevant | 3474 | Åros | Signed |  |  | Not set | 400 V | Project Sales | 146 | 2023-07-04 |  | Stige på terrasse/mesanin i andre etasje. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Henrik Johansen (https://www.notion.so/Henrik-Johansen-1a5a1d8f955980349aebc709c87a5674?pvs=21) | N/A |  |  | Not relevant |  |  | Done | NORGESNETT | Done | Completed |  |  | 1x Solis-110K-5G-Pro | JFV27 is too large in Solar-Log (https://www.notion.so/JFV27-is-too-large-in-Solar-Log-46b20443bd8048ad8e1f21dcf2424183?pvs=21) | Roof OK | No |  | Not applicable | 5706567329635211 (https://www.notion.so/5706567329635211-11aa1d8f955980748105fcd69b758bcf?pvs=21) |  |  | Not relevant | Papp | 2023 | 192x550W LONGi LR5-72HPH-550 | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 60 | 707.605
In operation (COD) | Fiboveien 8, 4580 Lyngdal |  | 163.17 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 163.17 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.16 | 0 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | 0 | 410.955752212389 | 0.410955752212 | 🟥 SUM! | 140.97888 | 140,978.88 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 4,079.25 | 4,079.25 | 7,478.625 | 0 | 0 | 1,360,948 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 163.17 | 185.752 | 1.138395538396 | 185.752 | 0 | 0 | 185.752 | 1.138395538396 | 8.340675369247 | 0 | 0 | 0.19 | 185.752 | 1.36 | 185.752 | 0 | 🟩 NoCs: 0 | 1.18 | 0 | 1.36 | 0 | 7.202279830851 | 1.138395538396 | 1,175,196 | 7.202279830851 | 0 | 0 | 0 | 0 | 0 | 1.18 | 0.16 | 0 | 0 | 0 | 8.340675369247 | 0 | 1,175,196 | [5 empty] | NTE | thing_b9ed3273-afa4-5d22-b189-c2a767a626ab (https://www.notion.so/thing_b9ed3273-afa4-5d22-b189-c2a767a626ab-22ca1d8f95598080981dcd2398ebc66d?pvs=21) | Done |  | Fiboveien 8 |  |  | Does not qualify | 250A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Yes - all PPAs | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 218 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget opp to nivåer på utsiden. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | N/A | Approved | 2029-03-11 | GoO priced in APA | Not relevant |  | Done | GLITRE | Done | Completed | F8 2025 (https://www.notion.so/F8-2025-23ea1d8f95598044b7e2f285ad4036fa?pvs=21) | Default | 1x Sungrow SG125CX-P2 | Modem is offline (https://www.notion.so/Modem-is-offline-b42d5253f0b24390ba524ab56f5aa6dd?pvs=21), Plant offline (https://www.notion.so/Plant-offline-e787330daf0648bcace54d0f1fa2c028?pvs=21) | Roof OK | Yes |  | Approved |  |  |  | Not relevant | Papp | 2015 | 294x555W LONGi LR5-72HPH 555M | Done | Not interested | Siri sender inn - inkl samtykkeerklæring | Installed | Kjetil |  |  |  |  | 108.264 | 1,066,932
In operation (COD) | Fiboveien 12C, 4580 Lyngdal |  | 233.1 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 233.1 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.23 | 0 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | 0 | 715.62389380531 | 0.715623893805 | 🟥 SUM! | 201.3984 | 201,398.4 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 5,827.5 | 5,827.5 | 10,683.75 | 0 | 0 | 1,932,406 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 233.1 | 323.462 | 1.387653367653 | 323.462 | 0 | 0 | 323.462 | 1.387653367653 | 8.29003003003 | 0 | 0 | 0.32 | 323.462 | 1.93 | 323.462 | 0 | 🟩 NoCs: 0 | 1.61 | 0 | 1.93 | 0 | 6.902376662377 | 1.387653367653 | 1,608,944 | 6.902376662377 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0.23 | 0 | 0 | 0 | 8.29003003003 | 0 | 1,608,944 | [5 empty] | NTE | thing_c10d6b5c-aaef-5bdc-ad03-b7a5f5d2e711 (https://www.notion.so/thing_c10d6b5c-aaef-5bdc-ad03-b7a5f5d2e711-22ca1d8f95598050987ac86b9cf1f87a?pvs=21) | Done |  | Fiboveien 12C |  |  | Does not qualify | 250A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Pending | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 236 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget hos Plantasjen. Må inn via Plantasjen sitt uteområdet. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | N/A | Approved | 2029-03-11 | GoO priced in APA | Not relevant |  | Done | GLITRE | Done | Completed | F12C 2025 (https://www.notion.so/F12C-2025-23ea1d8f9559804abc92cf6ef44b9032?pvs=21) | Default | 1x Sungrow SG125CX-P2, 1x Sungrow SG33CX | No production data (https://www.notion.so/No-production-data-22aa1d8f955980979183f0d11271dfe2?pvs=21) | Roof OK | Yes |  | Approved | 5706567333536269 (https://www.notion.so/5706567333536269-11aa1d8f955980b18b8bdf4e5a1409b3?pvs=21) |  |  | Not relevant | PVC | 2018 | 420x555W LONGi LR5-72HPH | Done | Not interested | 07.03: ok | Installed | Kjetil |  |  |  |  | 100 | 1,508,944
In operation (COD) | Fiboveien 12D, 4580 Lyngdal |  | 113.22 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 113.22 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.11 | 0 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | 0 | 317.79203539823 | 0.317792035398 | 🟥 SUM! | 97.82208 | 97,822.08 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 2,830.5 | 2,830.5 | 5,189.25 | 0 | 0 | 938.597 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 113.22 | 143.642 | 1.268698109875 | 143.642 | 0 | 0 | 143.642 | 1.268698109875 | 8.290028263558 | 0 | 0 | 0.14 | 143.642 | 0.94 | 143.642 | 0 | 🟩 NoCs: 0 | 0.79 | 0 | 0.94 | 0 | 7.021330153683 | 1.268698109875 | 794.955 | 7.021330153683 | 0 | 0 | 0 | 0 | 0 | 0.79 | 0.11 | 0 | 0 | 0 | 8.290028263558 | 0 | 794.955 | [5 empty] | NTE | thing_33422e6f-7250-54df-b774-19c645f434d8 (https://www.notion.so/thing_33422e6f-7250-54df-b774-19c645f434d8-22ca1d8f9559802986ece8938e79b06f?pvs=21) | Done |  | Fiboveien 12D |  |  | Does not qualify | 200A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Pending | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 117 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget hos Plantasjen. Må inn via Plantasjen sitt uteområdet. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | N/A | Approved | 2029-03-11 | GoO priced in APA | Not relevant |  | Done | GLITRE | Done | Completed | F12D 2025 (https://www.notion.so/F12D-2025-23ea1d8f95598047a577cccda12794fc?pvs=21) | Default | 1x Sungrow SG125CX-P2 | AC-cables disconnected due to construction work (https://www.notion.so/AC-cables-disconnected-due-to-construction-work-203a1d8f955980989b49d48b9cf91a05?pvs=21) | Roof OK | Yes |  | Approved | 5706567333536276 (https://www.notion.so/5706567333536276-11aa1d8f955980e19adadfa2295c7553?pvs=21) |  |  | Not relevant | PVC | 2018 | 204x555W LONGi LR5-72HPH | Done | Not interested | Siri følger opp | Installed | Kjetil |  |  |  |  | 100 | 694.955
In operation (COD) | Fiboveien 14A, 4580 Lyngdal |  | 188.7 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 188.7 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.19 | 19.582 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | -19.582 | 470.006637168142 | 0.470006637168 | 🟥 SUM! | 163.0368 | 163,036.8 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 4,717.5 | 4,717.5 | 8,648.75 | 0 | 0 | 1,563,442 | ⌚ 785 days | 0 | 0 | -19.582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 188.7 | 232.025 | 1.229597244303 | 212.443 | 0 | 0 | 232.025 | 1.229597244303 | 8.285331213567 | 0 | 0 | 0.23 | 232.025 | 1.56 | 425.905 | 19.582 | 🟩 NoCs: 0 | 1.33 | -0.10377318495 | 1.56 | 0 | 7.055733969263 | 1.125824059353 | 1,331,417 | 7.055733969263 | 0 | 0 | 0 | 0 | 213.462 | 1.33 | 0.19 | 0 | 0 | 213.462 | 8.285331213567 | 0 | 1,331,417 | [5 empty] | NTE | thing_c2fdc8de-99d6-54f5-b3a8-bb107f7c56ab (https://www.notion.so/thing_c2fdc8de-99d6-54f5-b3a8-bb107f7c56ab-22ca1d8f95598049880fe67fd9c9020b?pvs=21) | Done |  | Fiboveien 14A |  |  | Does not qualify | 500A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Pending | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 365 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget hos Plantasjen. Må inn via Plantasjen sitt uteområdet. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | N/A | Approved | 2029-03-11 | GoO priced in APA | Not relevant |  | Done | GLITRE | Done | Completed | F14A 2025 (https://www.notion.so/F14A-2025-23ea1d8f955980e49173d5c364d3ea47?pvs=21) | Default | 1x Sungrow SG125CX-P2 | Inverter cuts production at 115 kW (https://www.notion.so/Inverter-cuts-production-at-115-kW-b91d73ea88674160bc25cf9e2a509b2a?pvs=21), Wrong kWp in SolarLog (https://www.notion.so/Wrong-kWp-in-SolarLog-27ecbe9ac2254ae6873747753a77f7ca?pvs=21), Capped production (https://www.notion.so/Capped-production-8a4cf2e0d9614d7fbeb1ce7d1c99349c?pvs=21) | Roof OK | Yes |  | Approved | 5706567333537235 (https://www.notion.so/5706567333537235-11aa1d8f9559802eb979eabb64ba2a46?pvs=21), 5706567293632094 (https://www.notion.so/5706567293632094-28da1d8f9559806db1f5d17773aaa8c6?pvs=21) |  |  | Not relevant | Papp | 2018 | 340x555W LONGi LR5-72HPH | Done | In operation | Siri følger opp - sendt med 12E | Installed | Kjetil |  |  |  |  | 100 | 1,231,417
In operation (COD) | Fiboveien 14B, 4580 Lyngdal |  | 367.41 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 365.19 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.37 | 0 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | 0 | 1,220.347345132744 | 1.220347345133 | 🟥 SUM! | 312.96783 | 312,967.83 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 9,129.75 | 9,129.75 | 16,737.875 | 0 | 0 | 3,049,319 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | -2.22 | 365.19 | 551.597 | 1.510438401928 | 551.597 | 0 | 0 | 551,596.56 | 1.510437197075 | 8.299499197082 | 0 | 0 | 0.55 | 551.597 | 2026-05-03 | 551.597 | 0 | 🟩 NoCs: 0 | 2026-05-02 | 0.000001204853 | 2026-05-03 | 0 | 6.839513677812 | 1.510438401928 | 2,497,722.44 | 6.79818850875 | 0 | 0 | 0 | 0 | 0 | 2026-05-02 | 0.37 | 0 | 0 | 0 | 8.349952079739 | 0 | 2,497,722 | [5 empty] | NTE | thing_e5bd69f8-9323-53d5-8a5c-2c75ec56f95d (https://www.notion.so/thing_e5bd69f8-9323-53d5-8a5c-2c75ec56f95d-22ca1d8f955980839f60f65ac6ae00c3?pvs=21) | Done |  | Fiboveien 14B |  |  | Does not qualify | 400A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Pending | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 378 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget hos Plantasjen. Må inn via Plantasjen sitt uteområdet. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | N/A | Approved | 2029-03-11 | GoO priced in APA | Not relevant |  | Done | GLITRE | Done | Completed | F14B 2025 (https://www.notion.so/F14B-2025-23ea1d8f955980b6afcdd406e44a7ffd?pvs=21) | Default | 2x Sungrow SG125CX-P2 | No production data (SolarLog) (https://www.notion.so/No-production-data-SolarLog-207a1d8f9559800fa510ef1d788dd53b?pvs=21), Inverter 1 down (https://www.notion.so/Inverter-1-down-229a1d8f95598015ad3ce06cb91786cc?pvs=21) | Roof OK | Yes |  | Approved | 5706567346205411 (https://www.notion.so/5706567346205411-11aa1d8f955980938a5efac467c7c54c?pvs=21) |  |  | Not relevant | Papp | 2017 | 658x555W LONGi LR5-72HPH | Done | Not interested | Siri følger opp | Installed | Kjetil |  |  |  |  | 106,810.44 | 2,390,912
In operation (COD) | Lundedalen 51, 3940 Porsgrunn |  | 228.69 | 2023-09-04 | 2024-02-27 | 2023-09-04 | 2023-10-10 | 2024-02-27 | 228.69 | Transferred | 🟥 176 days | 176 | 🟩 36 days | 36 | 🟥 140 days | 140 | 🟥 425 days | 425 | 🟨 249 days | 249 | 0.23 | 0 | 🟩 All good | 25 | 🟩 1270 days left | 💚 All good | 2026-02-24 | 2310 | 0 | 909.494117647059 | 0.909494117647 | 🟥 SUM! | 191.64222 | 191,642.22 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 5,717.25 | 5,717.25 | 10,481.625 | 0 | 0 | 1,986,034 | ⌚ 764 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 228.69 | 386.535 | 1.690213826577 | 386.535 | 0 | 0 | 386,534.99715 | 1.690213814115 | 8.684393720757 | 0 | 0 | 0.39 | 386.535 | 1.99 | 386.535 | 0 | 🟩 NoCs: 0 | 2026-06-01 | 1.2462e-8 | 1.99 | 0 | 6.99417989418 | 1.690213826577 | 1,599,499.00285 | 6.994179906642 | 0 | 77.429 | 0 | 77.429 | 0 | 2026-06-01 | 0.23 | 0 | 0 | 0 | 8.684393720757 | 0 | 1,599,499 | [5 empty] | NTE | thing_32ef2664-1364-5544-8592-a14f7ec2abb6 (https://www.notion.so/thing_32ef2664-1364-5544-8592-a14f7ec2abb6-207a1d8f9559804aa569cbf4ddea2791?pvs=21) | Done |  | Lundedalen 51 |  |  | Does not qualify | 1600A | Heistad Utvikling AS (https://www.notion.so/Heistad-Utvikling-AS-1a7a1d8f955980e4807fe4bb32ae8d9f?pvs=21) | Yes - all PPAs | 3940 | Porsgrunn | Signed |  |  | Rikard | 400 V | Solar as a Service | 964 | 2022-12-29 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Kodelås til inspeksjonsstige: 3940 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | N/A | Approved | 2029-09-23 | Retrofit - GoO earnout | Retrofit not completed |  | Done | LEDE | Done | Completed | L51 2025 (https://www.notion.so/L51-2025-218a1d8f955980908868ff3b34bdb372?pvs=21) | Default | 1x Solis 110K-5G-PRO, 1x Solis S5-GC60K | Missing FDV (https://www.notion.so/Missing-FDV-e2beb5492b694b529f386fdb898cb66d?pvs=21), Missing data (https://www.notion.so/Missing-data-5ede88cecd6643b3941047fad5a119df?pvs=21), No production data (https://www.notion.so/No-production-data-1b2a1d8f9559806fa151c48655ec0434?pvs=21), No data inverter 2 (https://www.notion.so/No-data-inverter-2-229a1d8f9559808f80ebc4c9ea94a4ee?pvs=21), No production from MPPT 7 and 8 (https://www.notion.so/No-production-from-MPPT-7-and-8-229a1d8f955980a59ff9fa92952295b4?pvs=21), Grid No Grid (https://www.notion.so/Grid-No-Grid-255a1d8f9559803c8830ea9bcfc0b9b4?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992901822367 (https://www.notion.so/7359992901822367-11aa1d8f9559805a8044cde4f7fb733b?pvs=21) |  | Received | To be started | Papp | 2022 (en mindre andel av taket er eldre) | 462x495W JA Solar JAM66S30 | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 120,000.00285 | 1,479,499
On hold | Vestbyveien 113-115-117, 1543 Vestby |  | 408.32 | 2026-10-01 | 2026-12-31 |  |  |  |  | Appr. awaiting APA | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 1190 days (ongoing) | 1190 | 🟥 1190 days (ongoing) | 1190 | 0.41 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 99.668907563025 | 0.099668907563 | 🟩 OK! | 329.10592 | 329,105.92 |  |  | 2022 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,396,318 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11,860.6 | 0 | 0 |  | 2022 | -408.32 | 408.32 | 118.606 | 0.290473158307 | 118.606 | 0 | 0 | 118.606 | 0.290473158307 | 5.868725509404 | 0 | 0 | 0 | 118.606 | 2026-04-02 | 118.606 | 0 | 🟩 NoCs: 0 | 2.28 | 0 | 2026-04-02 | 0 | 5.578252351097 | 0.290473158307 | 2,277,712 | 5.578252351097 | 0 | 0 | 0 | 0 | 0 | 2.28 | 0 | 0 | 0 | 0 |  | 0 | 2,277,712 |  |  |  | Trenger energimerke | [5 empty] | Vestbyveien 113-115-117 | Bygg Control AS v/ Felix Mediaa Lenning (2011) - Dag Bastiansen (2021) |  | Need new score | 630A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) |  | 1543 | Vestby | Signed |  |  | Rikard | 400 V | Solar as a Service | 380 | 2022-12-28 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status |  |  |  | 2x Solis 110K-5G-PRO 1x Solis S5-GC60K |  |  | TBD | 12.06: Ikke søknadspliktig | Approved | [5 empty] | 2011 | 704x580W Tongwei TWMND-72HD |  |  |  |  | Kjetil |  |  |  |  | 180 | 2,097,712
Cancelled | Skeievegen 76, 5239 Rådal | [9 empty] | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Skeievegen 76 |  |  |  | 1000 A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) |  | 5239 | Rådal |  |  |  | Not set | 230 V | TBD | 219 | [5 empty] | Not uploaded | [5 empty] | Not started | BKK NETT | No status | [13 empty] | Tekket Q dekke
Cancelled | Mjåvannsvegen 128, 4628 Kristiansand |  | 617.12 | [6 empty] | Appr. awaiting APA | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 1190 days (ongoing) | 1190 | 🟥 1190 days (ongoing) | 1190 | 0.62 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 1,055.13025210084 | 1.055130252101 | 🟥 SUM! | 562.81344 | 562,813.44 |  |  | 2022 - Q4 | 0 | 0 |  |  | 0 | 0 | 4,509,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022 | -617.12 | 617.12 | 1,255,605 | 2.034620495204 | 1,255,605 | 0 | 0 | 1,255,605 | 2.034620495204 | 7.306520611875 | 0 | 0 | 0 | 1,255,605 | 4.51 | 1,255,605 | 0 | 🟩 NoCs: 0 | 3.25 | 0 | 4.51 | 0 | 5.271900116671 | 2.034620495204 | 3,253,395 | 5.271900116671 | 0 | 0 | 0 | 0 | 0 | 3.25 | 0 | 0 | 0 | 0 |  | 0 | 3,253,395 |  |  |  | Kvalifiserer ikke pga ingen oppvarmet BRA | [5 empty] | Mjåvannsvegen 128 |  |  | Does not qualify | 630A (not 100% confirmed) | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) |  | 4628 | Kristiansand | Signed |  |  | Not set |  | Solar as a Service | 191 | 2022-12-28 |  |  |  |  | Not uploaded | [5 empty] | Not started | GLITRE | No status |  |  |  | 4x Solis 110kW |  |  |  | 08.08: Sendt søknad om unntak. 23.08: Purret på PBE og fikk til svar at vi må søke. | [5 empty] | Trapesplater | 2007-2009 | 1064x580W Tongwei TW-580Wp | [9 empty] | 240 | 3,013,395
In operation (COD) | Vekstveien 5B, 3474 Åros |  | 158 | 2023-05-30 | 2023-08-28 | 2023-05-30 | 2023-05-30 | 2023-08-28 | 158.4 | Transferred | 🟨 90 days | 90 | 🟩 0 days | 0 | 🟨 90 days | 90 | 🟨 244 days | 244 | 🟩 154 days | 154 | 0.16 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 2026-08-23 | 2305 | 0 | 1,035.245901639344 | 1.035245901639 | 🟥 SUM! | 129.888 | 129.888 | 2023 - Q3 | 2023 - Q2 | 2022 - Q4 | 0 | 3.96 | 3.96 | 3.96 | 0 | 0 | 1,323,305 | ⌚ 947 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0.4 | 158.4 | 252.6 | 1.594696969697 | 252.6 | 0 | 0 | 252.6 | 1.594696969697 | 8.375348101266 | 0 | 0 | 0.25 | 252.6 | 1.32 | 285.403 | 0 | 🟩 NoCs: 0 | 2026-07-01 | 0 | 1.32 | 0 | 6.759501262626 | 1.594696969697 | 1,070,705 | 6.776613924051 | 0 | 0 | 0 | 0 | 0 | 2026-07-01 | 0.16 | 0 | 32.803 | 0 | 8.354198232323 | 0 | 1,070,705 | [5 empty] | NTE | thing_abb303ac-8826-5b9e-b401-0c308bab3eb5 (https://www.notion.so/thing_abb303ac-8826-5b9e-b401-0c308bab3eb5-226a1d8f95598022a66af43b907c859f?pvs=21) | Done |  | Vekstveien 5B |  |  | Does not qualify | 800A | Generator Solutions AS (https://www.notion.so/Generator-Solutions-AS-1a7a1d8f95598018ae34e9409e5dbb70?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Jonas | 400 V | Solar as a Service | 221 | 2022-12-27 | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Inn i bygget og ut mesanin/kantina for så videre med fastmontert inspeksjonsstige med ryggsøyle opp hele veien til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Anne Marte Minge Engh (https://www.notion.so/Anne-Marte-Minge-Engh-1a5a1d8f9559803f950ada0e8645b8e4?pvs=21) | N/A | Approved | 2028-11-13 | Retrofit - GoO earnout | Applied |  | Done | NORGESNETT | Done | Completed | V5B 2024 (https://www.notion.so/V5B-2024-188a1d8f955980c8b542d08ebe91d293?pvs=21), V5B2025 (https://www.notion.so/V5B2025-24ca1d8f95598058aea6f0848fb15474?pvs=21) | Default | 1x Solis 110K-5G-PRO | No production and short circuit (https://www.notion.so/No-production-and-short-circuit-1bca1d8f955980108416d5ef68edc801?pvs=21), System turned off (https://www.notion.so/System-turned-off-209a1d8f9559803180d3ee2bf61e878c?pvs=21), Issues retrofit AMS (https://www.notion.so/Issues-retrofit-AMS-26fa1d8f955980c6b8f6d17a28a72ff4?pvs=21) | Roof OK | Retrofit |  | Not applicable | 5706567313977518 (https://www.notion.so/5706567313977518-11aa1d8f9559807780f4ec2f5c91b8fe?pvs=21), 5706567337624207 (https://www.notion.so/5706567337624207-24fa1d8f9559806d8e0ac797b00a252b?pvs=21) |  |  | Done | PVC | 2019 | 288x Longi LR5-72HPH 550W | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 60 | 1,010,705
In operation (COD) | Johan Follestads vei 25, 3474 Åros |  | 456 | 2023-10-17 | 2024-04-09 | 2023-10-17 | 2023-12-08 | 2024-04-09 | 460.56 | N/A | 🟥 175 days | 175 | 🟨 52 days | 52 | 🟥 123 days | 123 | 🟩 192 days | 192 | 🟩 17 days | 17 | 0.46 | 0 | 🟩 All good |  | ❌ End date missing | ❌ Missing | 2026-04-24 | 2312 | 0 | 2,427.005208333334 | 2.427005208333 | 🟥 SUM! | 377.19864 | 377,198.64 | 2024 - Q2 | 2023 - Q4 | 2023 - Q3 | 0 | 0 |  |  | 0 | 0 | 3,328,800 | ⌚ 722 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 4.56 | 460.56 | 465.985 | 1.01177913844 | 465.985 | 0 | 0 | 465.985 | 1.01177913844 | 2026-03-07 | 0 | 0 | 0.47 | 465.985 | 3.33 | 465.985 | 0 | 🟩 NoCs: 0 | 2.86 | 0 | 3.33 | 0 | 6.215943633837 | 1.01177913844 | 2,862,815 | 6.278103070175 | 0 | 0 | 0 | 0 | 0 | 2.86 | 0.46 | 0 | 0 | 0 | 7.227722772277 | 0 | 2,862,815 | [7 empty] | N/A |  | Johan Follestads vei 25 |  |  |  | 630A | Medvind Eiendom AS (https://www.notion.so/Medvind-Eiendom-AS-1a7a1d8f95598073832bc64c14b9038c?pvs=21) | Not relevant | 3474 | Åros | Signed |  | Røyken Næringspark Invest AS (https://www.notion.so/R-yken-N-ringspark-Invest-AS-311a1d8f955980a48068eea4a9f175d5?pvs=21) | Rikard | 400 V | Project Sales | 456 | 2023-09-30 | Robin Eek Hoel (https://www.notion.so/Robin-Eek-Hoel-1a5a1d8f955980048ad2ff6f3f8f9d74?pvs=21) | Takstige fra bakkenivå | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Per-Christian Vadvedt (https://www.notion.so/Per-Christian-Vadvedt-1a5a1d8f95598095b1d1c3f9c19e0aa1?pvs=21) | N/A |  |  | Not relevant |  |  | Done | NORGESNETT | Done | Completed |  |  | 3x Solis 110K-5G-PRO | Missing SolarLog (https://www.notion.so/Missing-SolarLog-62537ee6471a496d8f648d6fa754918a?pvs=21), Deviations from Bravida inspection (https://www.notion.so/Deviations-from-Bravida-inspection-279a1d8f955980489b30ffe97ab9f3a2?pvs=21) | Roof OK | No |  | Not applicable | 4706567269916739 (https://www.notion.so/4706567269916739-11aa1d8f95598096ae8fc56fa4c1250f?pvs=21) |  |  | Not relevant | Papp | 2023 | 912x505W LONGi LR5-66HPH-505M | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 180 | 2,682,815
In operation (COD) | Vekstveien 5A, 3474 Åros |  | 158 | 2023-05-30 | 2023-08-28 | 2023-05-30 | 2023-05-30 | 2023-08-28 | 158.4 | Transferred | 🟨 90 days | 90 | 🟩 0 days | 0 | 🟨 90 days | 90 | 🟨 244 days | 244 | 🟩 154 days | 154 | 0.16 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 2026-08-23 | 2305 | 0 | 1,035.245901639344 | 1.035245901639 | 🟥 SUM! | 129.888 | 129.888 | 2023 - Q3 | 2023 - Q2 | 2022 - Q4 | 0 | 3.96 | 3.96 | 3.96 | 0 | 0 | 1,323,305 | ⌚ 947 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0.4 | 158.4 | 252.6 | 1.594696969697 | 252.6 | 0 | 0 | 252.6 | 1.594696969697 | 8.375348101266 | 0 | 0 | 0.25 | 252.6 | 1.32 | 285.403 | 0 | 🟩 NoCs: 0 | 2026-07-01 | 0 | 1.32 | 0 | 6.759501262626 | 1.594696969697 | 1,070,705 | 6.776613924051 | 0 | 0 | 0 | 0 | 0 | 2026-07-01 | 0.16 | 0 | 32.803 | 0 | 8.354198232323 | 0 | 1,070,705 | [5 empty] | NTE | thing_eaac0548-5ce0-51f2-835c-323c9dc58361 (https://www.notion.so/thing_eaac0548-5ce0-51f2-835c-323c9dc58361-226a1d8f9559802fbd00fadfda2cdba1?pvs=21) | Done |  | Vekstveien 5A |  |  | Does not qualify | 800A | Scala Bad AS (https://www.notion.so/Scala-Bad-AS-1a7a1d8f955980ed95e3ffa172c9a6c0?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Jonas | 400 V | Solar as a Service | 221 | 2022-12-27 | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Inn i bygget og ut mesanin/kantina for så videre med fastmontert inspeksjonsstige med ryggsøyle opp hele veien til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Anne Marte Minge Engh (https://www.notion.so/Anne-Marte-Minge-Engh-1a5a1d8f9559803f950ada0e8645b8e4?pvs=21) | N/A | Approved | 2028-11-13 | Retrofit - GoO earnout | Applied |  | Done | NORGESNETT | Done | Completed | V5A 2024 (https://www.notion.so/V5A-2024-188a1d8f955980f9a142f5365d18f0d0?pvs=21), V5A 2025 (https://www.notion.so/V5A-2025-24ca1d8f955980869eb1f2726a67264b?pvs=21) | Default | 1x Solis 110K-5G-PRO | System switched off (https://www.notion.so/System-switched-off-1cfa1d8f95598091a620e7ae42241238?pvs=21), No production and short circuit (Error UN-G-V & No Grid) (https://www.notion.so/No-production-and-short-circuit-Error-UN-G-V-No-Grid-1ffa1d8f955980f1a75ec8b63a280533?pvs=21), Issues retrofit AMS (https://www.notion.so/Issues-retrofit-AMS-26fa1d8f955980c6b8f6d17a28a72ff4?pvs=21) | Roof OK | Retrofit |  | Not applicable | 5706567297671426 (https://www.notion.so/5706567297671426-11aa1d8f9559808d878ee6a589cceb16?pvs=21), 5706567337624207 (https://www.notion.so/5706567337624207-24fa1d8f955980aaa216edf9adf3e98d?pvs=21) |  |  | Done | PVC | 2019 | 288x550W LONGi LR5-72HPH | Done | In operation |  | Installed | Kjetil |  |  |  |  | 60 | 1,010,705
In operation (COD) | Longhammarvegen 24, 5536 Haugesund |  | 380 | 2023-06-13 | 2023-11-07 | 2023-06-13 | 2023-07-17 | 2023-11-07 | 383.8 | N/A | 🟨 147 days | 147 | 🟩 34 days | 34 | 🟥 113 days | 113 | 🟨 300 days | 300 | 🟩 153 days | 153 | 0.38 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 2026-11-23 | 2307 | 0 | 1,143.85 | 1.14385 | 🟥 SUM! | 300.5154 | 300,515.4 | 2023 - Q4 | 2023 - Q2 | 2023 - Q1 | 0 | 19.19 | 19,784.89 | 19,784.89 | 0 | 0 | 3,398,032 | ⌚ 876 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 2026-08-03 | 383.8 | 343.155 | 0.894098488796 | 343.155 | 0 | 0 | 343.155 | 0.894098488796 | 8.942189473684 | 0 | 0 | 0.34 | 343.155 | 2026-04-03 | 343.155 | 0 | 🟩 NoCs: 0 | 2026-05-03 | 0 | 2026-04-03 | 0 | 7.959554455446 | 0.894098488796 | 3,054,877 | 8.03915 | 0 | 0 | 0 | 0 | 0 | 2026-05-03 | 0.38 | 0 | 0 | 0 | 8.853652944242 | 0 | 3,054,877 | [5 empty] | Legacy |  | Done |  | Longhammarvegen 24 |  |  |  | 2300A | God Driv AS (https://www.notion.so/God-Driv-AS-1a8a1d8f955980e0ac76fb889741f4e4?pvs=21) | Not relevant | 5536 | Haugesund | Signed |  |  | Jonas | 230 V | Project Sales | 560 | 2023-01-11 | Lars Olav Tveit Olsen (https://www.notion.so/Lars-Olav-Tveit-Olsen-1a5a1d8f95598047a895d0cecc12190d?pvs=21) |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Jahn Røberg (https://www.notion.so/Jahn-R-berg-1a5a1d8f955980a2bc58c156302887ff?pvs=21) | Uploaded FDV |  |  | Not relevant |  |  | Done | FAGNE | Done | Completed |  |  | 5x Solis 60K-LV-5G | No Grid on 3x inverters (https://www.notion.so/No-Grid-on-3x-inverters-21432c01f6724817bbdae513af5fdb62?pvs=21), Incorrect AMS setup (https://www.notion.so/Incorrect-AMS-setup-4d568cdab55b45ae80b838e4f3bd88b1?pvs=21), Multiple inverters offline (https://www.notion.so/Multiple-inverters-offline-57590801144449efa62bfae0eec0511d?pvs=21), No Grid on one inverter(s) (https://www.notion.so/No-Grid-on-one-inverter-s-443d5fe5f55b493fa8c592969fa2debe?pvs=21) | Roof OK | No |  | Not applicable | 6970631400483838 (https://www.notion.so/6970631400483838-11aa1d8f95598079bdc1e0222a125f03?pvs=21) |  |  | Not relevant | PVC |  | 760x505W LONGi LR5-66HPH 505M | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 300 | 2,754,877
In operation (COD) | Smemyrveien 1, 3474 Åros |  | 144 | 2023-06-21 | 2023-09-05 | 2023-06-21 | 2023-07-10 | 2023-09-05 | 145.44 | Transferred | 🟨 76 days | 76 | 🟩 19 days | 19 | 🟩 57 days | 57 | 🟨 222 days | 222 | 🟩 146 days | 146 | 0.14 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 2026-09-23 | 2307 | 0 | 1,139.900900900901 | 1.139900900901 | 🟥 SUM! | 119.2608 | 119,260.8 | 2023 - Q3 | 2023 - Q2 | 2023 - Q1 | 0 | 3.636 | 3.636 | 909 | 0 | 0 | 1,271,009 | ⌚ 939 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 1.44 | 145.44 | 253.058 | 1.739947744774 | 253.058 | 0 | 0 | 253.058 | 1.739947744774 | 8.826451388889 | 0 | 0 | 0.25 | 253.058 | 1.27 | 253.058 | 0 | 🟩 NoCs: 0 | 2026-02-01 | 0 | 1.27 | 0 | 6.999113036304 | 1.739947744774 | 1,017,951 | 7.069104166667 | 0 | 48.753 | 0 | 48.753 | 0 | 2026-02-01 | 0.15 | 0 | 0 | 0 | 8.739060781078 | 0 | 1,017,951 | [5 empty] | NTE | thing_a2deab38-8e10-514a-957b-d43f9426bd53 (https://www.notion.so/thing_a2deab38-8e10-514a-957b-d43f9426bd53-226a1d8f95598013b2e6f9e00157faaa?pvs=21) | Done |  | Smemyrveien 1 |  |  | Does not qualify | 200A | Stenseth & RS Entreprenør AS (https://www.notion.so/Stenseth-RS-Entrepren-r-AS-1a7a1d8f9559804b9c78cb84eab0a716?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Not set | 400 V | Solar as a Service | 151 | 2023-01-26 |  | Fra bakkenivå, så går det spiraltrapp opp ett nivå. Så er det fastmontert inspeksjonsstige med ryggsøyle opp resten av veien til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Branko Culjak (https://www.notion.so/Branko-Culjak-1a5a1d8f95598026b553fc108d980ae0?pvs=21) | Uploaded FDV | Approved | 2028-11-13 | Retrofit - GoO earnout | Retrofit not completed |  | Done | NORGESNETT | Done | Completed | S1 2024 (https://www.notion.so/S1-2024-188a1d8f955980a1a5dacc14f7ae2761?pvs=21), S1 2025 (https://www.notion.so/S1-2025-224a1d8f9559807db653d82f7b943469?pvs=21) | Default | 1x Solis 110K-5G-PRO |  | Roof OK | Retrofit |  | Not applicable | 5706567291195492 (https://www.notion.so/5706567291195492-11aa1d8f955980379c3bd759761caea4?pvs=21) |  |  | To be started | PVC | 2010 | 288x505W LONGi Hi-MO LR5-66HPH | Done | In operation |  | Installed | Kjetil |  |  |  |  | 90.5 | 927.451
In operation (COD) | Jeksleveien 47, 2016 Frogner |  | 181.5 | 2023-05-29 | 2023-10-27 | 2023-05-29 | 2023-10-06 | 2023-10-27 | 184.8 | Transferred | 🟥 151 days | 151 | 🟥 130 days | 130 | 🟩 21 days | 21 | 🟨 241 days | 241 | 🟩 90 days | 90 | 0.18 | 4.85 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 23 - Oct | 2310 | -4.85 | 1,075.477178423236 | 1.075477178423 | 🟥 SUM! | 147.4704 | 147,470.4 | 2023 - Q4 | 2023 - Q2 | 2023 - Q1 | 0 | 4.62 | 4.62 | 1.925 | 0 | 0 | 1,543,560 | ⌚ 887 days | 0 | 0 | -4.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 2026-03-03 | 184.8 | 264.04 | 1.428787878788 | 259.19 | 0 | 0 | 264.04 | 1.428787878788 | 8.504462809917 | 0 | 0 | 0.26 | 264.04 | 1.54 | 280.735 | 4.85 | 🟩 NoCs: 0 | 1.28 | -0.026244588745 | 1.54 | 0 | 6.92380952381 | 1.402543290043 | 1,279,520 | 7.049696969697 | 0 | 0 | 0 | 0 | 0 | 1.28 | 0.18 | 0 | 21.545 | 0 | 8.352597402597 | 0 | 1,279,520 | [5 empty] | NTE | thing_46d2cf5e-9cde-503f-b91e-24dcf75916a5 (https://www.notion.so/thing_46d2cf5e-9cde-503f-b91e-24dcf75916a5-20aa1d8f9559804facc7cb73306182c3?pvs=21) | Done |  | Jeksleveien 47 |  |  | Does not qualify | 400A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 47 AS (https://www.notion.so/KLP-Jeksleveien-47-AS-31fa1d8f955980a6a95be09681ca1635?pvs=21) | Jonas | 400 V | Solar as a Service | 181 | 2023-02-28 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Inspeksjonsstige på utsiden og opp til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | Approved | 2029-01-15 | Retrofit - GoO earnout | To be applied |  | Done | ELVIA | Done | Completed | J47 (Kominox) 2024 (https://www.notion.so/J47-Kominox-2024-188a1d8f955980a68979fd4af99cc18a?pvs=21), J47 (Kominox) 2025 (https://www.notion.so/J47-Kominox-2025-200a1d8f955980c99e2df55b2376cc35?pvs=21) | Default | 1x Sungrow SG125CX-P2 | Loose inverter cover (https://www.notion.so/Loose-inverter-cover-106a1d8f9559808e8a44e8fbde700595?pvs=21), Wrong kWp in SundayOS (https://www.notion.so/Wrong-kWp-in-SundayOS-196a1d8f9559801abcabc7b0ce1c950a?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992926667547 (https://www.notion.so/7359992926667547-11aa1d8f955980839c60ca959edfb252?pvs=21) |  |  | In progress | PVC | 2021 | 330x556W LONGi LR5-72HPH-550 | Done | In operation |  | Installed | Kjetil |  |  |  |  | 120 | 1,159,520
In operation (COD) | Jeksleveien 47, 2016 Frogner |  | 228.8 | 2023-05-29 | 2023-10-20 | 2023-05-29 | 2023-06-12 | 2023-10-20 | 232.96 | Transferred | 🟨 144 days | 144 | 🟩 14 days | 14 | 🟥 130 days | 130 | 🟨 234 days | 234 | 🟩 90 days | 90 | 0.23 | 4.85 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 23 - Oct | 2306 | -4.85 | 1,609.230769230769 | 1.609230769231 | 🟥 SUM! | 185.90208 | 185,902.08 | 2023 - Q4 | 2023 - Q2 | 2023 - Q1 | 0 | 5.824 | 5.824 | 5.824 | 0 | 0 | 1,967,097 | ⌚ 894 days | 0 | 0 | -4.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 4.16 | 232.96 | 381.41 | 1.63723385989 | 376.56 | 0 | 0 | 381.41 | 1.63723385989 | 8.597451923077 | 0 | 0 | 0.38 | 381.41 | 1.97 | 403.084 | 4.85 | 🟩 NoCs: 0 | 1.59 | -0.020819024725 | 1.97 | 0 | 6.806692135989 | 1.616414835165 | 1,585,687 | 6.930450174825 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0.23 | 0 | 26.524 | 0 | 8.443925995879 | 0 | 1,585,687 | [5 empty] | NTE | thing_6aeca53f-5780-5829-8956-bdd4726c5ea4 (https://www.notion.so/thing_6aeca53f-5780-5829-8956-bdd4726c5ea4-209a1d8f955980cdba95f19fe245072e?pvs=21) | Done |  | Jeksleveien 47 |  |  | Does not qualify | 500A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 47 AS (https://www.notion.so/KLP-Jeksleveien-47-AS-31fa1d8f955980a6a95be09681ca1635?pvs=21) | Jonas | 400 V | Solar as a Service | 229 | 2023-02-28 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Inspeksjonsstige på utsiden og opp til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | Approved | 2029-01-15 | Retrofit - GoO earnout | Retrofit not completed |  | Done | ELVIA | Done | Completed | J47 (Antra) 2024 (https://www.notion.so/J47-Antra-2024-188a1d8f955980ff989fdc6249a73fff?pvs=21), J47 (Antra) 2025 (https://www.notion.so/J47-Antra-2025-200a1d8f955980f6ac3ae70502d2c18d?pvs=21) | Default | 1x Sungrow SG125CX-P2, 1x Sungrow SG50CX-P2 | Loose inverter cover (https://www.notion.so/Loose-inverter-cover-106a1d8f9559808e8a44e8fbde700595?pvs=21), Tilsynsrapport (https://www.notion.so/Tilsynsrapport-18fa1d8f9559801a91f4f861aa58c5cd?pvs=21), Wrong kWp in SundayOS (https://www.notion.so/Wrong-kWp-in-SundayOS-196a1d8f9559801abcabc7b0ce1c950a?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992901793421 (https://www.notion.so/7359992901793421-11aa1d8f95598011bf35c1390eceb85d?pvs=21) |  |  | In progress | PVC | 2021 | 416x560W LONGi LR5-72HPH-550 | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 120 | 1,465,687
In operation (COD) | Jeksleveien 100, 2016 Frogner |  | 642.4 | 2023-05-29 | 2023-11-07 | 2023-05-29 | 2023-07-20 | 2023-11-07 | 642.4 | Transferred | 🟥 162 days | 162 | 🟨 52 days | 52 | 🟥 110 days | 110 | 🟨 238 days | 238 | 🟩 76 days | 76 | 0.64 | 0 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 2026-11-23 | 2307 | 0 | 4,111.764705882353 | 4.111764705882 | 🟥 SUM! | 511.3504 | 511,350.4 | 2023 - Q4 | 2023 - Q2 | 2023 - Q1 | 0 | 16.06 | 16.06 | 16.06 | 0 | 0 | 5,357,086 | ⌚ 876 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 0 | 642.4 | 978.6 | 1.523349937733 | 978.6 | 0 | 0 | 978.6 | 1.523349937733 | 8.339174968867 | 0 | 0 | 0.98 | 978.6 | 5.36 | 978.6 | 0 | 🟩 NoCs: 0 | 4.38 | 0 | 5.36 | 0 | 6.815825031133 | 1.523349937733 | 4,378,486 | 6.815825031133 | 0 | 217.355 | 0 | 217.355 | 0 | 4.38 | 0.64 | 0 | 0 | 0 | 8.339174968867 | 0 | 4,378,486 | [5 empty] | NTE | thing_60bd76da-3875-47fd-aa66-e5c8407beac8 (https://www.notion.so/thing_60bd76da-3875-47fd-aa66-e5c8407beac8-46ba789d253c4c3b9a9a4286833eb6ea?pvs=21) | Done |  | Jeksleveien 100 |  |  | Does not qualify | 900 A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 100 AS (https://www.notion.so/KLP-Jeksleveien-100-AS-31fa1d8f9559801da630eb8dc1448468?pvs=21) | Jonas | 400 V | Solar as a Service | 642 | 2023-03-14 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Enten via bakkenivå eller via mesanin/kantine. Stige med ryggsøyle hele veien til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | Approved | 2029-01-15 | Retrofit - GoO earnout | Retrofit not completed |  | Done | ELVIA | Done | Completed | J100 2024 (https://www.notion.so/J100-2024-188a1d8f955980cf87d0f3e3d4f150da?pvs=21), J100 2025 (https://www.notion.so/J100-2025-213a1d8f955980048e26fb42ea3b0bed?pvs=21) | Default | 3x Sungrow 125CX-P2 1x Sungrow 110CX | Roof leakage (https://www.notion.so/Roof-leakage-e51702494d22456bbe85e3ea68f10da7?pvs=21), Plant is offline (https://www.notion.so/Plant-is-offline-0c59a64a59824c349beece29d746e1fc?pvs=21), Wrong kWp in SolarLog (https://www.notion.so/Wrong-kWp-in-SolarLog-0dfdf47207b24fefbdc965de0489d905?pvs=21), Missing one inverter in SolarLog (https://www.notion.so/Missing-one-inverter-in-SolarLog-43b17ebf807146a6963152fb49861fe4?pvs=21), INV4: String Current Reflux + PV Abnormal Alarm (https://www.notion.so/INV4-String-Current-Reflux-PV-Abnormal-Alarm-94dec216d0bc47c19945084ff85bb95f?pvs=21), Low Production (https://www.notion.so/Low-Production-715ca30737594381878daafcd13ba6f5?pvs=21), INV4: Production cap at 100 kWp (https://www.notion.so/INV4-Production-cap-at-100-kWp-1e4a1d8f955980e2bcd4e064ec553ec4?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992904983966 (https://www.notion.so/7359992904983966-11aa1d8f955980dda345f26885f6fb94?pvs=21) |  |  | In progress | PVC | 2020 | 1168x550W LONGi LR5-72HPH 550M | Done | In operation |  | Installed | Kjetil |  |  |  |  | 240 | 4,138,486
In operation (COD) | Jeksleveien 55, 2016 Frogner |  | 158.4 | 2023-06-08 | 2023-10-16 | 2023-06-08 | 2023-07-10 | 2023-10-16 | 159.58 | Transferred | 🟨 130 days | 130 | 🟩 32 days | 32 | 🟨 98 days | 98 | 🟩 130 days | 130 | 🟩 0 days | 0 | 0.16 | 4.85 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 23 - Oct | 2307 | -4.85 | 1,914.876923076923 | 1.914876923077 | 🟥 SUM! | 127.34484 | 127,344.84 | 2023 - Q4 | 2023 - Q2 | 2023 - Q2 | 0 | 3,989.5 | 3,989.5 | 1,662.291666666667 | 0 | 0 | 1,365,781 | ⌚ 898 days | 0 | 0 | -4.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 1.18 | 159.58 | 253.784 | 1.59032460208 | 248.934 | 0 | 0 | 253.784 | 1.59032460208 | 8.62235479798 | 0 | 0 | 0.25 | 253.784 | 1.37 | 248.934 | 4.85 | 🟩 NoCs: 0 | 2026-11-01 | -0.030392279734 | 1.37 | 0 | 6.968272966537 | 1.559932322346 | 1,111,997 | 7.020183080808 | 0 | 54.17 | 0 | 54.17 | 0 | 2026-11-01 | 0.16 | 0 | 0 | 0 | 8.558597568618 | 0 | 1,111,997 | [5 empty] | NTE | thing_c3694fb0-7f1c-5009-9a08-4bf0263f1cfb (https://www.notion.so/thing_c3694fb0-7f1c-5009-9a08-4bf0263f1cfb-20aa1d8f9559809796d0e9e2469fdb85?pvs=21) | Done |  | Jeksleveien 55 |  |  | Does not qualify | 2500A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 55 AS (https://www.notion.so/KLP-Jeksleveien-55-AS-31fa1d8f955980d4816beb8bc691467d?pvs=21) | Jonas | 400 V | Solar as a Service | 129 | 2023-06-08 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Tilgang gjennom vindu i andre etasje. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | Uploaded FDV | Approved | 2028-11-13 | Retrofit - GoO earnout | Retrofit not completed |  | Done | ELVIA | Done | Completed | J55 2024 (https://www.notion.so/J55-2024-188a1d8f95598093a095effe3fce2e57?pvs=21), J55 2025 (https://www.notion.so/J55-2025-213a1d8f955980d6a5fcefb7402dcb2b?pvs=21) | Default | 1x Solis 110K-5G-PRO | No solar log data (https://www.notion.so/No-solar-log-data-ca143216796a44aebdf91d5c50bc83fb?pvs=21), Missing 20 000 kWh (https://www.notion.so/Missing-20-000-kWh-177a1d8f9559805f8b8dc482891a95ad?pvs=21), INV1 MPPT5 underperforming (https://www.notion.so/INV1-MPPT5-underperforming-24ea1d8f95598021b8f1f3b0240a3981?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992894564909 (https://www.notion.so/7359992894564909-11aa1d8f955980cd8700c8d9531c3c5b?pvs=21) |  |  | In progress | PVC |  | 316x505W Longi LR5-66HPH-505M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 60 | 1,051,997
Cancelled | Jeksleveien 59, 2016 Frogner |  | 96.8 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.1 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | -96.8 | 96.8 | 0 | 0 | 0 | 0 | 0 | -724.27 | -7.482128099174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.72 | 0 | 0 | 0 | 7.482128099174 | 0 | 724.27 | 7.482128099174 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 724.27 | [9 empty] | Jeksleveien 59 |  |  |  | 400A | Bulk Industrial Real Estate AS (https://www.notion.so/Bulk-Industrial-Real-Estate-AS-1a8a1d8f9559805ca7cbd0938f7b649d?pvs=21) |  | 2016 | Frogner |  |  |  | Not set | 400 V | Solar as a Service | 108 | [5 empty] | Not uploaded | [5 empty] | Not started | ELVIA | No status |  |  |  | 1x SG110CX |  | Roof OK | [7 empty] | PVC | 2013 | 176x550W | [9 empty] | 60 | 664.27
In operation (COD) | Johan Follestads vei 6, 3474 Åros |  | 288 | 2023-06-30 | 2023-10-12 | 2023-06-30 | 2023-08-15 | 2023-10-12 | 290.88 | Transferred | 🟨 104 days | 104 | 🟨 46 days | 46 | 🟩 58 days | 58 | 🟩 143 days | 143 | 🟩 39 days | 39 | 0.29 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 23 - Oct | 2308 | 0 | 3,191.048951048951 | 3.191048951049 | 🟥 SUM! | 238.5216 | 238,521.6 | 2023 - Q4 | 2023 - Q2 | 2023 - Q2 | 0 | 7.272 | 7.272 | 2.424 | 0 | 0 | 2,457,367 | ⌚ 902 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2023 | 2.88 | 290.88 | 456.32 | 1.568756875688 | 456.32 | 0 | 0 | 456.32 | 1.568756875688 | 8.532524305556 | 0 | 0 | 0.46 | 456.32 | 2.46 | 500.118 | 0 | 🟩 NoCs: 0 | 2 | 0 | 2.46 | 0 | 6.879286991199 | 1.568756875688 | 2,001,047 | 6.948079861111 | 0 | 0 | 0 | 0 | 0 | 2 | 0.29 | 0 | 43.798 | 0 | 8.448043866887 | 0 | 2,001,047 | [5 empty] | NTE | thing_dff1f529-a4f0-5815-80c9-30daaffec2c6 (https://www.notion.so/thing_dff1f529-a4f0-5815-80c9-30daaffec2c6-226a1d8f9559801aa3a3e2fdf334a594?pvs=21) | Done |  | Johan Follestads vei 6 |  |  | Does not qualify |  | Warbo Gruppen AS (https://www.notion.so/Warbo-Gruppen-AS-1a8a1d8f95598050b0a5e2021e3c87f2?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  | Warbo Røyken AS (https://www.notion.so/Warbo-R-yken-AS-311a1d8f9559800891bfe3379ed09f6e?pvs=21) | Rikard | 400 V | Solar as a Service | 320 | 2023-05-22 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Stige fra bakkenivå og helt opp til taket med lem. Venter på at Certex skal ordne med lås og dele nøkkel/kode med oss. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Jon Fredrik Skogen (https://www.notion.so/Jon-Fredrik-Skogen-1a5a1d8f9559805c9b4cc2125f8d2a1d?pvs=21) | Uploaded FDV | Approved | 2028-11-13 | Retrofit - GoO earnout | Applied |  | Done | NORGESNETT | Done | Completed | JF6 2024 (https://www.notion.so/JF6-2024-188a1d8f955980338f80f0d64124aa77?pvs=21), JF6 2025 (https://www.notion.so/JF6-2025-213a1d8f95598005b818f2d3ecdfe848?pvs=21) | Default | 2x Solis S5-GC110K-5G | Inverter Offline (https://www.notion.so/Inverter-Offline-12da1d8f9559807789a3e644435ce7c4?pvs=21) | Roof OK | Retrofit |  | Approved | 5706567291195737 (https://www.notion.so/5706567291195737-11aa1d8f955980c88109e7e46ff97881?pvs=21), 5706567334930295 (https://www.notion.so/5706567334930295-24fa1d8f955980efa5e4d5d567d8bfef?pvs=21) |  |  | Done | PVC | 2016 | 576x505W Longi-LR66-HPH-505M | Done | In operation |  | Installed | Kjetil |  |  |  |  | 120 | 1,881,047
On hold | Edvard Griegs vei 45, 2060 Gardermoen |  | 1 |  |  |  |  | 2026-06-30 |  | Appr. awaiting APA | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 1135 days | 1135 | 🟥 1045 days (ongoing) | 1045 | 1 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Jun |  | 0 | 472.246696035242 | 0.472246696035 | 🟥 SUM! | 778 | 778 | 2026 - Q2 |  | 2023 - Q2 | 0 | 0 |  |  | 0 | 0 | 5,636,000 | 🔸🕐 -89 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2023 | -1 | 1 | 536 | 0.536 | 536 | 0 | 0 | 536 | 0.536 | 5.636 | 0 | 0 | 0.54 | 536 | 5.64 | 536 | 0 | 🟩 NoCs: 0 | 2026-01-05 | 0 | 5.64 | 0 | 2026-01-05 | 0.536 | 5,100,000 | 2026-01-05 | 0 | 0 | 0 | 0 | 0 | 2026-01-05 | 0 | 0 | 0 | 0 |  | 0 | 5,100,000 |  |  |  | Energiattest for gammelt | [5 empty] | Edvard Griegs vei 45 |  |  | Need new score | 1000A | Warbo Gruppen AS (https://www.notion.so/Warbo-Gruppen-AS-1a8a1d8f95598050b0a5e2021e3c87f2?pvs=21) |  | 2060 | Gardermoen | Signed |  |  | Rikard | 400 V | Solar as a Service | 856 | 2023-05-22 |  |  |  |  | Not uploaded | [5 empty] | Not started | ELVIA | No status | Not completed |  |  | 6x 110 kW |  | Roof OK | TBD | 03.01: Fått til svar at vi må søke. | Sent | [5 empty] | 2016 | 1780x505W | [9 empty] | 0 | 5,100,000
In operation (COD) | Jeksleveien 36, 2016 Frogner |  | 310.8 | 2023-10-30 | 2024-06-27 | 2023-10-30 | 2023-11-28 | 2024-06-27 | 310.8 | Transferred | 🟥 241 days | 241 | 🟩 29 days | 29 | 🟥 212 days | 212 | 🟥 363 days | 363 | 🟩 122 days | 122 | 0.31 | 0 | 🟩 All good | 25 | 🟩 1400 days left | 💚 All good | 24 - Jun | 2311 | 0 | 1,165.977961432507 | 1.165977961433 | 🟥 SUM! | 247.3968 | 247,396.8 | 2024 - Q2 | 2023 - Q4 | 2023 - Q2 | 0 | 7.77 | 7.77 | 11.655 | 0 | 0 | 2,531,843 | ⌚ 643 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 310.8 | 423.25 | 1.361808236808 | 423.25 | 0 | 0 | 423.25 | 1.361808236808 | 8.146212998713 | 0 | 0 | 0.42 | 423.25 | 2.53 | 491.213 | 0 | 🟩 NoCs: 0 | 2026-11-02 | 0 | 2.53 | 0 | 6.784404761905 | 1.361808236808 | 2,108,593 | 6.784404761905 | 0 | 0 | 0 | 0 | 0 | 2026-11-02 | 0.31 | 0 | 67.963 | 0 | 8.146212998713 | 0 | 2,108,593 |  |  |  | Kvalifiserer ikke pga nybygg |  | NTE | thing_09ee0054-a5f9-4696-9fdc-5514625bfd50 (https://www.notion.so/thing_09ee0054-a5f9-4696-9fdc-5514625bfd50-3332f935be8b482b9bfe10bdf4fce437?pvs=21) | Done |  | Jeksleveien 36 |  |  | Does not qualify | 500A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | KLP Jeksleveien 36 AS (https://www.notion.so/KLP-Jeksleveien-36-AS-31fa1d8f95598053bd94cdc4fc51aae2?pvs=21) | Jonas | 400 V | Solar as a Service | 311 | 2023-06-30 |  | Fastmontert stige på veggen fra bakkenivå til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Per-Christian Vadvedt (https://www.notion.so/Per-Christian-Vadvedt-1a5a1d8f95598095b1d1c3f9c19e0aa1?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | Retrofit - GoO earnout | Applied | 2025-01-31 | Done | ELVIA | Done | Completed | J36 2025 (https://www.notion.so/J36-2025-218a1d8f955980559c83ebbf1280f788?pvs=21) | Default | 2x Solis 110K-5G-PRO | No monitoring (https://www.notion.so/No-monitoring-3d6919f6b47a4ea49d3bad49d662ced3?pvs=21), Grid Over Frequency (https://www.notion.so/Grid-Over-Frequency-113a1d8f955980e993a0cb4ac4313357?pvs=21), Wrong data from smart meter (https://www.notion.so/Wrong-data-from-smart-meter-1afa1d8f95598065a45dc906fa7ff65c?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992932882453 (https://www.notion.so/7359992932882453-11aa1d8f955980a9bbbed71564835063?pvs=21), 7359992936892267 (https://www.notion.so/7359992936892267-14ba1d8f9559808bad0ed42f0725fe65?pvs=21) |  |  | Done | PVC | 2023 | Fasade: 54x410W LONGi LR5-54 HPB 410M Tak: 566x510W LONGi LR5-66HPH 510M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 183.25 | 1,925,343
Cancelled | Grenseveien 99, 0663 Oslo | [8 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 1195 days (ongoing) | 1195 | 🟥 1195 days (ongoing) | 1195 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 0 | 0 | 🟥 SUM! | 0 | 0 |  |  | 2022 - Q4 | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Grenseveien 99 |  |  |  |  | NCC Norge AS (https://www.notion.so/NCC-Norge-AS-1a8a1d8f955980f1be29f16e71e06858?pvs=21), Arctic Real Estate Management AS (https://www.notion.so/Arctic-Real-Estate-Management-AS-1a8a1d8f955980d5a730c61ecd65d820?pvs=21) |  | 663 | Oslo | Signed |  |  | Not set |  | Solar as a Service | 126 | 2022-12-23 |  |  |  |  | Not uploaded | [5 empty] | Not started |  | No status
In operation (COD) | Nordbyveien 98, 1406 Ski |  | 184.8 | 2023-09-15 | 2024-01-31 | 2023-09-15 | 2023-09-18 | 2024-01-31 | 185.37 | N/A | 🟨 138 days | 138 | 🟩 3 days | 3 | 🟥 135 days | 135 | 🟨 208 days | 208 | 🟩 70 days | 70 | 0.18 | 0 | 🟩 All good |  | ❌ End date missing | ❌ Missing | 2026-01-24 | 2309 | 0 | 1,523.009615384616 | 1.523009615385 | 🟥 SUM! | 151.44729 | 151,447.29 | 2024 - Q1 | 2023 - Q3 | 2023 - Q3 | 0 | 0 |  |  | 0 | 0 | 1,619,200 | ⌚ 791 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0.57 | 185.37 | 316.786 | 1.708938878999 | 316.786 | 0 | 0 | 316.786 | 1.708938878999 | 8.761904761905 | 0 | 0 | 0.32 | 316.786 | 1.62 | 316.786 | 0 | 🟩 NoCs: 0 | 2026-03-01 | 0 | 1.62 | 0 | 7.026023628419 | 1.708938878999 | 1,302,414 | 7.047694805195 | 0 | 0 | 0 | 0 | 0 | 2026-03-01 | 0.19 | 0 | 0 | 0 | 8.734962507418 | 0 | 1,302,414 | [7 empty] | N/A |  | Nordbyveien 98 |  |  |  | 3200A | Møller Eiendom Holding AS (https://www.notion.so/M-ller-Eiendom-Holding-AS-1a7a1d8f9559801d9d4dd7a47e765546?pvs=21) | Not relevant | 1406 | Ski | Signed |  |  | Rikard | 400 V | Project Sales | 184 | 2023-07-07 | Magnus Anderssen (https://www.notion.so/Magnus-Anderssen-1a5a1d8f9559806eb59dd7aa9f4e32f9?pvs=21), Hans Martin Løken (https://www.notion.so/Hans-Martin-L-ken-1bca1d8f95598037b70cf6d48790fee6?pvs=21), Henning Kolstad (https://www.notion.so/Henning-Kolstad-1a5a1d8f9559805691c8edea660e4ba0?pvs=21) | Via luke på innsiden av bygget i ventilasjonsrommet. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Ole Johannessen (https://www.notion.so/Ole-Johannessen-1a5a1d8f955980878e25fae80870e8e9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | NORGESNETT | Done | Completed |  |  | 1x Solis 110K 5G PRO, 1x Solis S5 GC40K | Deviations from annual report (https://www.notion.so/Deviations-from-annual-report-1f1a1d8f955980099a62f71f6781c9d9?pvs=21) | Roof OK | No |  | Not applicable | 7359992899894889 (https://www.notion.so/7359992899894889-11aa1d8f955980958a12d83cdc62a349?pvs=21) |  |  | Not relevant | PVC | 2019? | 334x555W LONGi LR5-72HPH555M | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 125 | 1,177,414
In operation (COD) | Professor Birkelands vei 36, 1081 Oslo |  | 697.95 | 2024-02-06 | 2024-09-09 | 2024-02-06 | 2024-03-20 | 2024-09-09 | 697.95 | N/A | 🟥 216 days | 216 | 🟨 43 days | 43 | 🟥 173 days | 173 | 🟥 384 days | 384 | 🟩 168 days | 168 | 0.7 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 2026-09-24 | 2403 | 0 | 2,854.815104166667 | 2.854815104167 | 🟥 SUM! | 549.28665 | 549,286.65 | 2024 - Q3 | 2024 - Q1 | 2023 - Q3 | 0 | 34,897.5 | 35,979.3225 | 35,979.3225 | 0 | 0 | 6,147,600 | ⌚ 569 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 697.95 | 1,096,249 | 1.570669818755 | 1,096,249 | 0 | 0 | 1,096,249 | 1.570669818755 | 8.808080808081 | 0 | 0 | 2026-01-01 | 1,096,249 | 6.15 | 1,096,249 | 0 | 🟩 NoCs: 0 | 2026-05-05 | 0 | 6.15 | 0 | 7.237410989326 | 1.570669818755 | 5,051,351 | 7.237410989326 | 0 | 0 | 0 | 0 | 0 | 2026-05-05 | 0.7 | 0 | 0 | 0 | 8.808080808081 | 0 | 5,051,351 | [5 empty] | Premium | thing_249513c5-e8b5-532c-9e47-3b6686963096 (https://www.notion.so/thing_249513c5-e8b5-532c-9e47-3b6686963096-8be2f6a3fc754b459cc0777ea4e74a8c?pvs=21), thing_5627b17e-7b44-5856-9f90-a142bd5a2e96 (https://www.notion.so/thing_5627b17e-7b44-5856-9f90-a142bd5a2e96-8ef5e467c274420d8b63f52914e5ac1c?pvs=21) | Done |  | Professor Birkelands vei 36 |  |  |  |  | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 1081 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 705 | 2023-08-22 |  | Fastmontert stige med ryggsøyle fra bakkeplan. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Mathea Marjavara (https://www.notion.so/Mathea-Marjavara-1a5a1d8f955980da85e2ddefe19c6510?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 7x Solis 60K-LV-5G 2x Solis S5-GC-36K-LV | Connection down (https://www.notion.so/Connection-down-134a1d8f955980b287a3c1040705adbc?pvs=21), Big inverter difference (https://www.notion.so/Big-inverter-difference-13ea1d8f955980e8a86fffe500a11119?pvs=21), Wrong meter constant in Elhub (https://www.notion.so/Wrong-meter-constant-in-Elhub-1dfa1d8f95598067bd28dd7489111708?pvs=21), Plant is not behind meter (https://www.notion.so/Plant-is-not-behind-meter-208a1d8f9559809bb921ddb51883742c?pvs=21) | Roof OK | No |  | Not applicable | 7359992926229325 (https://www.notion.so/7359992926229325-113a1d8f9559802e8aa6e929af9bad72?pvs=21), 7359992895586245 (https://www.notion.so/7359992895586245-113a1d8f955980e5af59f1dede3fb265?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp | 1991 | 1410x495W JA Solar JAM66S30 | Done | Not started |  | Installed | Kjetil |  |  |  |  | 928.536 | 4,122,815
In operation (COD) | Nordre Kullerød 5, 3241 Sandefjord |  | 359.6 | 2024-06-14 | 2024-08-28 | 2024-06-14 | 2024-08-07 | 2024-08-28 | 365.78 | Transferred | 🟨 75 days | 75 | 🟨 54 days | 54 | 🟩 21 days | 21 | 🟥 420 days | 420 | 🟥 345 days | 345 | 0.36 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 2026-08-24 | 2408 | 0 | 2,886.011904761905 | 2.886011904762 | 🟥 SUM! | 322.61796 | 322,617.96 | 2024 - Q3 | 2024 - Q2 | 2023 - Q3 | 0 | 9,144.5 |  |  | 0 | 0 | 2,771,846 | ⌚ 581 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 6.18 | 365.78 | 621.846 | 1.700054677675 | 1,212,125 | 590.279 | 590.279 | 621.846 | 1.700054677675 | 7.708136818687 | 0 | 0 | 0.62 | 621.846 | 2.77 | 1,212,125 | 0 | 🟩 NoCs: 0 | 2.15 | 1.613754169173 | 2.77 | 0 | 5.877850073815 | 3.313808846848 | 2,150,000 | 5.978865406007 | 0 | 119.06 | 0 | 119.06 | 0 | 2.15 | 0.37 | 590.279 | 0 | 0 | 7.57790475149 | 0 | 2,150,000 | 2024-03-22 | Deployment/Energieffektivisering_med_solcelleanlegg-2.pdf |  |  | 100% | NTE | thing_9b7bdea3-4ee3-590f-a44d-55e8ad39720c (https://www.notion.so/thing_9b7bdea3-4ee3-590f-a44d-55e8ad39720c-1cfe5c5285e04ae1b472d989af25ae36?pvs=21), thing_4df863a2-803a-5db9-b9f3-a01712da6038 (https://www.notion.so/thing_4df863a2-803a-5db9-b9f3-a01712da6038-58aac62629b449b6ae2b053d12f01815?pvs=21) | Not started | 590.279 | Nordre Kullerød 5 | GK Norge as v/ Geir Seland |  | Payment received | 5A: 570A 5B: 200A | Brække Eiendom AS (https://www.notion.so/Br-kke-Eiendom-AS-1a8a1d8f955980e98516e82f55b2e603?pvs=21) | Yes - all PPAs | 3241 | Sandefjord | Signed |  |  | Jonas | 400 V | Solar as a Service | 348 | 2023-07-05 | Ole Petter Ervik (https://www.notion.so/Ole-Petter-Ervik-1a5a1d8f955980a98ea6eb7ec975005d?pvs=21) | Fri tilgang fra bakkeplan og opp. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | Retrofit - GoO earnout | Retrofit not completed | 2025-01-31 | Done | LEDE | Done | Completed | NK5A 2025 (https://www.notion.so/NK5A-2025-218a1d8f95598078a157c433bda79f7d?pvs=21), NK5B 2025 (https://www.notion.so/NK5B-2025-252a1d8f955980768c80ee9e1bf392ce?pvs=21) | Default | 2x Solis 110 kW, 1x Solis 60kW | Error - not specified and Grid Under Frequency (https://www.notion.so/Error-not-specified-and-Grid-Under-Frequency-ee555a046a3d4da49674edea49ed6556?pvs=21), Yield deviation bug (https://www.notion.so/Yield-deviation-bug-111a1d8f9559806aab0fd63342c20523?pvs=21), Data loss (https://www.notion.so/Data-loss-112a1d8f95598036b97cc377d8a9cf03?pvs=21), Grid Over Frequency (https://www.notion.so/Grid-Over-Frequency-113a1d8f95598016ae1bc56821f7dd68?pvs=21), Very high yield deviation (https://www.notion.so/Very-high-yield-deviation-120a1d8f95598091b1c1e8c7cf1e4c8f?pvs=21), Missing data (https://www.notion.so/Missing-data-12da1d8f955980a6bef7c62e0c93a29c?pvs=21), Way too positive yield deviation (https://www.notion.so/Way-too-positive-yield-deviation-131a1d8f95598060ac58fc1b42d65215?pvs=21), No data (https://www.notion.so/No-data-138a1d8f9559803b99eeebfd82e1f16c?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992904021774 (https://www.notion.so/7359992904021774-11aa1d8f9559806a8525dda67e6dff7d?pvs=21), 7359992904022054 (https://www.notion.so/7359992904022054-11aa1d8f955980e4a718c86107eb82f3?pvs=21) |  |  | To be started | PVC | 2008 | 620x580W PhonoSolar | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 215 | 1,935,000
In operation (COD) | Smalvollveien 61-63, 0667 Oslo |  | 133 | 2023-09-12 | 2024-03-13 | 2023-09-12 | 2023-10-13 | 2024-03-13 | 134.33 | N/A | 🟥 183 days | 183 | 🟩 31 days | 31 | 🟥 152 days | 152 | 🟨 203 days | 203 | 🟩 20 days | 20 | 0.13 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 24 - Mar | 2310 | 0 | 739.172413793104 | 0.739172413793 | 🟥 SUM! | 104.24008 | 104,240.08 | 2024 - Q1 | 2023 - Q3 | 2023 - Q3 | 0 | 6,716.5 | 6,924.7115 | 6,924.7115 | 0 | 0 | 1,149,120 | ⌚ 749 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 1.33 | 134.33 | 150.052 | 1.117040125065 | 150.052 | 0 | 0 | 150.052 | 1.117040125065 | 8.64 | 0 | 0 | 0.15 | 150.052 | 1.15 | 150.052 | 0 | 🟩 NoCs: 0 | 1 | 0 | 1.15 | 0 | 7.437415320479 | 1.117040125065 | 999.068 | 7.511789473684 | 0 | 0 | 0 | 0 | 0 | 1 | 0.13 | 0 | 0 | 0 | 8.554455445545 | 0 | 999.068 | [5 empty] | Premium | thing_a479ad9a-0e1c-5b57-8a12-bdf6fa377529 (https://www.notion.so/thing_a479ad9a-0e1c-5b57-8a12-bdf6fa377529-0acbd905b8054fd4a90b99b8d6f46cd9?pvs=21), thing_47c13f7e-186a-5e34-88cd-27c687beb3f4 (https://www.notion.so/thing_47c13f7e-186a-5e34-88cd-27c687beb3f4-6f9dd52d1fdc440bbe868667a872fefc?pvs=21) | Done |  | Smalvollveien 61-63 |  |  |  | 630A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 667 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 151 | 2023-08-23 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rino Ombudstvedt (https://www.notion.so/Rino-Ombudstvedt-1a5a1d8f955980218040c8e684568b18?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | Nr. 61: 1x Solis S5-GC60K Nr. 63: 1x Solis S5-GC60K | 61 is not live (https://www.notion.so/61-is-not-live-13ea1d8f955980728ed7e51e393126f8?pvs=21), Grid No Grid (https://www.notion.so/Grid-No-Grid-1d5a1d8f9559807495d5fc985a14bcaa?pvs=21), No production MPPT1 (https://www.notion.so/No-production-MPPT1-1eaa1d8f95598011b44fcb8121ae772f?pvs=21), Plant moved to another meter? (https://www.notion.so/Plant-moved-to-another-meter-209a1d8f955980bf9787d990af4c4918?pvs=21), Cable management must be fixed (https://www.notion.so/Cable-management-must-be-fixed-218a1d8f955980adbc52d2b79f223ec8?pvs=21) | Roof OK | No |  | Not applicable | 7359992903073170 (https://www.notion.so/7359992903073170-43f464970f7b42a5b8cf509b8f00fdb0?pvs=21), 7359992903074450 (https://www.notion.so/7359992903074450-28a7c0161f394474aae6e0beb3c26586?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp | 1993 | Nr. 61: 120x505W LONGi LR5-66HPH 505M Nr. 63: 146x505W LONGi LR5-66HPH 505M | Done | Not started |  | Installed | Kjetil |  |  |  |  | 88.99 | 910.078
In operation (COD) | Stubberudveien 8, 0668 Oslo |  | 178.64 | 2024-03-27 | 2024-07-17 | 2024-03-27 | 2024-05-27 | 2024-07-17 | 178.5 | N/A | 🟨 112 days | 112 | 🟥 61 days | 61 | 🟩 51 days | 51 | 🟥 330 days | 330 | 🟨 218 days | 218 | 0.18 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 24 - Jul | 2405 | 0 | 1,114.933333333333 | 1.114933333333 | 🟥 SUM! | 141.372 | 141.372 | 2024 - Q3 | 2024 - Q1 | 2023 - Q3 | 0 | 8.925 | 9,201.675 | 9,201.675 | 0 | 0 | 1,477,200 | ⌚ 623 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | -0.14 | 178.5 | 367.928 | 2.061221288515 | 367.928 | 0 | 0 | 367,927.03 | 2.061215854342 | 8.269144648455 | 0 | 0 | 0.37 | 367.928 | 1.48 | 367.928 | 0 | 🟩 NoCs: 0 | 2026-11-01 | 0.000005434173 | 1.48 | 0 | 6.214408963585 | 2.061221288515 | 1,109,272.97 | 6.20954416704 | 0 | 0 | 0 | 0 | 0 | 2026-11-01 | 0.18 | 0 | 0 | 0 | 8.275630252101 | 0 | 1,109,272 | [5 empty] | Premium | thing_6d15f7be-b8b7-5687-b8fd-60d839998384 (https://www.notion.so/thing_6d15f7be-b8b7-5687-b8fd-60d839998384-524cef03c344418988f370c712da19e9?pvs=21) | Done |  | Stubberudveien 8 |  |  |  | 400A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  | Stubberudveien 8 AS (https://www.notion.so/Stubberudveien-8-AS-247a1d8f95598036b56bf5f9db95f783?pvs=21) | Rikard | 230 V | Project Sales | 165 | 2023-08-22 | Petter Haugan (https://www.notion.so/Petter-Haugan-1a5a1d8f955980359272c7d77f7ea7e6?pvs=21) | Tilkomst til taket via inspeksjonsstige med ryggsøyle på nordveggen. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Henrik Johansen (https://www.notion.so/Henrik-Johansen-1a5a1d8f955980349aebc709c87a5674?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 2x Solis S5-GC60K-LV-5G | Low Production (https://www.notion.so/Low-Production-cfe3752597e546cabcaec76269c4de68?pvs=21), No production (https://www.notion.so/No-production-1c2a1d8f955980b1ab7cdaedf396c496?pvs=21) | Roof OK | No |  | Not applicable | 7359992900569164 (https://www.notion.so/7359992900569164-aa3c631d0d134dad9f85647be40c631b?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp | 1993 | 340x525W LONGi LR5-66HTH | Done | Not started |  | Installed | Kjetil |  |  |  |  | 173.5 | 935,772.97
In operation (COD) | Vollaveien 19, 0668 Oslo |  | 49.14 | 2024-05-30 | 2025-07-08 | 2024-05-30 | 2025-02-24 | 2025-07-08 | 49.14 | N/A | 🟥 404 days | 404 | 🟥 270 days | 270 | 🟥 134 days | 134 | 🟥 686 days | 686 | 🟨 282 days | 282 | 0.05 | 5.178 | 🟩 All good | 50 | ❌ End date missing | ❌ Missing | 25 - Jul | 2502 | -642 | -0.935860058309 | -0.000935860058 | 🟩 OK! | 38.52576 | 38,525.76 | 2025 - Q3 | 2024 - Q2 | 2023 - Q3 | 0 | 2.457 | 2.457 | 1,023.75 | 4.536 | 405.252 | 405.252 | ⌚ 267 days | 0 | 4.536 | -642 | 0 | 405.252 | 4.536 | 4.536 | 0 | 4.536 | 405.252 | 2025 | 2023 | 0 | 49.14 | 4.536 | 0.092307692308 | -642 | 0 | 0 | 24.316 | 0.494831094831 | 8.246886446886 | 0 | 0 | 0 | 4.536 | 0.41 | -642 | 5.178 | 🟥 NoCs: 4 | 0.4 | -0.507895807896 | 0.41 | 0 | 8.154578754579 | -0.013064713065 | 380.936 | 7.752055352055 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.05 | 0 | 0 | 0 | 8.246886446886 | 19,780.578 | 400.716 | [5 empty] | Premium | thing_5d28b075-c0cc-5972-8dd1-5d4600761196 (https://www.notion.so/thing_5d28b075-c0cc-5972-8dd1-5d4600761196-1eaa1d8f955980e29e07ff18fbc4e752?pvs=21) |  |  | Vollaveien 19 |  |  |  | 1600/2000A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 374 | 2023-08-22 | Henning Kolstad (https://www.notion.so/Henning-Kolstad-1a5a1d8f9559805691c8edea660e4ba0?pvs=21) | Via trapp i andre etasje | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Andrii Petrychenko (https://www.notion.so/Andrii-Petrychenko-1aba1d8f955980d1838fec488c9647d3?pvs=21) | N/A | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 1x Growatt MAX35KTL3-XL | Fan fault (https://www.notion.so/Fan-fault-23fa1d8f9559807e9e6ae6cd2a7b956d?pvs=21) | Roof OK | No | 22.09.2025: Søkt om ferdigattest. | Approved | 7359992902714487 (https://www.notion.so/7359992902714487-2e0a1d8f9559805a89add1cb3fe481da?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp og PVC | 1993-2003 | 84x585W Tongwei TWMND-72HD | Done | Not started |  | Installed | Kjetil |  |  |  |  | 65.541 | 315.395
On hold | Professor Birkelands vei 32B, 1081 Oslo |  | 277 |  |  |  |  | 2026-12-01 |  | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.28 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Dec |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q4 |  |  | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -243 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | -277 | 277 | 0 | 0 | 0 | 0 | 0 | -2,265,870 | -8.180036101083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2.27 | 0 | 0 | 0 | 8.180036101083 | 0 | 2,265,870 | 8.180036101083 | 0 | 0 | 0 | 0 | 0 | 2.27 | 0 | 0 | 0 | 0 |  | 0 | 2,265,870 | [9 empty] | Professor Birkelands vei 32B |  |  |  | 850A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) |  | 1081 | Oslo |  |  |  | Rikard | 230 V | Project Sales | 277 | [5 empty] | N/A |  |  | Not relevant |  |  | Not started |  | No status | [5 empty] | Roof OK | No | [5 empty] | Not relevant | Papp | 1991 | [10 empty] | 240 | 2,025,870
On hold | Strømsveien 195-197, 0668 Oslo |  | 176 |  |  |  |  | 2026-12-01 |  | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.18 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Dec |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q4 |  |  | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -243 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | -176 | 176 | 0 | 0 | 0 | 0 | 0 | -1,480,016 | -8.409181818182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.48 | 0 | 0 | 0 | 8.409181818182 | 0 | 1,480,016 | 8.409181818182 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 0 | 0 | 0 |  | 0 | 1,480,016 | [9 empty] | Strømsveien 195-197 |  |  |  | 1700A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) |  | 668 | Oslo |  |  |  | Rikard | 230 V | Project Sales | 176 | [5 empty] | N/A |  |  | Not relevant |  |  | Not started |  | No status | [5 empty] | Roof OK | No | [5 empty] | Not relevant | Papp | Papp OK | [10 empty] | 120 | 1,360,016
On hold | Verkseier Furulunds vei 9, 0668 Oslo |  | 265 |  |  |  |  | 2026-12-01 |  | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.27 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Dec |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q4 |  |  | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -243 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | -265 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Verkseier Furulunds vei 9 |  |  |  | 315A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) |  | 668 | Oslo |  |  |  | Rikard | 230 V | Project Sales | 265 | [5 empty] | N/A |  |  | Not relevant |  |  | Not started |  | No status | [5 empty] | Roof OK | No | [5 empty] | Not relevant | Papp og PVC på mindre tak | 2011 | [10 empty] | 0 | 0
In operation (COD) | Vollaveien 20A-20B, 0668 Oslo |  | 256 | 2023-12-04 | 2024-05-27 | 2023-12-04 | 2023-12-08 | 2024-05-27 | 258.56 | N/A | 🟥 175 days | 175 | 🟩 4 days | 4 | 🟥 171 days | 171 | 🟨 278 days | 278 | 🟩 103 days | 103 | 0.26 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 24 - May | 2312 | 0 | 70.097122302158 | 0.070097122302 | 🟥 SUM! | 202.71104 | 202,711.04 | 2024 - Q2 | 2023 - Q4 | 2023 - Q3 | 0 | 12.928 | 13,328.768 | 13,328.768 | 0 | 0 | 2,204,160 | ⌚ 674 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 2.56 | 258.56 | 19.487 | 0.075367419554 | 19.487 | 0 | 0 | 19,486.5 | 0.075365485767 | 8.61 | 0 | 0 | 0.02 | 19.487 | 2026-02-02 | 19.487 | 0 | 🟩 NoCs: 0 | 2.18 | 0.000001933787 | 2026-02-02 | 0 | 8.449385055693 | 0.075367419554 | 2,184,673.5 | 8.533880859375 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0.26 | 0 | 0 | 0 | 8.524752475248 | 0 | 2,184,673 | [5 empty] | Premium | thing_837bf624-26a4-53a7-9067-5ad2d7358bd7 (https://www.notion.so/thing_837bf624-26a4-53a7-9067-5ad2d7358bd7-1eda1d8f9559801b9810c5157aeb4f0c?pvs=21) | Done |  | Vollaveien 20A-20B |  |  |  | 600A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 750 | 2023-08-23 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Trapp opp til tak. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | Vollaveien 20A: 3x Solis-60K-LV-5G Vollaveien 20B: 3x Solis-60K-LV-5G | Dead display and no communication (https://www.notion.so/Dead-display-and-no-communication-3dcd263163244ceda65da5bc500c13d3?pvs=21), No production data (https://www.notion.so/No-production-data-1e3a1d8f955980a9ba79dbfa677d5b1c?pvs=21), Inv 3 data missing in HW settings (https://www.notion.so/Inv-3-data-missing-in-HW-settings-20ea1d8f955980f09f58f96c11538e83?pvs=21) | Roof OK | No |  | Not applicable | 7359992898852514 (https://www.notion.so/7359992898852514-cdc10daf842741938620507260ff75c5?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp | 1993-2023 | Vollaveien 20A: 512x505W LONGi | Done | Not started |  | Installed | Kjetil |  |  |  |  | 180 | 2,004,673.5
In operation (COD) | Skjærdalen 2, 3533 Tyristrand |  | 247.45 | 2023-09-05 | 2024-02-06 | 2023-09-05 | 2023-09-25 | 2024-02-06 | 247.45 | N/A | 🟥 154 days | 154 | 🟩 20 days | 20 | 🟥 134 days | 134 | 🟩 158 days | 158 | 🟩 4 days | 4 | 0.25 | 0 | 🟩 All good |  | ❌ End date missing | ❌ Missing | 2026-02-24 | 2309 | 0 | 2,438.981012658228 | 2.438981012658 | 🟥 SUM! | 184.35025 | 184,350.25 | 2024 - Q1 | 2023 - Q3 | 2023 - Q3 | 0 | 0 |  |  | 0 | 0 | 2,342,500 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 247.45 | 385.359 | 1.557320670843 | 385.359 | 0 | 0 | 385.359 | 1.557320670843 | 9.466558900788 | 0 | 0 | 0.39 | 385.359 | 2.34 | 385.359 | 0 | 🟩 NoCs: 0 | 1.96 | 0 | 2.34 | 0 | 7.909238229945 | 1.557320670843 | 1,957,141 | 7.909238229945 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0.25 | 0 | 0 | 0 | 9.466558900788 | 0 | 1,957,141 | [7 empty] | N/A |  | Skjærdalen 2 |  |  |  | 2000A | Real Estate Holding AS (https://www.notion.so/Real-Estate-Holding-AS-1a8a1d8f955980d7ba82d99fd187fe4d?pvs=21) | Not relevant | 3533 | Tyristrand | Signed |  | Tyristrand Næringspark AS (https://www.notion.so/Tyristrand-N-ringspark-AS-311a1d8f955980bda3daf359cd641b35?pvs=21) | Rikard | 230 V | Project Sales | 245 | 2023-09-01 | Sigurd Narvestad (https://www.notion.so/Sigurd-Narvestad-1a5a1d8f95598007b895f1fadeedab47?pvs=21) | Inn i bygget og ut gjennom dør i øverste etasje (3. etg). Ta heis opp. Kommer inn midt på taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Branko Culjak (https://www.notion.so/Branko-Culjak-1a5a1d8f95598026b553fc108d980ae0?pvs=21), Viktor Lavik (https://www.notion.so/Viktor-Lavik-1a5a1d8f955980ae9254d0dd69d2fe1b?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | FØIE | Done | Completed |  |  | 3x Solis 60K-LV-5G |  | Roof OK | No |  | Not applicable | 18243215 (https://www.notion.so/18243215-11aa1d8f95598039a6afdab4b891ca17?pvs=21) |  |  | Not relevant | PVC (majoriteten av taket), papp (høyeste tak) | 2016 | 490x505W LONGi LR5-66HPH-505 | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 255 | 1,702,141
In operation (COD) | Industrigata 1, 3400 Lierstranda |  | 855.36 | 2024-02-12 | 2024-06-28 | 2024-02-12 | 2024-03-22 | 2024-06-28 | 855.36 | Transferred | 🟨 137 days | 137 | 🟩 39 days | 39 | 🟨 98 days | 98 | 🟨 275 days | 275 | 🟩 138 days | 138 | 0.86 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Jun | 2403 | 0 | 11,123.625454545454 | 11.123625454545 | 🟥 SUM! | 667.1808 | 667,180.8 | 2024 - Q2 | 2024 - Q1 | 2023 - Q3 | 0 | 21.384 |  |  | 0 | 0 | 6,580,706 | ⌚ 642 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 855.36 | 1,530,248 | 1.789010475122 | 3,058,997 | 1,528,749 | 1,528,749 | 1,530,248 | 1.789010475122 | 7.693492798354 | 0 | 0 | 1.53 | 1,530,248 | 6.58 | 3,256,427 | 0 | 🟩 NoCs: 0 | 2026-05-05 | 1.787257996633 | 6.58 | 0 | 5.904482323232 | 3.576268471755 | 5,050,458 | 5.904482323232 | 0 | 0 | 0 | 0 | 0 | 2026-05-05 | 0.86 | 1,528,749 | 197.43 | 0 | 7.693492798354 | 0 | 5,050,458 | 2024-03-22 | Deployment/Energieffektivisering_med_solcelleanlegg-2%201.pdf |  |  | 100% | NTE | thing_1710709a-6a37-45c0-b523-e667e121f4d1 (https://www.notion.so/thing_1710709a-6a37-45c0-b523-e667e121f4d1-2ce70a5a47c94065b2ad1f603133f8db?pvs=21) | N/A | 1,528,749 | Industrigata 1 | Filip Adrian Sørensen i Asplan Viak 41799417 |  | Payment received | 3200A | Selmer Eiendom AS (https://www.notion.so/Selmer-Eiendom-AS-1a7a1d8f95598039a0b7dd9193790725?pvs=21) | Yes - all PPAs | 3400 | Lierstranda | Signed |  |  | Rikard | 400 V | Solar as a Service | 866 | 2023-09-27 |  | Via innsiden av bygget. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Jon Fredrik Skogen (https://www.notion.so/Jon-Fredrik-Skogen-1a5a1d8f9559805c9b4cc2125f8d2a1d?pvs=21), Nirun Vigneswaran (https://www.notion.so/Nirun-Vigneswaran-1a5a1d8f9559805fa2c0cc4d612a1534?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | Retrofit - GoO earnout | To be applied | 2025-01-31 | Done | GLITRE | Done | Completed | I1 2025 (https://www.notion.so/I1-2025-209a1d8f9559807983bcc389e29e0031?pvs=21) | Default | 6x Solis 110K-5G-PRO | Grid Over Frequency (https://www.notion.so/Grid-Over-Frequency-113a1d8f9559808d9e9df2e8a150fc88?pvs=21), “Tilsynsrapport” (https://www.notion.so/Tilsynsrapport-218a1d8f95598008a997ca3233419178?pvs=21), Consumption registered and invoice received from grid owner (https://www.notion.so/Consumption-registered-and-invoice-received-from-grid-owner-23fa1d8f95598058968bd1455aa2a453?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992930292001 (https://www.notion.so/7359992930292001-11aa1d8f9559807a8354caea6918312b?pvs=21), 7359992906543601 (https://www.notion.so/7359992906543601-23ea1d8f9559805285d1cfa2aff95154?pvs=21) |  |  | Done | PVC | 2023 | 1728x495W JA Solar JAM66S30 | Done | In operation |  | Installed | Kjetil |  |  |  |  | 360 | 4,690,458
In operation (COD) | Barstølveien 19, 4636 Kristiansand |  | 345 | 2023-11-21 | 2024-03-15 | 2023-11-21 | 2024-02-05 | 2024-03-15 | 348.45 | N/A | 🟨 115 days | 115 | 🟥 76 days | 76 | 🟩 39 days | 39 | 🟩 147 days | 147 | 🟩 32 days | 32 | 0.35 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 24 - Mar | 2402 | 0 | 3,356.585034013606 | 3.356585034014 | 🟥 SUM! | 311.16585 | 311,165.85 | 2024 - Q1 | 2023 - Q4 | 2023 - Q4 | 0 | 17,422.5 | 17,962.5975 | 17,962.5975 | 0 | 0 | 2,704,639 | ⌚ 747 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 3.45 | 348.45 | 493.418 | 1.416036734108 | 493.418 | 0 | 0 | 493.418 | 1.416036734108 | 7.839533333333 | 0 | 0 | 0.49 | 493.418 | 2026-07-02 | 493.418 | 0 | 🟩 NoCs: 0 | 2.21 | 0 | 2026-07-02 | 0 | 6.345877457311 | 1.416036734108 | 2,211,221 | 6.409336231884 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0.35 | 0 | 0 | 0 | 7.761914191419 | 0 | 2,211,221 | [5 empty] | Legacy |  | Done |  | Barstølveien 19 |  |  |  | 500A | God Driv AS (https://www.notion.so/God-Driv-AS-1a8a1d8f955980e0ac76fb889741f4e4?pvs=21) | Not relevant | 4636 | Kristiansand | Signed |  |  | Jonas | 400 V | Project Sales | 344.54 | 2023-10-20 |  | Trapp fra innsiden av bygget. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Uploaded FDV |  |  | Not relevant |  |  | Done | GLITRE | Done | Completed |  |  | 2x Solis 110K-5G-PRO, 1x Solis S5-GC60K | Missing SolarLog (https://www.notion.so/Missing-SolarLog-727cd0eca8cb445297390268c98df39c?pvs=21), Missing FDV (https://www.notion.so/Missing-FDV-88a4a529c9154490bfbd9f802205a696?pvs=21) | Roof OK | No |  | Not applicable | 5706567293631271 (https://www.notion.so/5706567293631271-254517f12589457983d0ae4268be3a60?pvs=21) |  |  | Not relevant | PVC | 2024 | 690x505W LONGi LR5-66HPH505M | Done | Not interested |  | Not applicable | Kjetil |  |  |  |  | 139 | 2,072,221
In operation (COD) | Holmestrandsveien 117, 3036 Drammen |  | 160.08 | 2024-05-06 | 2024-07-25 | 2024-05-06 | 2024-06-07 | 2024-07-25 | 160.08 | Transferred | 🟨 80 days | 80 | 🟩 32 days | 32 | 🟩 48 days | 48 | 🟨 288 days | 288 | 🟨 208 days | 208 | 0.16 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Jul | 2406 | 0 | 1,343.479166666667 | 1.343479166667 | 🟥 SUM! | 123.90192 | 123,901.92 | 2024 - Q3 | 2024 - Q2 | 2023 - Q4 | 0 | 4.002 |  |  | 0 | 0 | 1,017,186 | ⌚ 615 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 160.08 | 101.081 | 0.631440529735 | 386.922 | 285.841 | 285.841 | 101.081 | 0.631440529735 | 6.354235382309 | 0 | 0 | 0.1 | 101.081 | 2026-02-01 | 454.041 | 0 | 🟩 NoCs: 0 | 0.92 | 1.785613443278 | 2026-02-01 | 0 | 5.722794852574 | 2.417053973013 | 916.105 | 5.722794852574 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0.16 | 285.841 | 67.119 | 0 | 6.354235382309 | 0 | 916.105 | 2023-10-27 | Deployment/Energieffektivisering_med_solcelleanlegg_Holmestrandsveien_117.pdf |  |  | 100% | NTE | thing_3433cbbc-969c-505e-9185-5a2e34622525 (https://www.notion.so/thing_3433cbbc-969c-505e-9185-5a2e34622525-2cee79d769844a36942b3ce4c5bb3ab8?pvs=21) | Done | 285.841 | Holmestrandsveien 117 | EM Teknikk - Energi AS v/ Oddvar Schjøtt-Høiholt |  | Payment received | 2500A | Carnegie AS (https://www.notion.so/Carnegie-AS-1a7a1d8f955980b59e5aee0d20d14161?pvs=21) | Yes - all PPAs | 3036 | Drammen | Signed |  | Holmestrandsveien 117 AS (https://www.notion.so/Holmestrandsveien-117-AS-311a1d8f955980e4995ec8f4541168bb?pvs=21) | Rikard | 400 V | Solar as a Service | 130 | 2023-10-11 | Jarle Halvorsen (https://www.notion.so/Jarle-Halvorsen-1a5a1d8f9559800da068f1ac13dd3c8d?pvs=21) |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nirun Vigneswaran (https://www.notion.so/Nirun-Vigneswaran-1a5a1d8f9559805fa2c0cc4d612a1534?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | Retrofit - GoO earnout | Applied | 2025-01-31 | Done | GLITRE | Done | Completed | H117 2025 (https://www.notion.so/H117-2025-206a1d8f9559801aafceefc96e7b5c16?pvs=21) | Default | 1x Solis 110K-5G-PRO | Grid no grid (https://www.notion.so/Grid-no-grid-230a1d8f955980df85ebcdd8278ca401?pvs=21), Fuse tripping (https://www.notion.so/Fuse-tripping-24ca1d8f955980d08a96e54b6ae4f2d2?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992901829915 (https://www.notion.so/7359992901829915-26629d6754b94d7daacd81f58d643759?pvs=21), 7359992932891318 (https://www.notion.so/7359992932891318-229a1d8f95598080a403dbbeeac813e5?pvs=21) |  |  | Done | Asfaltpapp | 2023 | 276x580W Tongwei TWMND-72HD | Done | In operation |  | Installed | Kjetil |  |  |  |  | 60 | 856.105
In operation (COD) | Stemmane 6, 4636 Kristiansand |  | 653.1 | 2023-10-30 | 2024-05-15 | 2023-10-30 | 2024-03-18 | 2024-05-15 | 653.1 | N/A | 🟥 198 days | 198 | 🟥 140 days | 140 | 🟩 58 days | 58 | 🟨 208 days | 208 | 🟩 10 days | 10 | 0.65 | 0 | 🟩 All good | 61.86 | ❌ End date missing | ❌ Missing | 24 - May | 2403 | 0 | 2,899.225961538462 | 2.899225961538 | 🟥 SUM! | 572.7687 | 572,768.7 | 2024 - Q2 | 2023 - Q4 | 2023 - Q4 | 0 | 39.186 | 40,400.766 | 40,400.766 | 0 | 0 | 4,712,442 | ⌚ 686 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 653.1 | 603.039 | 0.923348644924 | 603.039 | 0 | 0 | 603.039 | 0.923348644924 | 7.215498392283 | 0 | 0 | 0.6 | 603.039 | 4.71 | 603.039 | 0 | 🟩 NoCs: 0 | 2026-11-04 | 0 | 4.71 | 0 | 6.292149747359 | 0.923348644924 | 4,109,403 | 6.292149747359 | 0 | 0 | 0 | 0 | 0 | 2026-11-04 | 0.65 | 0 | 0 | 0 | 7.215498392283 | 0 | 4,109,403 | [5 empty] | Smart | thing_df6ddb64-07bd-42d9-b61b-959aa673a5da (https://www.notion.so/thing_df6ddb64-07bd-42d9-b61b-959aa673a5da-e3fe4db7676f4927a9870a18177af3ad?pvs=21) | Done |  | Stemmane 6 |  |  |  | 960A | Ivar Mjåland Eiendom AS (https://www.notion.so/Ivar-Mj-land-Eiendom-AS-1a8a1d8f9559801dbb97eadd7cf11307?pvs=21) | Not relevant | 4636 | Kristiansand | Signed |  | MRK Eiendom (https://www.notion.so/MRK-Eiendom-247a1d8f955980a59fcbd1fe2882ab93?pvs=21) | Rikard | 400 V | Project Sales | 622 | 2023-10-20 | Thor Gunnar Åsheim (https://www.notion.so/Thor-Gunnar-sheim-1a5a1d8f95598034b93bc14a01c524bd?pvs=21) | Stige opp til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rino Ombudstvedt (https://www.notion.so/Rino-Ombudstvedt-1a5a1d8f955980218040c8e684568b18?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | GLITRE | Done | Completed |  |  | 4x Sungrow 125CX-P2 | Stemmane 6 is down (https://www.notion.so/Stemmane-6-is-down-d251f07d4f654128beccbfa6735ff83f?pvs=21), Missing FDV (https://www.notion.so/Missing-FDV-a83687fb3afa430ba98cc505d69b644b?pvs=21), Broken module (https://www.notion.so/Broken-module-1e0a1d8f955980da9b45e75cecf2453e?pvs=21), No production (https://www.notion.so/No-production-218a1d8f9559805d9b14c30b19ec2be1?pvs=21), “Tilsynsrapport fra DLE” (https://www.notion.so/Tilsynsrapport-fra-DLE-24fa1d8f95598074841dc91be02f9b90?pvs=21) | Roof OK | No |  | Not applicable | 5706567288737179 (https://www.notion.so/5706567288737179-11aa1d8f9559804fada9cbf6ef9dd3d9?pvs=21) |  | Received | Not relevant | PVC | 2023 | 1244x525W LONGi LR5-66HPH 525M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 264 | 3,845,403
On hold | Deliveien 4, 1540 Vestby |  | 302.76 |  |  |  |  | 2026-12-31 |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 1149 days | 1149 | 🟥 875 days (ongoing) | 875 | 0.3 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Dec |  | 0 | 850.885117493473 | 0.850885117493 | 🟥 SUM! | 241.60248 | 241,602.48 | 2026 - Q4 |  | 2023 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,312,000 | 🔸🕐 -273 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2023 | -302.76 | 302.76 | 705.052 | 2.328748843969 | 977.667 | 272.615 | 272.615 | 705.052 | 2.328748843969 | 7.636411679218 | 0 | 0 | 0 | 0 | 0 | 272.615 | 0 | 🟩 NoCs: 0 | 1.61 | 0.900432685956 | 2.31 | 0 | 5.307662835249 | 3.229181529925 | 1,606,948 | 5.307662835249 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 272.615 | 0 | 0 |  | 0 | 1,606,948 | 2024-10-15 | Deployment/Deliveien_4_-_Energieffektivisering_med_solcelleanlegg.pdf | 6.64 | Enova-søknad sendt | 100% |  |  |  | 272.615 | Deliveien 4 | COWI v/ AKAM |  | Application: Successful |  | Greenwich Land Securities AS (https://www.notion.so/Greenwich-Land-Securities-AS-1a8a1d8f955980d882d8dd3c7a47afee?pvs=21) |  | 1540 | Vestby | Signed |  |  | Rikard | 400 V | Solar as a Service | 445 | 2023-11-08 |  |  |  |  | Not uploaded | [5 empty] | Not started | ELVIA | No status | Not completed |  |  | 2x Solis 110K-5G-PRO |  |  | TBD | Ikke søknadspliktig | Approved |  |  |  |  | TBD - skal tekkes om | 2009 | 522x580W Tongwei TWMND-72HD | [9 empty] | 120 | 1,486,948
In operation (COD) | Grudevegen 2, 4351 Kleppe |  | 135.72 | 2024-08-29 | 2024-12-03 | 2024-08-29 | 2024-10-10 | 2024-12-03 | 135.72 | Transferred | 🟨 96 days | 96 | 🟨 42 days | 42 | 🟩 54 days | 54 | 🟥 372 days | 372 | 🟨 276 days | 276 | 0.14 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Dec | 2410 | 0 | 649.731182795699 | 0.649731182796 | 🟥 SUM! | 115.49772 | 115,497.72 | 2024 - Q4 | 2024 - Q3 | 2023 - Q4 | 0 | 3.393 |  |  | 0 | 0 | 858.746 | ⌚ 484 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 135.72 | -34.743 | -0.255990274094 | 241.7 | 276.443 | 276.443 | -34.743 | -0.255990274094 | 6.327335691129 | 0 | 0 | -0.03 | -34.743 | 0.86 | 241.7 | 0 | 🟩 NoCs: 0 | 0.89 | 2.036862658415 | 0.86 | 0 | 6.583325965223 | 1.780872384321 | 893.489 | 6.583325965223 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0.14 | 276.443 | 0 | 0 | 6.327335691129 | 0 | 893.489 | 2024-03-22 | Deployment/Energieffektivisering_med_solcelleanlegg-2%202.pdf |  |  | 100% | NTE | thing_ef27caaf-6fd3-505a-ac77-b54a87095969 (https://www.notion.so/thing_ef27caaf-6fd3-505a-ac77-b54a87095969-064de640ca7c4a68a46f6705281fa0ad?pvs=21) | N/A | 276.443 | Grudevegen 2 | BTS-Consulting AS, Erlend Bøgwald |  | Payment received | 250A | Kyvik Gruppen AS (https://www.notion.so/Kyvik-Gruppen-AS-1a8a1d8f955980e4acf6ef39c334b9d9?pvs=21) | No | 4351 | Kleppe | Signed |  |  | Jonas | 400 V | Solar as a Service | 158 | 2023-11-27 |  | Ingen tilkomst | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rasmus Svebestad (https://www.notion.so/Rasmus-Svebestad-1a5a1d8f9559803d892ee708d78dd434?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | GoO priced in APA |  | 2025-01-31 | Done | LNETT | Done | Completed |  | Default | 1x Sungrow SG110CX | No production (https://www.notion.so/No-production-196a1d8f955980348b08df41740bcf5f?pvs=21), 2/3 export (https://www.notion.so/2-3-export-1aea1d8f955980729ed6e90ba4b94252?pvs=21) | Roof OK | Yes | 12.06: Ikke søknadspliktig. | Approved | 7359992921544836 (https://www.notion.so/7359992921544836-153a1d8f9559808093b9cea17c53e7f0?pvs=21) |  |  | Not relevant | PVC | 2015 | 234x580W Tongwei TWMND-72HD | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 60 | 833.489
In operation (COD) | Ingeniør Rybergs gate 99, 3027 Drammen |  | 163.2 | 2023-03-01 | 2023-07-10 | 2023-03-01 | 2023-04-01 | 2023-07-10 | 163.2 | Transferred | 🟨 131 days | 131 | 🟩 31 days | 31 | 🟨 100 days | 100 | 🟥 320 days | 320 | 🟩 189 days | 189 | 0.16 | 0 | 🟩 All good | 25 | 🟩 956 days left | 💚 All good | 23 - Jul | 2304 | 0 | 811.875 | 0.811875 | 🟥 SUM! | 126.3168 | 126,316.8 | 2023 - Q3 | 2023 - Q1 | 2022 - Q3 | 0 | 4.08 | 4.08 | 4.08 | 0 | 0 | 1,445,676 | ⌚ 996 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0 | 163.2 | 259.8 | 1.591911764706 | 259.8 | 0 | 0 | 259.8 | 1.591911764706 | 8.858308823529 | 0 | 0 | 0.26 | 259.8 | 1.45 | 314.985 | 0 | 🟩 NoCs: 0 | 1.19 | 0 | 1.45 | 0 | 7.266397058824 | 1.591911764706 | 1,185,876 | 7.266397058824 | 0 | 0 | 0 | 0 | 0 | 1.19 | 0.16 | 0 | 55.185 | 0 | 8.858308823529 | 0 | 1,185,876 | [5 empty] | NTE | thing_ca7b69fc-d4a6-40e5-a8c2-6a045e3ceffb (https://www.notion.so/thing_ca7b69fc-d4a6-40e5-a8c2-6a045e3ceffb-8ea314c063334d00b3bf9cebe38c83e9?pvs=21) | N/A |  | Ingeniør Rybergs gate 99 |  |  | Does not qualify | 250A | Brække Eiendom AS (https://www.notion.so/Br-kke-Eiendom-AS-1a8a1d8f955980e98516e82f55b2e603?pvs=21) | Yes - all PPAs | 3027 | Drammen | Signed |  |  | Jonas | 230 V | Solar as a Service | 215.5 | 2022-08-24 | Allen Carlsen (https://www.notion.so/Allen-Carlsen-1a5a1d8f9559800eb9dce1ad7bd5eadf?pvs=21) | Bruke OLH nøkkel på bakside av bygg for å komme deg inn i teknisk rom. Der er det stige som kan benyttes for å komme opp til inspeksjonsstigen og videre til taket. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Dragan Zoric (https://www.notion.so/Dragan-Zoric-1a5a1d8f955980878e29d59ffb12fb90?pvs=21), Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | Approved | 2028-11-13 | Retrofit - GoO earnout | To be applied |  | Done | GLITRE | Done | Completed | IRG99 2025 (https://www.notion.so/IRG99-2025-209a1d8f9559806a8cfcf441a536d329?pvs=21) | Default | 2x Solis 60K-5G-LV | 50kW inverter instead of 60kW (https://www.notion.so/50kW-inverter-instead-of-60kW-2f98393f25bc4c8bba5cba2e2a6464e3?pvs=21), Check if the fan problem on IRG99 Rush goes away (https://www.notion.so/Check-if-the-fan-problem-on-IRG99-Rush-goes-away-18042a37f0e8451fac551040bb790212?pvs=21), Solar-Log not working (https://www.notion.so/Solar-Log-not-working-4c859739bac6412ba44f13228359e895?pvs=21), Inv 2 og 3: Warning Fan Fault (https://www.notion.so/Inv-2-og-3-Warning-Fan-Fault-2344a3550f954b469bca033fc5f6cc89?pvs=21), Warning Fan Fault (https://www.notion.so/Warning-Fan-Fault-12ea1d8f955980c19c37c9dc199d0ed9?pvs=21), No data for drammen padel and rush (https://www.notion.so/No-data-for-drammen-padel-and-rush-138a1d8f95598003848fdad86806328c?pvs=21), No production (https://www.notion.so/No-production-14ca1d8f955980ca9bcac11f2f8c6b7f?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992903526201 (https://www.notion.so/7359992903526201-11aa1d8f95598033aedae98559ccf811?pvs=21) |  |  | To be started | PVC | 2018 | 320x510W Longi LR5-66HPH 510M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 160 | 1,025,876
In operation (COD) | Lysaker Torg 6-10, 1366 Lysaker |  | 134.7 | 2024-01-04 | 2024-05-14 | 2024-01-04 | 2024-03-05 | 2024-05-14 | 128.31 | N/A | 🟨 131 days | 131 | 🟥 61 days | 61 | 🟨 70 days | 70 | 🟩 187 days | 187 | 🟩 56 days | 56 | 0.13 | 0 | 🟩 All good | 87.635 | ❌ End date missing | ❌ Missing | 24 - May | 2403 | 0 | 1,323.133689839572 | 1.32313368984 | 🟥 SUM! | 100.59504 | 100,595.04 | 2024 - Q2 | 2024 - Q1 | 2023 - Q4 | 0 | 10,906.35 | 11,244.44685 | 11,244.44685 | 0 | 0 | 1,135,521 | ⌚ 687 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | -6.39 | 128.31 | 247.426 | 1.928345413452 | 247.426 | 0 | 0 | 247.426 | 1.928345413452 | 8.43 | 0 | 0 | 0.25 | 247.426 | 1.14 | 247.426 | 0 | 🟩 NoCs: 0 | 0.89 | 0 | 1.14 | 0 | 6.92147922999 | 1.928345413452 | 888.095 | 6.593132887899 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0.13 | 0 | 0 | 0 | 8.849824643442 | 0 | 888.095 | [5 empty] | Premium | thing_9a1cc5b1-371b-576b-9cf9-b0e79cd1feca (https://www.notion.so/thing_9a1cc5b1-371b-576b-9cf9-b0e79cd1feca-14ca1d8f955980659c1dfc1309d21a19?pvs=21) | Done |  | Lysaker Torg 6-10 |  |  |  | 2500A (justert ned til 2000A) | Farvatn Capital AS (https://www.notion.so/Farvatn-Capital-AS-1a8a1d8f9559809bbc2fed4a07a94774?pvs=21) | Not relevant | 1366 | Lysaker | Signed |  | Lysaker Torg 6-12 Ans (https://www.notion.so/Lysaker-Torg-6-12-Ans-247a1d8f955980049facf5dd557d2abf?pvs=21) | Rikard | 400 V | Project Sales | 141 | 2023-11-09 | Marius Bakken (https://www.notion.so/Marius-Bakken-1a5a1d8f955980d99f9bd258f1c8daf3?pvs=21) | Tilkomst til taket via innsiden av bygget. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Uploaded FDV |  |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 1x Solis 110K-5G-PRO | No data found (https://www.notion.so/No-data-found-a410f9dbcf184b738b7acfe3edf3e117?pvs=21), Incorrect declaration of conformity (https://www.notion.so/Incorrect-declaration-of-conformity-441ac3e6293b4f42b60e6a24af4db3d5?pvs=21) | Roof OK | No |  | Not applicable | 7359992926464702 (https://www.notion.so/7359992926464702-11aa1d8f95598097a200dde5744a432d?pvs=21) |  |  | Not relevant | Asfaltpapp |  | Installert: 282x455W Ulica UL-455M-144HV Levert: 296x455W Ulica UL-455M-144HV (kunde ønsket ekstra paneler i tilfelle noe må byttes) | Done | Not started |  | Delivered to installer | Kjetil |  |  |  |  | 69.145 | 818.95
In operation (COD) | Orhusveien 77, 3070 Sande I Vestfold |  | 1,271.16 | 2024-01-12 | 2024-08-29 | 2024-01-12 | 2024-04-02 | 2024-08-29 | 1,271.16 | Transferred | 🟥 230 days | 230 | 🟥 81 days | 81 | 🟥 149 days | 149 | 🟨 277 days | 277 | 🟩 47 days | 47 | 1.27 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 2026-08-24 | 2404 | 0 | 5,730.956678700361 | 5.7309566787 | 🟥 SUM! | 1,011.84336 | 1,011,843.36 | 2024 - Q3 | 2024 - Q1 | 2023 - Q4 | 0 | 31.779 |  |  | 0 | 0 | 8,777,528 | ⌚ 580 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 0 | 1,271.16 | 1,587,475 | 1.248839642531 | 1,587,475 | 0 | 0 | 1,587,475 | 1.248839642531 | 6.905132320086 | 0 | 0 | 1.59 | 1,587,475 | 8.78 | 1,915,853 | 0 | 🟩 NoCs: 0 | 7.19 | 0 | 8.78 | 0 | 5.656292677554 | 1.248839642531 | 7,190,053 | 5.656292677554 | 0 | 0 | 0 | 0 | 0 | 7.19 | 1.27 | 0 | 328.378 | 0 | 6.905132320086 | 0 | 7,190,053 |  |  |  | Kvalifiserer ikke pga nybygg |  | NTE | thing_b3dcf7a0-2b74-4413-9b78-a2d5567d331f (https://www.notion.so/thing_b3dcf7a0-2b74-4413-9b78-a2d5567d331f-6501e4092028440290445df23b5b49f9?pvs=21) | Done |  | Orhusveien 77 |  |  | Does not qualify | 1250A (økt til 1600A for buffer) | Pareto AS (https://www.notion.so/Pareto-AS-1a7a1d8f955980b6b8cce7e4ff90df80?pvs=21) | Yes - all PPAs | 3070 | Sande I Vestfold | Signed |  | Orhusveien 75-77 AS (https://www.notion.so/Orhusveien-75-77-AS-311a1d8f9559801d96e1c12dd05d1b6a?pvs=21) | Jonas | 400 V | Solar as a Service | 1.287 | 2023-11-26 | Thomas Grotli (https://www.notion.so/Thomas-Grotli-1a5a1d8f95598029a544cd5b58254853?pvs=21), Preben Kildal Langseth (https://www.notion.so/Preben-Kildal-Langseth-1a5a1d8f955980839437fdd8221a2e84?pvs=21), Bjørn Stengrimsen (https://www.notion.so/Bj-rn-Stengrimsen-1a5a1d8f955980eea0f3cece316ea863?pvs=21) | Spiraltrapp opp på taket nord-øst på bygningen. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Per-Christian Vadvedt (https://www.notion.so/Per-Christian-Vadvedt-1a5a1d8f95598095b1d1c3f9c19e0aa1?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | GoO priced in APA |  | 2025-01-31 | Done | LEDE | Done | Completed | O77 2025 (https://www.notion.so/O77-2025-218a1d8f955980229cf8d66ba6993e8f?pvs=21) | Default | 8x Solis 110K-5G-PRO 1x Solis GC-60K | No communication with plant (https://www.notion.so/No-communication-with-plant-111a1d8f955980b485b2c71428214bb0?pvs=21), No data (https://www.notion.so/No-data-138a1d8f955980c09bddd391ce9dd249?pvs=21), Inverter 9 shows consistently lower production (https://www.notion.so/Inverter-9-shows-consistently-lower-production-13ea1d8f955980b6b88eeaab1b7a8a94?pvs=21), Peculiar data (https://www.notion.so/Peculiar-data-192a1d8f95598052ad47fef88ddde26c?pvs=21), Too low production (https://www.notion.so/Too-low-production-207a1d8f95598001bc42e951ceb0c137?pvs=21) | Roof OK | Yes | Rammetillattelse | Approved | 7359992935159002 (https://www.notion.so/7359992935159002-100a1d8f95598031a370f378c92bbd79?pvs=21), 7359992935159996 (https://www.notion.so/7359992935159996-100a1d8f955980ab82fafb5a6b24bd0d?pvs=21), 7359992935157169 (https://www.notion.so/7359992935157169-b5f1b80a3924408f877703afbb7e7ff7?pvs=21), 7359992935157213 (https://www.notion.so/7359992935157213-11aa1d8f9559809b837bf14d7dfbe006?pvs=21), 7359992922902925 (https://www.notion.so/7359992922902925-11aa1d8f95598042b6a8d84d78397711?pvs=21) |  |  | Not relevant | PVC | 2024 | 2376x535W LONGi LR5-66HTH | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 315.5 | 6,874,553
In operation (COD) | Nensetbakken 27-29, 3736 Skien |  | 230.28 | 2024-07-17 | 2024-10-24 | 2024-07-17 | 2024-08-06 | 2024-10-24 | 225.17 | Transferred | 🟨 99 days | 99 | 🟩 20 days | 20 | 🟨 79 days | 79 | 🟥 308 days | 308 | 🟨 209 days | 209 | 0.23 | 0 | 🟩 All good |  | 🟩 1386 days left | 💚 All good | 24 - Oct | 2408 | 0 | 555.376623376623 | 0.555376623377 | 🟥 SUM! | 188.01695 | 188,016.95 | 2024 - Q4 | 2024 - Q3 | 2023 - Q4 | 0 | 5,629.25 |  |  | 0 | 0 | 1,595,183 | ⌚ 524 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | -5.11 | 225.17 | 171.056 | 0.759674912288 | 171.056 | 0 | 0 | 171.056 | 0.759674912288 | 6.927145214521 | 0 | 0 | 0.17 | 171.056 | 2026-06-01 | 214.113 | 0 | 🟩 NoCs: 0 | 1.42 | 0 | 2026-06-01 | 0 | 6.324674690234 | 0.759674912288 | 1,424,127 | 6.184327774883 | 0 | 0 | 0 | 0 | 0 | 1.42 | 0.23 | 0 | 43.057 | 0 | 7.084349602523 | 0 | 1,424,127 |  |  |  | Kvalifiserer ikke grunnet mindre enn 20% forbedring |  | NTE | thing_9108f696-2dea-58f8-9d65-e44362fb74ff (https://www.notion.so/thing_9108f696-2dea-58f8-9d65-e44362fb74ff-f1cbad6981064319b632f8e3f3c6081d?pvs=21) | N/A |  | Nensetbakken 27-29 |  |  | Does not qualify | 500A | Telemark Bygginvest AS (https://www.notion.so/Telemark-Bygginvest-AS-1a8a1d8f95598000872cfb6a7c6039ab?pvs=21) | Yes - all PPAs | 3736 | Skien | Signed |  |  | Ole Bjørn | 400 V | Solar as a Service | 212 | 2023-12-21 | Peder Rui Sørheim (https://www.notion.so/Peder-Rui-S-rheim-1a5a1d8f95598063bcffc83f64f8e3fd?pvs=21) | Fastmontert stige på fasaden med ryggsøyle fra bakkeplan. Nøkler inne hos NAF. | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved | 2030-01-17 | GoO priced in APA |  | 2025-01-17 | Done | LEDE | Done | Completed |  | Default | 2x Solis 110 kW | Bad inverter (https://www.notion.so/Bad-inverter-130a1d8f9559802f8985ebfc549855f0?pvs=21) | Roof OK | Yes | Generell godkjenning fra Skien kommune | Approved | 7359992933171266 (https://www.notion.so/7359992933171266-129a1d8f95598053aa60c7990e6bf019?pvs=21), 7359992894591813 (https://www.notion.so/7359992894591813-129a1d8f955980dd9437c7cee5ff8800?pvs=21) |  |  | Not relevant | Asfaltpapp |  | 506x445W DMGEC | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 241.6 | 1,182,527
In operation (COD) | Bjørnerudveien 14, 1266 Oslo |  | 320.16 | 2024-07-04 | 2024-09-13 | 2024-07-04 | 2024-08-05 | 2024-09-13 | 323.64 | Transferred | 🟨 71 days | 71 | 🟩 32 days | 32 | 🟩 39 days | 39 | 🟨 249 days | 249 | 🟩 178 days | 178 | 0.32 | 0 | 🟩 All good |  | 🟩 1386 days left | 💚 All good | 2026-09-24 | 2408 | 0 | 2,009.746987951807 | 2.009746987952 | 🟥 SUM! | 256.64652 | 256,646.52 | 2024 - Q3 | 2024 - Q3 | 2024 - Q1 | 0 | 8.091 |  |  | 0 | 0 | 2,302,471 | ⌚ 565 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 3.48 | 323.64 | 183.416 | 0.566728463725 | 500.427 | 317.011 | 317.011 | 183.416 | 0.566728463725 | 7.191626061969 | 0 | 0 | 0.18 | 183.416 | 2026-03-02 | 500.427 | 0 | 🟩 NoCs: 0 | 2026-12-02 | 0.979517364974 | 2026-03-02 | 0 | 6.54756828575 | 1.546245828699 | 2,119,055 | 6.618737506247 | 0 | 122.614 | 0 | 122.614 | 0 | 2026-12-02 | 0.32 | 317.011 | 0 | 0 | 7.114296749475 | 0 | 2,119,055 | 2024-10-15 | Deployment/Energieffektivisering_med_solcelleanlegg_Bjrnerudveien_14.pdf, Deployment/rapport-10.pdf |  |  | 50% | NTE | thing_0f36e9ce-3c1a-51c5-a48b-1897d3b63622 (https://www.notion.so/thing_0f36e9ce-3c1a-51c5-a48b-1897d3b63622-d2e98c40927e4e7caaae38d2adee7a23?pvs=21) | Done | 634.022 | Bjørnerudveien 14 | GK Norge AS v/ Tom Nguyen |  | Payment received | 400 | Spabo Eiendom AS (https://www.notion.so/Spabo-Eiendom-AS-1a8a1d8f955980e7bee0e8946fff87bb?pvs=21) | Yes - all PPAs | 1266 | Oslo | Signed |  | Hauketo Eiendom AS (https://www.notion.so/Hauketo-Eiendom-AS-311a1d8f95598068bad4efa8e0b28e31?pvs=21) | Rikard | 400 V | Solar as a Service | 308 | 2024-01-08 |  | Fra bakkeplan vis stige med ryggsøyle. | Solcellekraft AS (https://www.notion.so/Solcellekraft-AS-1aba1d8f955980778682ce1973340572?pvs=21) | Daniel Angeltveit Lie (https://www.notion.so/Daniel-Angeltveit-Lie-1a5a1d8f95598065afc2f97b82177db2?pvs=21) | Uploaded FDV | Approved | 2030-01-17 | Retrofit - GoO earnout | Retrofit not completed | 2025-01-17 | Done | ELVIA | Done | Completed | B14 2025 (https://www.notion.so/B14-2025-173a1d8f955980bdaa95fae53f433ca8?pvs=21) | Default | 2x Growatt MAX 100KTL3-X LV |  | Roof OK | Retrofit | Ikke søknadspliktig. | Approved | 7359992907396916 (https://www.notion.so/7359992907396916-11aa1d8f955980c1a8adecab48a6f84f?pvs=21) |  |  | To be started | Asfaltpapp | 2024 | 558x580W LONGi LR5-72HTH | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 0 | 2,119,055
In operation (COD) | Fossveien 43, 4373 Egersund |  | 886.24 | 2025-01-31 | 2025-05-21 | 2025-01-31 | 2025-04-01 | 2025-05-21 | 886.24 | Transferred | 🟨 110 days | 110 | 🟨 60 days | 60 | 🟩 50 days | 50 | 🟨 204 days | 204 | 🟩 94 days | 94 | 0.89 | 9.945 | 🟩 All good |  | ❌ End date missing | 💚 All good | 25 - May | 2504 | 843,162.4 | 4,133.14705882353 | 4.133147058824 | 🟩 OK! | 736.46544 | 736,465.44 | 2025 - Q2 | 2025 - Q1 | 2024 - Q4 | 531,326.4 | 22.156 |  |  | 321.781 | 5,071,781 | 5,071,781 | ⌚ 315 days | 531,326.4 | 321.781 | 843,162.4 | 0 | 5,071,781 | 321.781 | 321.781 | 0 | 321.781 | 5,071,781 | 2025 | 2024 | 0 | 886.24 | 321.781 | 0.363085620148 | 843.162 | 531,326.4 | 531,326.4 | 321.781 | 0.363085620148 | 5.722807591623 | 0 | 0 | 0.32 | 321.781 | 2026-07-05 | 843.162 | 9.945 | 🟩 NoCs: 0 | 4.75 | 0.588306779202 | 2026-07-05 | 0 | 5.359721971475 | 0.95139239935 | 4,750,000 | 5.359721971475 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0.89 | 531.326 | 0 | 0 | 5.722807591623 | 0 | 4,750,000 | 2024-08-30 | Deployment/Fossveien_43_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  | 40% | NTE | thing_26ded7be-0a08-543b-a92d-841f06995033 (https://www.notion.so/thing_26ded7be-0a08-543b-a92d-841f06995033-1c2a1d8f95598014a1a5ffb83cebe5da?pvs=21) | In progress | 1,328,316 | Fossveien 43 |  | Yes | Payment received | 800A (nedjustert til 630A) | God Driv AS (https://www.notion.so/God-Driv-AS-1a8a1d8f955980e0ac76fb889741f4e4?pvs=21) | Yes - not all PPAs | 4373 | Egersund | Signed |  | Tengsareid III AS (https://www.notion.so/Tengsareid-III-AS-1a7a1d8f95598017839eceb0099ae527?pvs=21) | Jonas | 400 V | Solar as a Service | 805 | 2024-10-29 |  | Fra bakkeplan med fastmontert stige. Det er nøkler til takstige i nøkkelboks på siden av dør til lager seksjon C. Kode nøkkel boks 2354. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21), Atle Doksrud (https://www.notion.so/Atle-Doksrud-1a5a1d8f955980cd9307ee28464c98ec?pvs=21), Kim Andre Johansen (https://www.notion.so/Kim-Andre-Johansen-1e3a1d8f9559805fb8e3f75f67b4bd0d?pvs=21) | Uploaded FDV | Approved |  | GoO priced in APA |  | 2025-09-17 | Done | ENIDA | Done | Completed |  | Default | 5x Growatt MAX 100KTL3-X LV | Only 1/3 phases are connected (https://www.notion.so/Only-1-3-phases-are-connected-217a1d8f95598068bfd9dfd936f4c383?pvs=21), Fixed ca. 15% curtailment on all inverters (https://www.notion.so/Fixed-ca-15-curtailment-on-all-inverters-218a1d8f95598080b06fcdf9485ed0e4?pvs=21) | Roof OK | Yes |  | Approved | 5706567338651912 (https://www.notion.so/5706567338651912-18ca1d8f955980fd9a5aff07cbe19208?pvs=21), 5706567299617491 (https://www.notion.so/5706567299617491-18ca1d8f95598017a24bd78ba1d0993c?pvs=21), 5706567338652001 (https://www.notion.so/5706567338652001-206a1d8f95598098816de735743f783b?pvs=21), 5706567338651943 (https://www.notion.so/5706567338651943-20ea1d8f9559801386abc0a45f603ea5?pvs=21) |  | Received | Not relevant | Installatør vet | 2024 | 1528x580W PhonoSolar Premium bifacial | Done | Not started | 28.01.26: Sendt på nytt med festenummer 02.10: fått i retur. Fått nummer til saksbehandler: 32 11 88 34 | Installed | Kjetil |  |  |  |  | 360 | 4,390,000
In operation (COD) | Fiboveien 12E, 4580 Lyngdal |  | 186.48 | 2023-08-17 | 2024-02-06 | 2023-08-17 | 2023-09-14 | 2024-02-06 | 186.48 | Transferred | 🟥 173 days | 173 | 🟩 28 days | 28 | 🟥 145 days | 145 | 🟥 452 days | 452 | 🟨 279 days | 279 | 0.19 | 0 | 🟩 All good | 25 | 🟩 1074 days left | 💚 All good | 2026-02-24 | 2309 | 0 | 516.519911504425 | 0.516519911504 | 🟥 SUM! | 161.11872 | 161,118.72 | 2024 - Q1 | 2023 - Q3 | 2022 - Q4 | 0 | 4.662 | 4.662 | 8.547 | 0 | 0 | 1,546,810 | ⌚ 785 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2022 | 0 | 186.48 | 233.467 | 1.251968039468 | 233.467 | 0 | 0 | 233.467 | 1.251968039468 | 8.294776919777 | 0 | 0 | 0.23 | 233.467 | 1.55 | 389.987 | 0 | 🟩 NoCs: 0 | 1.31 | 0 | 1.55 | 0 | 7.042808880309 | 1.251968039468 | 1,313,343 | 7.042808880309 | 0 | 0 | 0 | 0 | 156.52 | 1.31 | 0.19 | 0 | 0 | 156.52 | 8.294776919777 | 0 | 1,313,343 | [5 empty] | NTE | thing_1fd61088-14ed-5cad-981f-264d444932e2 (https://www.notion.so/thing_1fd61088-14ed-5cad-981f-264d444932e2-22ca1d8f95598086a49aeefd05838691?pvs=21) | Done |  | Fiboveien 12E |  |  | Does not qualify | 500A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Pending | 4580 | Lyngdal | Signed |  |  | Rikard | 400 V | Solar as a Service | 365 | 2022-11-11 | Simen Halse (https://www.notion.so/Simen-Halse-1a5a1d8f955980b7b756da7f6c69fcf2?pvs=21) | Inspeksjonsstige bak bygget hos Plantasjen. Må inn via Plantasjen sitt uteområdet. Kodelås: 4580 (samme som postnr.) | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | Uploaded FDV | Approved | 2029-03-11 | GoO priced in APA |  |  | Done | GLITRE | Done | Completed | F12E 2025 (https://www.notion.so/F12E-2025-23ea1d8f9559807a960cc63a4af6241b?pvs=21) | Default | 1x Sungrow SG125CX-P2 | Inverter cuts production at 115 kW (https://www.notion.so/Inverter-cuts-production-at-115-kW-b91d73ea88674160bc25cf9e2a509b2a?pvs=21), Wrong kWp in SolarLog (https://www.notion.so/Wrong-kWp-in-SolarLog-4fcfb68d00834c3c83ac6a369d326c10?pvs=21), Capped production (https://www.notion.so/Capped-production-8a4cf2e0d9614d7fbeb1ce7d1c99349c?pvs=21) | Roof OK | Yes |  | Approved | 5706567333537211 (https://www.notion.so/5706567333537211-11aa1d8f9559803ba942fbe75396e7a1?pvs=21), 5706567293632117 (https://www.notion.so/5706567293632117-18fa1d8f955980c89965caa884a95c14?pvs=21) |  |  | Not relevant | Papp | 2018 | 336x555W LONGi LR5-72HPH | Done | Not interested | Siri følger opp - sendt med 14A | Installed | Kjetil |  |  |  |  | 100 | 1,213,343
In operation (COD) | Hoffsveien 10, 0275 Oslo |  | 99 |  | 2021-08-01 |  | 2021-06-01 | 2021-08-01 | 99 | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | 🟨 61 days | 61 | 🟩 39 days | 39 | 🟥 1743 days (ongoing) | 1743 | 0.1 | 0 | 🟧 Est. FID missing | 51.55 | ❌ End date missing | ❌ Missing | 2026-08-21 | 2106 | 0 | 0 | 0 | 🟥 SUM! | 76.527 | 76.527 | 2021 - Q3 |  | 2021 - Q2 | 0 | 4.95 | 5,103.45 | 5,103.45 | 0 | 0 |  | ⌚ 1704 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 2021 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Premium | thing_33cc5876-895c-5da5-993d-5fdf8d6d4c42 (https://www.notion.so/thing_33cc5876-895c-5da5-993d-5fdf8d6d4c42-c1ad2f85966c497f8dee9b9712e0a182?pvs=21) | Done |  | Hoffsveien 10 |  |  |  |  | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 275 | Oslo | Signed |  |  | Not set |  | Project Sales | 99 | 2021-06-23 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Wafa Mohammadi (https://www.notion.so/Wafa-Mohammadi-1a5a1d8f955980a487fac205c2007830?pvs=21) | Not uploaded | Not relevant |  |  |  |  | Done | ELVIA | Done | Completed |  |  | 1x Sungrow SG110CX | Three plants missing data (https://www.notion.so/Three-plants-missing-data-e8c2d1ae0cbf487bbee950fcd4f1751e?pvs=21) | Roof OK | No |  | Not applicable | 7359992907649326 (https://www.notion.so/7359992907649326-a0a6d3ec455546c3bf781598638d5e99?pvs=21) | [6 empty] | Not relevant | Not started |  | Installed | Alex
In operation (COD) | Gjennestadtunet 8, 3160 Stokke |  |  |  | 2020-01-29 |  |  | 2020-01-29 |  | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 152 days | 152 | 🟥 2406 days (ongoing) | 2406 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-01-20 |  | 0 | 0 | 0 | 🟥 SUM! | 0 | 0 | 2020 - Q1 |  | 2019 - Q3 | 0 | 0 |  |  | 0 | 0 |  | ⌚ 2254 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 2019 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [7 empty] | N/A |  | Gjennestadtunet 8 | [5 empty] | Not relevant | 3160 | Stokke | Signed |  |  | Not set |  | Project Sales |  | 2019-08-30 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) |  | Not uploaded | Not relevant |  | Not relevant |  |  | Done |  | Done | Completed |  |  |  |  | Roof OK | TBD |  | Approved | [7 empty] | Not relevant | Not started |  | Not applicable | Alex
In operation (COD) | Jeksleveien 50, 2016 Frogner |  | 442.8 | 2024-09-02 | 2024-09-18 | 2024-09-02 | 2024-09-18 | 2024-09-18 | 442.8 | Transferred | 🟩 16 days | 16 | 🟩 16 days | 16 | 🟩 0 days | 0 | 🟩 131 days | 131 | 🟩 115 days | 115 | 0.44 | 33.361 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 2026-09-24 | 2409 | -33.361 | 2,413.87786259542 | 2.413877862595 | 🟥 SUM! | 354.24 | 354.24 | 2024 - Q3 | 2024 - Q3 | 2024 - Q2 | 0 | 11.07 |  |  | 0 | 0 | 2,674,039 | ⌚ 560 days | 0 | 0 | -33.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0 | 442.8 | 349.579 | 0.789473803071 | 316.218 | 0 | 0 | 349.579 | 0.789473803071 | 6.038931797651 | 0 | 0 | 0.35 | 349.579 | 2.67 | 316.218 | 33.361 | 🟩 NoCs: 0 | 2.32 | -0.075341011743 | 2.67 | 0 | 5.24945799458 | 0.714132791328 | 2,324,460 | 5.24945799458 | 0 | 0 | 0 | 0 | 0 | 2.32 | 0.44 | 0 | 0 | 0 | 6.038931797651 | 0 | 2,324,460 | [5 empty] | NTE | thing_70dad92f-30df-58a1-91a9-3df6fb9561be (https://www.notion.so/thing_70dad92f-30df-58a1-91a9-3df6fb9561be-8fb877517a0c4d378f83c28eb39fd4a0?pvs=21) | Done |  | Jeksleveien 50 |  |  |  | 500A | KLP Eiendom AS (https://www.notion.so/KLP-Eiendom-AS-31fa1d8f955980ff8728e372c2a1efde?pvs=21) | No | 2016 | Frogner | Signed |  | KLP Jeksleveien 50 AS (https://www.notion.so/KLP-Jeksleveien-50-AS-31fa1d8f955980dea4e8fa2e404065fc?pvs=21) | Jonas | 400 V | Solar as a Service | 442.8 | 2024-05-10 | Petter Haugan (https://www.notion.so/Petter-Haugan-1a5a1d8f955980359272c7d77f7ea7e6?pvs=21) | Inspekssjonsstige med ryggsøyle på nordsiden av bygget. Tilkomst hele veien fra bakke til tak. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Robert Jernström (https://www.notion.so/Robert-Jernstr-m-1a5a1d8f95598025b2c3dbd0b8e68b6d?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | Retrofit - GoO earnout | Applied | 2025-01-31 | Done | ELVIA | Done | Completed | J50 2024 (https://www.notion.so/J50-2024-188a1d8f955980f2827cf7c103da88fa?pvs=21), J50 2025 (https://www.notion.so/J50-2025-213a1d8f9559805f84b6ca15110587c9?pvs=21) | Default | 3x Sungrow SG110CX | No Data (https://www.notion.so/No-Data-4bd5812bc0d6497bb507fa4efbe3bc7f?pvs=21), Alarm Run: System Alarm (https://www.notion.so/Alarm-Run-System-Alarm-12da1d8f955980a59d58d1804a966ca5?pvs=21), Lost connection to one inverter (https://www.notion.so/Lost-connection-to-one-inverter-153a1d8f9559802d9a28e185854994c5?pvs=21), Wrong kWp in SundayOS (https://www.notion.so/Wrong-kWp-in-SundayOS-196a1d8f9559801abcabc7b0ce1c950a?pvs=21), Connected to wrong smart meter (https://www.notion.so/Connected-to-wrong-smart-meter-1eda1d8f9559801ca4e3c3a88152cd65?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992936316497 (https://www.notion.so/7359992936316497-e3d1e64e83644b3b87acedec358591ee?pvs=21), 7359992921019471 (https://www.notion.so/7359992921019471-afb8ac71ffbc4cddb299a10f7d581c28?pvs=21), 7359992894563926 (https://www.notion.so/7359992894563926-2e3a1d8f95598009b02ac99cea114b3d?pvs=21) |  |  | Done | PVC |  | Tak: 912x450W LONGi LR4-72HPH-450M Fasade: 90x360W LONGi LR4-60HPB-360M |  | Not interested | 24.02: ok | Installed | Kjetil |  |  |  |  | 186.361 | 2,138,099
In operation (COD) | Hvittingfossveien 117, 3085 Holmestrand |  | 138 | 2024-07-23 | 2024-10-23 | 2024-07-23 | 2024-08-21 | 2024-10-23 | 126.26 | Transferred | 🟨 92 days | 92 | 🟩 29 days | 29 | 🟨 63 days | 63 | 🟩 188 days | 188 | 🟩 96 days | 96 | 0.14 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Oct | 2408 | 0 | 444.867021276596 | 0.444867021277 | 🟥 SUM! | 103.5332 | 103,533.2 | 2024 - Q4 | 2024 - Q3 | 2024 - Q2 | 0 | 3,156.5 |  |  | 0 | 0 | 988.035 | ⌚ 525 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | -11.74 | 126.26 | 83.635 | 0.662402977982 | 83.635 | 0 | 0 | 83.635 | 0.662402977982 | 7.159673913043 | 0 | 0 | 0.08 | 83.635 | 0.99 | 127.558 | 0 | 🟩 NoCs: 0 | 0.9 | 0 | 0.99 | 0 | 7.162996990337 | 0.662402977982 | 904.4 | 6.553623188406 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.13 | 0 | 43.923 | 0 | 7.825399968319 | 0 | 904.4 |  |  |  | Kvalifiserer ikke. Allerede fått støtte for lignende tiltak. |  | NTE | thing_43b9d8de-47fd-58d1-ae25-5d26af62e4c7 (https://www.notion.so/thing_43b9d8de-47fd-58d1-ae25-5d26af62e4c7-91da3f3b5cad4014a02477ffc8f8941c?pvs=21) | Done |  | Hvittingfossveien 117 |  |  | Does not qualify | 315 | Millermorland AS (https://www.notion.so/Millermorland-AS-1a8a1d8f955980af9ee4cc1e65a801e4?pvs=21) | Yes - all PPAs | 3085 | Holmestrand | Signed |  | Hvittingfossveien 117 AS (https://www.notion.so/Hvittingfossveien-117-AS-1a7a1d8f955980879936d6c14afdc2a8?pvs=21) | Ole Bjørn | 230 V | Solar as a Service | 103.24 | 2024-04-18 |  | Tilkomst via bakkeplan med fastmontert stige på fasaden. Stigen er låst, men man finner nøkkel til stigen i en nøkkelboks ved siden av stigen. Koden er 3805 | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Anders Skogen (https://www.notion.so/Anders-Skogen-1a5a1d8f955980c8a013e1c763a8f701?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | GoO priced in APA |  | 2025-01-31 | Done | LEDE | Done | Completed |  | Default | 2x Solis-50K-LV-5G | Generating (Over Volt Derating) (https://www.notion.so/Generating-Over-Volt-Derating-207a1d8f95598029a8fefb3c42b20e83?pvs=21), DC-cables needs protection (https://www.notion.so/DC-cables-needs-protection-279a1d8f95598082b4e6da3ccaa6d2cc?pvs=21) | Roof OK | Yes | 11.06: Ikke søknadspliktig. | Approved | 7359992904977583 (https://www.notion.so/7359992904977583-129a1d8f955980d99be5ea040795985c?pvs=21), 7359992936306252 (https://www.notion.so/7359992936306252-129a1d8f955980a18508ed8bd178f297?pvs=21), 7359992935185308 (https://www.notion.so/7359992935185308-152a1d8f95598069bb32ef28b27d16b8?pvs=21) |  |  | Not relevant | PVC |  | 214x590W LONGi LR5-72HTH-590 | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 68 | 836.4
In operation (COD) | Kanalvegen 12, 4033 Stavanger |  | 191.4 | 2024-04-30 | 2024-09-17 | 2024-04-30 | 2024-06-24 | 2024-09-17 | 191.4 | N/A | 🟨 140 days | 140 | 🟨 55 days | 55 | 🟨 85 days | 85 | 🟩 140 days | 140 | 🟩 0 days | 0 | 0.19 | 0 | 🟩 All good | 103.1 | ❌ End date missing | ❌ Missing | 2026-09-24 | 2406 | 0 | 1,806.542857142857 | 1.806542857143 | 🟥 SUM! | 157.5222 | 157,522.2 | 2024 - Q3 | 2024 - Q2 | 2024 - Q2 | 0 | 19.14 | 19,733.34 | 19,733.34 | 0 | 0 | 1,337,886 | ⌚ 561 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0 | 191.4 | 252.916 | 1.321400208986 | 252.916 | 0 | 0 | 252.916 | 1.321400208986 | 6.99 | 0 | 0 | 0.25 | 252.916 | 1.34 | 252.916 | 0 | 🟩 NoCs: 0 | 2026-08-01 | 0 | 1.34 | 0 | 5.668599791014 | 1.321400208986 | 1,084,970 | 5.668599791014 | 0 | 0 | 0 | 0 | 0 | 2026-08-01 | 0.19 | 0 | 0 | 0 | 6.99 | 0 | 1,084,970 | [5 empty] | Premium | thing_c97c15ac-9582-52e6-96a7-bdcaa9faca2f (https://www.notion.so/thing_c97c15ac-9582-52e6-96a7-bdcaa9faca2f-83f569d02d9645a4a19384689522e4ca?pvs=21) | Done |  | Kanalvegen 12 |  |  |  | 360A | Km Eiendom Holding AS (https://www.notion.so/Km-Eiendom-Holding-AS-1a8a1d8f955980aeb768d381f53f7f5f?pvs=21) | Not relevant | 4033 | Stavanger | Signed |  | Km Eiendom Stavanger AS (https://www.notion.so/Km-Eiendom-Stavanger-AS-246a1d8f955980f0a97dc1bc2891cc4d?pvs=21) | Jonas | 400 V | Project Sales | 191.4 | 2024-04-30 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rasmus Svebestad (https://www.notion.so/Rasmus-Svebestad-1a5a1d8f9559803d892ee708d78dd434?pvs=21) | Uploaded FDV |  |  | Not relevant |  |  | Done | LNETT | Done | Completed |  |  | 1x Solis 110K-5G-PRO, 1x Solis S5-GC40K | Inv 2: Grid Over Frequency (https://www.notion.so/Inv-2-Grid-Over-Frequency-10ca1d8f95598070aaf4ee697f56bbdf?pvs=21), Big inverter difference (https://www.notion.so/Big-inverter-difference-13ea1d8f955980e8a86fffe500a11119?pvs=21), Too high temperature in AC-cable/-fuse (https://www.notion.so/Too-high-temperature-in-AC-cable-fuse-1ffa1d8f9559807c8cf6d93ce54acfec?pvs=21) | Roof OK | No |  | Approved | 7359992922188145 (https://www.notion.so/7359992922188145-11aa1d8f955980559777c12b058ad8f8?pvs=21) |  | Received | Not relevant | Asfalt (skal tekkes om) | 2024 (tekkes om i mai) | 330x580W Tongwei TWMND-72HD | Done | In operation |  | Installed | Kjetil |  |  |  |  | 120 | 964.97
In operation (COD) | Stokkamyrveien 11, 4313 Sandnes |  | 492.88 | 2025-08-29 | 2025-11-18 | 2025-08-29 | 2025-10-08 | 2025-11-18 | 492.88 | Transferred | 🟨 81 days | 81 | 🟩 40 days | 40 | 🟩 41 days | 41 | 🟩 91 days | 91 | 🟩 10 days | 10 | 0.49 | 21.947 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 2026-11-25 | 2510 | 857,322.2 | 9,421.12087912088 | 9.421120879121 | 🟩 OK! | 406.6407864 | 406,640.7864 | 2025 - Q4 | 2025 - Q3 | 2025 - Q3 | 19,492.2 | 12.322 | 12.322 | 1,026.833333333333 | 859.777 | 3,458,777 | 3,458,777 | ⌚ 134 days | 19,492.2 | 859.777 | 857,322.2 | 19.492 | 3,458,777 | 859.777 | 859.777 | 0 | 859.777 | 3,458,777 | 2025 | 2025 | 0 | 492.88 | 859.777 | 1.744394173024 | 857.322 | 19,492.2 | 19,492.2 | 476.923 | 0.967624979711 | 6.240713763999 | 0 | 0 | 0.86 | 859.777 | 3.46 | 837.83 | 21.947 | 🟩 NoCs: 0 | 2026-06-02 | 0.771788264892 | 3.46 | 19,492.2 | 5.273088784288 | 1.739413244603 | 2,599,000 | 5.273088784288 | 19,492.2 | 0 | 0 | 19,492.2 | 0 | 2026-06-02 | 0.49 | 0 | 0 | 0 | 7.017482957312 | 0 | 2,599,000 | 2024-10-15 | Deployment/Stokkamyrveien_11_-_Energieffektivisering_med_solcelleanlegg.pdf | 6.95 |  | 10% | NTE | thing_2e8e6b0b-6f16-56b3-87f0-0cd5d295ba09 (https://www.notion.so/thing_2e8e6b0b-6f16-56b3-87f0-0cd5d295ba09-287a1d8f955980d1af6be24b03725e51?pvs=21) |  | 194.922 | Stokkamyrveien 11 | DNF | Yes | Payment received | 240A oppgradert til 400A | Oro Eiendom AS (https://www.notion.so/Oro-Eiendom-AS-1a7a1d8f9559808ab717e86d2a8f3c16?pvs=21) | Yes - all PPAs | 4313 | Sandnes | Signed | https://drive.google.com/file/d/1xiIOUQDndSRku2ta-55D7k5AUjyZbDFN/view | Forus Handel Invest AS (https://www.notion.so/Forus-Handel-Invest-AS-1a7a1d8f95598003b5c8e2ea86924a43?pvs=21) | Jonas | 400 V | Solar as a Service | 496.48 | 2025-08-19 |  |  | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Applied |  | GoO priced in APA | Not relevant |  | Done | LNETT | Done | Completed |  | Default | 2x125kW Sungrow, 1x50kW Sungrow |  | Roof OK | Yes | PBE OK | Approved | 7359992936894780 (https://www.notion.so/7359992936894780-2a7a1d8f9559800d92a6e30ef7a03f1d?pvs=21), 7359992909599124 (https://www.notion.so/7359992909599124-2bfa1d8f955980b1bf67f8ec57d9bbd1?pvs=21), 7359992922176210 (https://www.notion.so/7359992922176210-2bfa1d8f9559804f8af8f2d9d81f7956?pvs=21) |  |  | Not relevant | PVC | 2024 | 976x505W Runergy bifacial glass/glass | Done | Planned | 02.05.25: oppført i grunnbok (etter tinglysning på Stokkamyrveien 5 som er samme gårds- og bruksnummer. Sjekket med Hovland at det er ok). | Installed | Kjetil |  |  |  |  | 0 | 2,599,000
In operation (COD) | Hålandsvegen 27, 4344 Bryne |  | 110.2 | 2024-08-29 | 2025-01-13 | 2024-08-29 | 2024-11-01 | 2025-01-13 | 110.2 | Transferred | 🟨 137 days | 137 | 🟥 64 days | 64 | 🟨 73 days | 73 | 🟨 223 days | 223 | 🟩 86 days | 86 | 0.11 | 0 | 🟩 All good |  | 🟩 1516 days left | 💚 All good | 2026-01-25 | 2411 | 304.089 | 1,363.627802690583 | 1.363627802691 | 🟩 OK! | 94.3312 | 94,331.2 | 2025 - Q1 | 2024 - Q3 | 2024 - Q2 | 0 | 2.755 |  |  | 304.089 | 901.533 | 901.533 | ⌚ 443 days | 0 | 304.089 | 304.089 | 0 | 901.533 | 304.089 | 304.089 | 0 | 304.089 | 901.533 | 2025 | 2024 | 0 | 110.2 | 304.089 | 2.75942831216 | 304.089 | 0 | 0 | 304.089 | 2.75942831216 | 8.180880217786 | 0 | 0 | 0.3 | 304.089 | 0.9 | 381.862 | 0 | 🟩 NoCs: 0 | 0.6 | 0 | 0.9 | 0 | 5.421451905626 | 2.75942831216 | 597.444 | 5.421451905626 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.11 | 0 | 77.773 | 0 | 8.180880217786 | 0 | 597.444 |  |  |  | 08.08: Enighet om at vi ikke søker. |  | NTE | thing_6307ef62-7d24-5d1c-95c6-d633821719a7 (https://www.notion.so/thing_6307ef62-7d24-5d1c-95c6-d633821719a7-62a3964de85f487eb3de21a137ba87ef?pvs=21) | Done |  | Hålandsvegen 27 |  | No | Does not qualify | 400A | Bris Næringseiendom AS (https://www.notion.so/Bris-N-ringseiendom-AS-1a8a1d8f9559803bbabbdfe6b01ca4fe?pvs=21) | Yes - all PPAs | 4344 | Bryne | Signed |  | Bryne Plast AS (https://www.notion.so/Bryne-Plast-AS-1a7a1d8f955980bca9a3d617bf39e05e?pvs=21) | Ole Bjørn | 400 V | Solar as a Service | 108 | 2024-06-04 |  | Ingen tilkomst | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Rasmus Svebestad (https://www.notion.so/Rasmus-Svebestad-1a5a1d8f9559803d892ee708d78dd434?pvs=21) | Uploaded FDV | Approved | 2030-05-27 | GoO priced in APA |  | 2025-05-27 | Done | LNETT | Done | Completed |  | Default | 1x Sungrow SG110CX |  | Roof OK | Yes | Fått godkjent unntak til søknadsplikt | Approved | 7359992927582245 (https://www.notion.so/7359992927582245-173a1d8f95598003926bd30ff2605058?pvs=21), 7359992905735403 (https://www.notion.so/7359992905735403-18aa1d8f95598081a079d34c5463e246?pvs=21), 7359992922247248 (https://www.notion.so/7359992922247248-18aa1d8f955980ddac1ae165bc1b1652?pvs=21) |  |  | Not relevant | Nylig lagt duk fra Protan mai/juni 2024! | 2024 | 190x580W Tongwei TWMND-72HD | Done | Not interested | 10.03.26: fått i retur fordi selve takleieavtalen ikke er i original. Prøver å sende inn på nytt og håper på en annen saksbehandler 29.01.26: sendt til kartverket. Kommentar: om den kommer i retur er det mulig vi trenger samtykke fra bank. 24.07: Trenger original kopi (kun fått et eksemplar). Skal til Thommesen 29.01.26. Sladdet avtale ligger klar. Siri 26.03: purret på Geir 07.02: Geir Vier og Svein (som også må signere) møtes fysisk først om 4-6 uker. De signerer da og sender til oss per post. | Installed | Kjetil |  |  |  |  | 60 | 537.444
In operation (COD) | Sjøvegen 16, 7790 Malm |  | 2,307.86 | 2024-08-29 | 2025-02-25 | 2024-08-29 | 2024-09-10 | 2025-02-25 | 2,214.73 | Transferred | 🟥 180 days | 180 | 🟩 12 days | 12 | 🟥 168 days | 168 | 🟨 231 days | 231 | 🟩 51 days | 51 | 2.31 | 0 | 🟩 All good |  | ❌ End date missing | 💚 All good | 2026-02-25 | 2409 | 277,905.40000000014 | 12,030.536796536797 | 12.030536796537 | 🟩 OK! | 1,552.52573 | 1,552,525.73 | 2025 - Q1 | 2024 - Q3 | 2024 - Q3 | 137,652.80000000013 | 55,368.25 |  |  | 140,252.6 | 1,555,495.5 | 15,554,955 | ⌚ 400 days | 137,652.80000000013 | 140,252.6 | 277,905.40000000014 | 1,726,204 | 1,555,496 | -12,596,933 | -12,596,933.5 | 0 | 1,402,526 | 1,555,495.5 | 2025 | 2024 | -93.13 | 2,214.73 | 1,402,526 | 0.633271775792 | 2,779,054 | 1,376,528.0000000014 | 1,376,528.0000000014 | 2,155,623 | 0.973311870973 | 7.022978863536 | 0 | 0 | 2026-04-01 | 1,402,526 | 15.55 | 2,779,054 | 0 | 🟨 NoCs: 1 | 14.15 | 0.281493003662 | 15.55 | 1,726,204 | 6.390137398238 | 1.254804874635 | 14,052,429 | 6.088943436777 | 0 | 1,726,204 | 0 | 1,726,204 | 0 | 14.15 | 2.21 | 1,376,528 | 0 | 0 | 7.02340917403 | 100 | 14,152,429 | 2024-08-06 | Deployment/SalMar_Tjuin_-__Energieffektivisering_med_solcelleanlegg.pdf |  | Søknad sendt 06.08.24 | 53.949163011341% | NTE | thing_1ac95ac1-2630-5971-bcfe-fa40f48ca7f5 (https://www.notion.so/thing_1ac95ac1-2630-5971-bcfe-fa40f48ca7f5-154a1d8f955980d7abb7d5ce9d31ea23?pvs=21), thing_960709af-f13f-583d-b685-a0c05e6a1819 (https://www.notion.so/thing_960709af-f13f-583d-b685-a0c05e6a1819-196a1d8f955980c18a0ef4ac5998f7fe?pvs=21) | Done | 2,551,528 | Sjøvegen 16 | Sondre Dahlen Lund (NorConsult) / Endre Jarl Hansen | Yes | Payment received | 4000A | Salmar Settefisk AS (https://www.notion.so/Salmar-Settefisk-AS-1a7a1d8f9559809a9bc7c3b055599ca1?pvs=21) | Yes - all PPAs | 7790 | Malm | Signed |  |  | Johan | 400 V | Solar as a Service | 2,172.9 | 2024-07-09 | Bård Valberg (https://www.notion.so/B-rd-Valberg-1a5a1d8f9559801190beebf0190706a2?pvs=21), Vegard Heistad (https://www.notion.so/Vegard-Heistad-1bca1d8f955980638c2cdedd3438676e?pvs=21) | Permanent på hovedbygg og på sidebygg. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | To be applied |  | Retrofit - GoO earnout | Retrofit not completed |  | Not started | TENSIO TN | Done | Completed |  | Default | 12x Sungrow SG125CX 1x Sungrow SG50CX | Electric Arc Fault (https://www.notion.so/Electric-Arc-Fault-1baa1d8f95598057b790e8cf1c92a839?pvs=21), Excess Leakage Current (https://www.notion.so/Excess-Leakage-Current-1baa1d8f9559804fb2abcad6dca0c12f?pvs=21), Defect inverters (https://www.notion.so/Defect-inverters-1baa1d8f95598009ab31d5e9481be23d?pvs=21) | Roof OK | Retrofit | 03.07.2025: Søknad om ferdigattest sendt til PBE. | Approved | 6970631405222777 (https://www.notion.so/6970631405222777-1a8a1d8f9559801baac4de861890c139?pvs=21), 6970631405222784 (https://www.notion.so/6970631405222784-1caa1d8f95598024a830ef9f73507f77?pvs=21), 6970631405222791 (https://www.notion.so/6970631405222791-1caa1d8f9559808a8293c799301219a4?pvs=21) |  |  | To be started | Bitumen (asfaltpapp) | 2023 | Tak: 3628x580W Tongwei TWMND-72HD Topcon Bifacial Fasade: 254x435W LONGi LR5-54 HTB | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 1,789,206 | 12,263,223
In operation (COD) | Strømsveien 258, 0668 Oslo |  | 50 |  |  |  |  | 2019-06-25 | 50 | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ ERROR / Check Date | -190 | 🟥 2282 days (ongoing) | 2282 | 0.05 | 0 | 🟧 Est. FID missing | 51.55 | ❌ End date missing | ❌ Missing | 19 - Jun |  | 0 |  | 0 | 🟥 SUM! | 39.05 | 39.05 | 2019 - Q2 |  | 2020 - Q1 | 0 | 2.5 | 2,577.5 | 2,577.5 | 0 | 0 |  | ⌚ 2472 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 2020 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Premium | thing_4fe09323-9d70-57e4-a904-55c928b31875 (https://www.notion.so/thing_4fe09323-9d70-57e4-a904-55c928b31875-2f2583f1d27c407887e0cebf3dd40c99?pvs=21) | Done |  | Strømsveien 258 |  |  |  |  | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) |  | 668 | Oslo | Signed |  |  | Not set |  | SaaS | 50 | 2020-01-01 |  |  |  |  | N/A |  |  | Not relevant |  |  | Done | ELVIA | No status | Completed |  |  | Solis | Wrong consumption meter in SundayOS (https://www.notion.so/Wrong-consumption-meter-in-SundayOS-208a1d8f95598030a122ee5c5dee7cc6?pvs=21) | Roof OK | No |  | Not applicable | 7359992903065014 (https://www.notion.so/7359992903065014-93ae86ad4c26423caa1e804ac365007a?pvs=21) |  |  | Not relevant | [6 empty] | Installed | Alex |  |  |  |  | 0 | 0
In operation (COD) | Larkollveien 4, 1570 Dilling |  | 1,037.38 | 2024-07-16 | 2024-12-13 | 2024-07-16 | 2024-10-07 | 2024-12-13 | 1,037.38 | Transferred | 🟨 150 days | 150 | 🟥 83 days | 83 | 🟨 67 days | 67 | 🟩 176 days | 176 | 🟩 26 days | 26 | 2026-04-01 | 0 | 🟩 All good |  | 🟩 1386 days left | 💚 All good | 24 - Dec | 2410 | 0 | 8,346.551136363636 | 8.346551136364 | 🟥 SUM! | 905.217788 | 905,217.788 | 2024 - Q4 | 2024 - Q3 | 2024 - Q2 | 0 | 25,934.5 |  |  | 0 | 0 | 6,937,090 | ⌚ 474 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0 | 1,037.38 | 1,468,993 | 1.416060652798 | 1,468,993 | 0 | 0 | 1,468,993 | 1.416060652798 | 7.089520715649 | 0 | 0 | 1.47 | 1,468,993 | 6.94 | 1,825,766 | 0 | 🟨 NoCs: 1 | 5.47 | 0 | 6.94 | 0 | 5.271064605063 | 1.416060652798 | 5,885,534 | 5.673460062851 | 0 | 0 | 0 | 0 | 356.773 | 5.47 | 2026-04-01 | 0 | 0 | 356.773 | 6.687125257861 | -417.437 | 5,468,097 | [5 empty] | NTE | thing_37984e3c-6eaf-5644-b06c-e028975bfe05 (https://www.notion.so/thing_37984e3c-6eaf-5644-b06c-e028975bfe05-bf8e5e1a892a4560a1b84c8442841a4b?pvs=21) | In progress |  | Larkollveien 4 |  |  |  | 1600A | Bonum Gruppen AS (https://www.notion.so/Bonum-Gruppen-AS-1a6a1d8f955980359c1bd99f34198fb1?pvs=21) | Yes - all PPAs | 1570 | Dilling | Signed |  | Larkollveien 4 AS (https://www.notion.so/Larkollveien-4-AS-1a7a1d8f9559809cb038dc20ebaebe81?pvs=21) | Jonas | 400 V | Solar as a Service | 1.029 | 2024-06-20 |  | Tilkomst via innsiden av bygget og fastmontert stige på fasaden på nordsiden. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Branko Culjak (https://www.notion.so/Branko-Culjak-1a5a1d8f95598026b553fc108d980ae0?pvs=21) | Uploaded FDV | Approved | 2030-01-17 | GoO priced in APA |  | 2025-01-17 | Done | ELVIA | Done | Completed |  | Default | 6x Solis 110K-5G-PRO | Defect inverter (Warning AC SPD ERROR) (https://www.notion.so/Defect-inverter-Warning-AC-SPD-ERROR-1aea1d8f955980f6ba59d086eff50007?pvs=21), No production from SundayBox (https://www.notion.so/No-production-from-SundayBox-1eca1d8f9559808f8e59da2ca5c8be2a?pvs=21), SundayBox down (https://www.notion.so/SundayBox-down-208a1d8f95598070a221ce92968a8da1?pvs=21), No communication with INV5 and INV6 (https://www.notion.so/No-communication-with-INV5-and-INV6-268a1d8f95598012a3c3f3daa2bcbe66?pvs=21) | Roof OK | No | Gårdeier har søkt og fått godkjent rammetillatelse. | Approved | 37976805 (https://www.notion.so/37976805-176a1d8f95598057959dd76ba7edb1f1?pvs=21), 37976804 (https://www.notion.so/37976804-176a1d8f9559809783a4f9d7480499c7?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 1497x580W LONGi LR5-72 HTD 396x430W LONGi LR5-54HTB-430M | Done | Not interested | 27.01.26: prøver å sende på nytt med ny “mal” for erklæring og endret til Sunday Gen. 24.07: prøver å sende på nytt. 03.06.25: mangler, kan ikke tinglyses 28.04: sendt Siri følger opp: 09.04: mottatt samtykke fra PWM. 27.01 Forespurt Bonum om samtykke for urådighet fra Nordea (Private II Wealth Management SCA-SIF) Samtykke fra DNB er mottatt og ligger på sak. Original erklæring ligger på pulten til Siri 04.03: purret angående urådighet 25.03: urådighet sendes i kopi på epost (avtalt med Mats) slik at vi kommer raskere i mål. | Installed | Kjetil |  |  |  |  | 598.188 | 5,287,346
In operation (COD) | Høgdaveien 1, 1543 Vestby |  | 251.85 | 2024-06-26 | 2024-10-21 | 2024-06-26 | 2024-09-24 | 2024-10-21 | 252.88 | N/A | 🟨 117 days | 117 | 🟥 90 days | 90 | 🟩 27 days | 27 | 🟩 122 days | 122 | 🟩 5 days | 5 | 0.25 | 0 | 🟩 All good | 100 | ❌ End date missing | ❌ Missing | 24 - Oct | 2409 | 0 | 1,861.844262295082 | 1.861844262295 | 🟥 SUM! | 208.626 | 208.626 | 2024 - Q4 | 2024 - Q2 | 2024 - Q2 | 0 | 25.288 | 25.288 | 29,502.666666666668 | 0 | 0 | 1,583,000 | ⌚ 527 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 2026-03-01 | 252.88 | 227.145 | 0.898232363176 | 227.145 | 0 | 0 | 227.145 | 0.898232363176 | 6.28548739329 | 0 | 0 | 0.23 | 227.145 | 1.58 | 227.145 | 0 | 🟩 NoCs: 0 | 1.36 | 0 | 1.58 | 0 | 5.361653748814 | 0.898232363176 | 1,355,855 | 5.383581496923 | 0 | 0 | 0 | 0 | 0 | 1.36 | 0.25 | 0 | 0 | 0 | 6.25988611199 | 0 | 1,355,855 | [5 empty] | Premium | thing_a00591f2-f565-522e-a7fd-e2e6253922a1 (https://www.notion.so/thing_a00591f2-f565-522e-a7fd-e2e6253922a1-bfeaa71b1a7741fa8962e8db9ecba494?pvs=21) | Not started | 377.237 | Høgdaveien 1 |  |  | Applied by client - closed | 1100A | Daimyo AS (https://www.notion.so/Daimyo-AS-1a5a1d8f955980e5bf65d626085f168f?pvs=21) | Not relevant | 1543 | Vestby | Signed |  |  | Rikard | 400 V | Project Sales | 251.85 | 2024-06-21 |  | Tilkomst til taket via spiraltrapp på sørsiden av bygget. | Ecosol AS (https://www.notion.so/Ecosol-AS-1aba1d8f95598094847fc6a923fd88b4?pvs=21) | Tormod Engesæth (https://www.notion.so/Tormod-Enges-th-1a5a1d8f95598010addac6474e46ce10?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | NORGESNETT | Done | Completed |  |  | 2x Solis-110K-5G-PRO |  | Roof OK | No |  | Approved | 7359992906139118 (https://www.notion.so/7359992906139118-130a1d8f955980feb921c2a55880408c?pvs=21) |  |  | Not relevant | PVC | 2024 | 436x580W LONGi Hi-MO 7 LR5-72HGD 580M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 0 | 1,355,855
In operation (COD) | Kolonivegen 43, 2072 Dal |  | 135.72 | 2024-07-02 | 2024-09-11 | 2024-07-02 | 2024-08-02 | 2024-09-11 | 136.89 | N/A | 🟨 71 days | 71 | 🟩 31 days | 31 | 🟩 40 days | 40 | 🟩 78 days | 78 | 🟩 7 days | 7 | 0.14 | 0 | 🟩 All good | 41.24 | ❌ End date missing | ❌ Missing | 2026-09-24 | 2408 | 0 | 334.435897435897 | 0.334435897436 | 🟥 SUM! | 107.45865 | 107,458.65 | 2024 - Q3 | 2024 - Q3 | 2024 - Q2 | 0 | 5,475.6 | 5,645.3436 | 5,645.3436 | 0 | 0 | 944.541 | ⌚ 567 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 1.17 | 136.89 | 26.086 | 0.190561764921 | 26.086 | 0 | 0 | 26.086 | 0.190561764921 | 6.959482758621 | 0 | 0 | 0.03 | 26.086 | 0.94 | 26.086 | 0 | 🟩 NoCs: 0 | 0.92 | 0 | 0.94 | 0 | 6.709438235079 | 0.190561764921 | 918.455 | 6.767278219864 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0.14 | 0 | 0 | 0 | 2026-09-06 | 0 | 918.455 | [5 empty] | Smart | thing_c41977fb-edef-52e4-baa5-6015a846b3f6 (https://www.notion.so/thing_c41977fb-edef-52e4-baa5-6015a846b3f6-cd97e9630cf542d89da98a7c01430cd0?pvs=21) | Done |  | Kolonivegen 43 |  |  |  | 3000A | Leto Eiendom AS (https://www.notion.so/Leto-Eiendom-AS-1a8a1d8f955980679cdcdef69a253aef?pvs=21) | Not relevant | 2072 | Dal | Signed |  | Leto Eiendom AS (https://www.notion.so/Leto-Eiendom-AS-1a8a1d8f955980679cdcdef69a253aef?pvs=21) | Ole Bjørn | 230 V | Project Sales | 134.55 | 2024-06-25 |  | To bygg her. Det ene har tilkomst fra bakkeplan til taket via spiraltrapp og det andre har tilkomst til taket via stige utendørs i andre etasje (må gå inn via bygget). | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Viktor Lavik (https://www.notion.so/Viktor-Lavik-1a5a1d8f955980ae9254d0dd69d2fe1b?pvs=21), Siri Ørewall (https://www.notion.so/Siri-rewall-1a5a1d8f95598060b317ea989f1d26ed?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 1x Solis S5-GC60K-LV, 1x Solis S5-GC-50K-LV |  | Roof OK | No |  | Approved | 7359992895554985 (https://www.notion.so/7359992895554985-11aa1d8f955980ae9e98def9d18bf055?pvs=21) |  | Received | Not relevant | Asfaltpapp og PVC |  | 234x585W TW Solar TWMND-72HD | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 159 | 759.455
In operation (COD) | Myhrersvingen 12, 2080 Eidsvoll |  | 155.44 | 2024-07-02 | 2024-10-11 | 2024-07-02 | 2024-09-04 | 2024-10-11 | 156.78 | N/A | 🟨 101 days | 101 | 🟥 64 days | 64 | 🟩 37 days | 37 | 🟩 108 days | 108 | 🟩 7 days | 7 | 0.16 | 0 | 🟩 All good | 41.24 | ❌ End date missing | ❌ Missing | 24 - Oct | 2409 | 0 | 834.287037037037 | 0.834287037037 | 🟥 SUM! | 121.97484 | 121,974.84 | 2024 - Q4 | 2024 - Q3 | 2024 - Q2 | 0 | 6,271.2 | 6,465.6072 | 6,465.6072 | 0 | 0 | 1,018,440 | ⌚ 537 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 1.34 | 156.78 | 90.103 | 0.574709784411 | 90.103 | 0 | 0 | 90.103 | 0.574709784411 | 6.551981471951 | 0 | 0 | 0.09 | 90.103 | 2026-02-01 | 90.103 | 0 | 🟩 NoCs: 0 | 0.93 | 0 | 2026-02-01 | 0 | 5.921271845899 | 0.574709784411 | 928.337 | 5.972317292846 | 0 | 0 | 0 | 0 | 0 | 0.93 | 0.16 | 0 | 0 | 0 | 6.49598163031 | 0 | 928.337 | [5 empty] | Smart | thing_af600ec1-a23e-563c-9eeb-814c739e98ab (https://www.notion.so/thing_af600ec1-a23e-563c-9eeb-814c739e98ab-5d61f2118f92435380280f40dae42bf3?pvs=21) | Done |  | Myhrersvingen 12 |  |  |  | 600A | Leto Eiendom AS (https://www.notion.so/Leto-Eiendom-AS-1a8a1d8f955980679cdcdef69a253aef?pvs=21) | Not relevant | 2080 | Eidsvoll | Signed |  |  | Ole Bjørn | 230 V | Project Sales | 155.25 | 2024-06-25 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Viktor Lavik (https://www.notion.so/Viktor-Lavik-1a5a1d8f955980ae9254d0dd69d2fe1b?pvs=21), Siri Ørewall (https://www.notion.so/Siri-rewall-1a5a1d8f95598060b317ea989f1d26ed?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 2x Solis S5-GC60K-LV | Grid No Grid (https://www.notion.so/Grid-No-Grid-237a1d8f9559804f9d9cf6a463c2ac13?pvs=21) | Roof OK | No |  | Approved | 7359992895571982 (https://www.notion.so/7359992895571982-11aa1d8f95598019a913cb08ab131553?pvs=21) |  | Received | Not relevant | PVC |  | 268x585W TW TWMND-72HD | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 120 | 808.337
In operation (COD) | Stasjonsvegen 26-30, 2100 Skarnes |  | 501 | 2024-08-26 | 2024-12-19 | 2024-08-26 | 2024-10-03 | 2024-12-19 | 502.715 | Transferred | 🟨 115 days | 115 | 🟩 38 days | 38 | 🟨 77 days | 77 | 🟩 164 days | 164 | 🟩 49 days | 49 | 0.5 | 15.337 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Dec | 2410 | -15.337 | 1,960.762195121951 | 1.960762195122 | 🟥 SUM! | 400.663855 | 400,663.855 | 2024 - Q4 | 2024 - Q3 | 2024 - Q3 | 0 | 12,567.875 |  |  | 0 | 0 | 2,884,914 | ⌚ 468 days | 0 | 0 | -15.337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 1.715 | 502.715 | 336.902 | 0.670165004028 | 321.565 | 0 | 0 | 336.901 | 0.670163014829 | 6.113760479042 | 0 | 0 | 0.34 | 336.902 | 2.88 | 454.757 | 15.337 | 🟨 NoCs: 1 | 2.55 | -0.030506350516 | 2.88 | 0 | 5.068502033956 | 0.639656664313 | 2,726,093 | 5.441303393214 | 0 | 0 | 0 | 0 | 0 | 2.55 | 0.5 | 0 | 133.192 | 0 | 5.738667037984 | -178.081 | 2,548,012 |  |  |  | 2022 Enova-ordning. Buyback case. |  | NTE | thing_21b18013-cedb-5eb6-9fe1-5dc2c901f808 (https://www.notion.so/thing_21b18013-cedb-5eb6-9fe1-5dc2c901f808-63fbceb498f347df927371fe837e99a3?pvs=21) | In progress |  | Stasjonsvegen 26-30 |  |  |  | 3200A | Parken Kjøpesenter AS (https://www.notion.so/Parken-Kj-pesenter-AS-1a7a1d8f955980e88169dd38f9625f49?pvs=21) | Yes - all PPAs | 2100 | Skarnes | Signed |  | Parken Kjøpesenter AS (https://www.notion.so/Parken-Kj-pesenter-AS-1a7a1d8f955980e88169dd38f9625f49?pvs=21) | Ole Bjørn | 230 V | Solar as a Service | 497 | 2024-07-08 |  |  | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | GoO priced in APA |  | 2025-01-31 | Done | ELVIA | Done | Completed |  | Default | 6x Solis 60K-LV |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 7359992922209185 (https://www.notion.so/7359992922209185-161a1d8f955980d3858ed158bf0c84bb?pvs=21), 7359992895844338 (https://www.notion.so/7359992895844338-17da1d8f9559804793a9fb9a7649f760?pvs=21) |  |  | Not relevant | Asfaltpapp | 2023/2024 | 545x580W LONGi LR5-72HTH-580M 319x585W LONGi LR5-72HTH-585M | Done | Not interested | 10.03: ok | Installed | Kjetil |  |  |  |  | 0 | 2,726,093
In operation (COD) | Stokkamyrveien 5, 4313 Sandnes |  | 412.08 | 2025-01-15 | 2025-04-03 | 2025-01-15 | 2025-03-02 | 2025-04-03 | 412.08 | Transferred | 🟨 78 days | 78 | 🟨 46 days | 46 | 🟩 32 days | 32 | 🟥 314 days | 314 | 🟨 236 days | 236 | 0.41 | 11.266 | 🟩 All good |  | 🟩 1516 days left | 💚 All good | 2026-04-25 | 2503 | 395,580.6 | 1,259.808917197452 | 1.259808917197 | 🟩 OK! | 334.19688 | 334,196.88 | 2025 - Q2 | 2025 - Q1 | 2024 - Q2 | 59,925.6 | 10.302 |  |  | 346.921 | 2,645,921 | 2,645,921 | ⌚ 363 days | 59,925.6 | 346.921 | 395,580.6 | 0 | 2,645,921 | 346.921 | 346.921 | 0 | 346.921 | 2,645,921 | 2025 | 2024 | 0 | 412.08 | 346.921 | 0.84187779072 | 395.58 | 59,925.6 | 59,925.6 | 429 | 1.041059988352 | 6.620073772083 | 0 | 0 | 0.35 | 346.921 | 2.65 | 395.581 | 11.266 | 🟩 NoCs: 0 | 2026-03-02 | -0.081100757135 | 2.65 | 0 | 5.579013783731 | 0.959959231217 | 2,299,000 | 5.579013783731 | 0 | 0 | 0 | 0 | 0 | 2026-03-02 | 0.41 | 59.926 | 0 | 0 | 6.420891574452 | 0 | 2,299,000 | 2024-05-24 | Deployment/Stokkamyrveien_5_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  | 10% | NTE | thing_2ad918bd-7e9b-5d4c-9c8d-cee7735aa614 (https://www.notion.so/thing_2ad918bd-7e9b-5d4c-9c8d-cee7735aa614-1a4a1d8f95598074b502d24919c450e6?pvs=21) | N/A | 599.256 | Stokkamyrveien 5 | DNF | Yes | Payment received | 200A | Oro Eiendom AS (https://www.notion.so/Oro-Eiendom-AS-1a7a1d8f9559808ab717e86d2a8f3c16?pvs=21) | Yes - all PPAs | 4313 | Sandnes | Signed | https://drive.google.com/file/d/1OOZCadbt5fbGbWa_-4CsEwGTuo8IWCLJ/view | Oro Stokkamyrveien 5-11 AS (https://www.notion.so/Oro-Stokkamyrveien-5-11-AS-2fba1d8f9559809fa443fe614389e4ee?pvs=21) | Jonas | 400 V | Solar as a Service | 380.48 | 2024-05-24 |  | Fastmontert stige langs fasaden. NB! Ifølge forvalter og leietaker, så er den noe gammel og slitt denne stigen. | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved | 2030-05-27 | GoO priced in APA |  | 2025-05-27 | Done | LNETT | Done | Completed |  | Default | 2x Sungrow 125 kW 1x Sungrow 50 kW |  | Roof OK | Yes | PBE OK | Approved | 7359992891283711 (https://www.notion.so/7359992891283711-11aa1d8f9559803fb81edaa58ad9cf15?pvs=21), 7359992939276927 (https://www.notion.so/7359992939276927-1c0a1d8f955980f6aeecf968ce69c5a0?pvs=21) |  |  | Not relevant | PVC | 2024 | 816x505W Runergy | Done | Not interested | 02.05.25: oppført i grunnbok Siri: sendt 28.04 Kjetil: 26.03 etterspurt signatur (egen takleieavtale i orden for Stokkamyrveien 5). | Installed | Kjetil |  |  |  |  | 332 | 1,967,000
In operation (COD) | Almedalsveien 6, 1391 Vollen |  | 102.38 | 2025-04-24 | 2025-06-27 | 2025-04-24 | 2025-05-21 | 2025-06-27 | 101.85 | Transferred | 🟨 64 days | 64 | 🟩 27 days | 27 | 🟩 37 days | 37 | 🟥 367 days | 367 | 🟥 303 days | 303 | 0.1 | 28.015 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Jun | 2505 | 20.604 | 56.141689373297 | 0.056141689373 | 🟩 OK! | 83.396817 | 83,396.817 | 2025 - Q2 | 2025 - Q2 | 2024 - Q2 | 0 | 2,546.25 | 2,546.25 | 1,273.125 | 48.619 | 657.238 | 657.238 | ⌚ 278 days | 0 | 48.619 | 20.604 | 49.996 | 657.238 | 48.619 | 48.619 | 0 | 48.619 | 657.238 | 2025 | 2024 | -0.53 | 101.85 | 48.619 | 0.47735886107 | 20.604 | 4.996 | 0 | 52.039 | 0.510937653412 | 6.452998632545 | 0 | 0 | 0.05 | 48.619 | 0.66 | 20.604 | 28.015 | 🟩 NoCs: 0 | 0.61 | -0.308640157094 | 0.66 | 49.996 | 5.975640648012 | 0.202297496318 | 608.619 | 5.944705997265 | 4.996 | 45 | 0 | 49.996 | 0 | 0.61 | 0.1 | 0 | 0 | 0 | 6.452999509082 | 0 | 608.619 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_og_tetting___lekkasjetest_til_Almedalsveien_6.pdf | 7 |  | 20% | NTE | thing_8b3f9861-463d-527e-a261-91245a48a7c9 (https://www.notion.so/thing_8b3f9861-463d-527e-a261-91245a48a7c9-209a1d8f9559800f95a8cac0d46a43e9?pvs=21) |  | 24.98 | Almedalsveien 6 |  | No | Cancelled | Maxbo: 710A E-motive: 250A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 1391 | Vollen | Signed | https://drive.google.com/file/d/1I1fn5cYLmv6GiHm8wKENuUwUmjSAW7Wx/view |  | Rikard | 230 V | Solar as a Service | 280 | 2024-06-25 |  | Må ha lift | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21), Leif-Erik Josefesen (https://www.notion.so/Leif-Erik-Josefesen-1a5a1d8f95598003b525f9d6f73786d5?pvs=21) | Uploaded FDV | Approved |  | Retrofit - GoO earnout | Retrofit not completed | 2025-09-17 | Done | ELVIA | Done | Completed |  | Default | 1x Solis 60K-LV-230V | No production data registered on meter (https://www.notion.so/No-production-data-registered-on-meter-249a1d8f955980bfac9bfbb1b876aac5?pvs=21) | Roof OK | Retrofit | 15.08.25: Ferdigattest godkjent | Approved | 7359992908006388 (https://www.notion.so/7359992908006388-11aa1d8f955980fd96d7d3f52681f588?pvs=21), 7359992906187935 (https://www.notion.so/7359992906187935-1e0a1d8f955980fc9f58ddc48a3a4457?pvs=21), 7359992906169795 (https://www.notion.so/7359992906169795-1e0a1d8f955980528c21d0fbc6d887c4?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | To be started | Asfaltpapp | Skal legges nytt tak | 194x525W JA solar JAM60D42 LB | Done | Not interested | Erklæring + samtykke klar på drive. Trenger samtykke fra SPAREBANK 1 SØR-NORGE ASA, org nr. 937 895 321 | To be installed | Kjetil |  |  |  |  | 47.5 | 561.119
In operation (COD) | Snipetjernveien 9, 1405 Langhus |  | 1,107.23 | 2025-07-08 | 2026-01-12 | 2025-07-08 | 2025-08-20 | 2026-01-12 | 1,107.23 | Transferred | 🟥 188 days | 188 | 🟨 43 days | 43 | 🟥 145 days | 145 | 🟨 257 days | 257 | 🟩 69 days | 69 | 2026-11-01 | 49.86 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 2026-01-26 | 2508 | 652,513.5 | 2,842.626459143969 | 2.842626459144 | 🟩 OK! | 904.1086565 | 904,108.6565 | 2026 - Q1 | 2025 - Q3 | 2025 - Q2 | 402,233.4 | 27,680.75 | 27,680.75 | 0 | 300,140.1 | 5,901,480 | 6,557,200 | ⌚ 79 days | 402,233.4 | 300,140.1 | 652,513.5 | 0 | 5,901,480 | -322.231 | -322.231 | 73,055.5 | 333.489 | 5,901,480 | 2026 | 2025 | 0 | 1,107.23 | 333.489 | 0.30119216423 | 730.555 | 446.926 | 446.926 | -6,068,296 | -5.480610171328 | 0 | 0 | 0 | 0.33 | 333.489 | 6.56 | 730.555 | 49.86 | 🟥 NoCs: 3 | 6.22 | 6.140414367385 | 6.56 | 0 | 5.620973962049 | 0.659804196057 | 6,068,296 | 5.480610171328 | 0 | 0 | 0 | 0 | 0 | 6.22 | 2026-11-01 | 446.926 | 0 | 0 | 5.922166126279 | 155.415 | 6,223,711 | 2025-03-21 | Deployment/Tilskuddsbrev-4.pdf |  |  | 100% | NTE | thing_1d397796-616e-5db7-bc3a-3c138fdd3088 (https://www.notion.so/thing_1d397796-616e-5db7-bc3a-3c138fdd3088-292a1d8f955980f9a56be028ab88b20c?pvs=21) | Not started | 446.926 | Snipetjernveien 9 | Malling & Co Energi og Miljø AS v/ Herman | Yes | Application: Successful | 1600A | Bulk Industrial Real Estate AS (https://www.notion.so/Bulk-Industrial-Real-Estate-AS-1a8a1d8f9559805ca7cbd0938f7b649d?pvs=21) | No | 1405 | Langhus |  | https://drive.google.com/file/d/1yzooVCYwONkp4A_8qmHxEOvQvKP1E-LF/view |  | Jonas | 400 V | Solar as a Service | 1,093.25 | 2025-04-30 | Marjan Radovic (https://www.notion.so/Marjan-Radovic-2e8a1d8f95598034a937ea87c5a7f8dc?pvs=21) |  | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | Uploaded FDV | Applied |  | GoO priced in APA | Retrofit not completed |  | Done | NORGESNETT | Planned | Completed |  | Default | 6x 125 kW INVT XG125KTR-PRO-NE (snow melting) 1x 60 kW INVT XG60KTR (for BIPV) |  | Roof OK | Yes | Ikke søknadspliktig. | Approved | 5706567269878808 (https://www.notion.so/5706567269878808-2fca1d8f95598030a0f3c277874d52b1?pvs=21) | Norconsult AS (https://www.notion.so/Norconsult-AS-22aa1d8f955980318108df778e1c40bb?pvs=21) | Received | Not relevant | PVC | 2003 | 1750x575W LONGi (roof) 198x510W LONGi (BIPV) | Done | Not started |  | Installed | Kjetil |  |  |  |  | 515 | 5,553,296
In operation (COD) | Årvollskogen 65, 1529 Moss |  | 320.16 | 2024-09-11 | 2024-12-17 | 2024-09-11 | 2024-11-05 | 2024-12-17 | 320.46 | N/A | 🟨 97 days | 97 | 🟨 55 days | 55 | 🟩 42 days | 42 | 🟩 105 days | 105 | 🟩 8 days | 8 | 0.32 | 0 | 🟩 All good | 100 | ❌ End date missing | ❌ Missing | 24 - Dec | 2411 | 0 | 1,737.980952380953 | 1.737980952381 | 🟥 SUM! | 278.8002 | 278,800.2 | 2024 - Q4 | 2024 - Q3 | 2024 - Q3 | 0 | 32.046 | 32.046 | 29,375.499999999996 | 0 | 0 | 2,017,008 | ⌚ 470 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0.3 | 320.46 | 182.488 | 0.569456406416 | 182.488 | 0 | 0 | 182.488 | 0.569456406416 | 2026-03-06 | 0 | 0 | 0.18 | 182.488 | 2026-02-02 | 182.488 | 0 | 🟩 NoCs: 0 | 1.83 | 0 | 2026-02-02 | 0 | 5.724645821631 | 0.569456406416 | 1,834,520 | 5.730009995002 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0.32 | 0 | 0 | 0 | 6.294102228047 | 0 | 1,834,520 | [5 empty] | Premium | thing_cbf68e1e-e3ff-511d-8d6d-9dc9eb5e3613 (https://www.notion.so/thing_cbf68e1e-e3ff-511d-8d6d-9dc9eb5e3613-14ca1d8f95598050aa26f0623027a173?pvs=21) | Done |  | Årvollskogen 65 |  |  | Unsuccessful application | 500A | Portal Eiendom AS (https://www.notion.so/Portal-Eiendom-AS-1a5a1d8f955980eb9e33d6bbd059f04b?pvs=21) | Not relevant | 1529 | Moss | Signed |  |  | Ole Bjørn | 230 V | Project Sales | 320 | 2024-09-03 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Espen Gangfløt (https://www.notion.so/Espen-Gangfl-t-1a5a1d8f9559807d9f25feda52575f13?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Not started | ELVIA | Done | Completed |  |  | 3x Solis 60K-LV-5G 1x S5-GC-36K-LV |  | Roof OK | No |  | Approved | 7359992905004288 (https://www.notion.so/7359992905004288-161a1d8f9559803ba802f47432c9d7c6?pvs=21), 7359992902746365 (https://www.notion.so/7359992902746365-183a1d8f9559805d9cf8c754a223f051?pvs=21) |  |  | Not relevant | Asfaltpapp | 2024 | 588x545W Sunova SS-BG545-72MDH | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 198.5 | 1,636,020
In operation (COD) | Deliveien 6, 1540 Vestby |  | 1,118.24 | 2024-09-10 | 2024-12-02 | 2024-09-10 | 2024-10-21 | 2024-12-02 | 1,115.92 | N/A | 🟨 83 days | 83 | 🟨 41 days | 41 | 🟩 42 days | 42 | 🟩 87 days | 87 | 🟩 4 days | 4 | 2026-12-01 | 1.44 | 🟩 All good | 70 | ❌ End date missing | ❌ Missing | 24 - Dec | 2410 | -1.44 | 845.51724137931 | 0.845517241379 | 🟥 SUM! | 916.17032 | 916,170.32 | 2024 - Q4 | 2024 - Q3 | 2024 - Q3 | 0 | 78,114.4 | 78,114.4 | 78,114.4 | 0 | 0 | 5,890,000 | ⌚ 485 days | 0 | 0 | -1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | -2.32 | 1,115.92 | 75 | 0.067209118933 | 73.56 | 0 | 0 | 75 | 0.067209118933 | 5.267205608814 | 0 | 0 | 0.08 | 75 | 5.89 | 73.56 | 1.44 | 🟩 NoCs: 0 | 5.82 | -0.001290415083 | 5.89 | 0 | 5.210947021292 | 0.065918703850 | 5,815,000 | 5.200135927887 | 0 | 0 | 0 | 0 | 0 | 5.82 | 2026-12-01 | 0 | 0 | 0 | 5.278156140225 | 0 | 5,815,000 | [5 empty] | Premium | thing_1271e9a7-7674-5b18-a022-4af79ef615ad (https://www.notion.so/thing_1271e9a7-7674-5b18-a022-4af79ef615ad-13da1d8f9559807dacb1d3ca7759e32c?pvs=21) | Done |  | Deliveien 6 |  |  |  | 1200A | Propcap AS (https://www.notion.so/Propcap-AS-1a8a1d8f955980e0a7c4d287d88049bf?pvs=21) | Not relevant | 1540 | Vestby | Signed |  |  | Ole Bjørn | 400 V | Project Sales | 1,118.24 | 2024-09-06 | Ole Petter Ervik (https://www.notion.so/Ole-Petter-Ervik-1a5a1d8f955980a98ea6eb7ec975005d?pvs=21) | Spiraltrall + fastmontert stige med ryggsøyle opp til taket fra bakkeplan. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 4x Growatt MAX 125KTL3-X LV 2x Growatt MAX 120KTL3-X LV | Not Specified & unknown fault code (https://www.notion.so/Not-Specified-unknown-fault-code-1caa1d8f955980e58c39e84609c64610?pvs=21) | Roof OK | No |  | Approved | 7359992907395322 (https://www.notion.so/7359992907395322-158a1d8f95598027993dd4056148b9b5?pvs=21), 7359992907397456 (https://www.notion.so/7359992907397456-1d2a1d8f955980619c0df19834d89671?pvs=21), 7359992907400538 (https://www.notion.so/7359992907400538-1d2a1d8f955980f18e40ede3d044df7a?pvs=21) |  |  | Not relevant | Asfaltpapp - Tekkes om nå! | 2024 | 1924x580W PhonoSolar | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 715 | 5,100,000
In operation (COD) | Storgata 38, 2390 Moelv |  | 257.6 | 2025-04-10 | 2025-07-03 | 2025-04-10 | 2025-05-21 | 2025-07-03 | 251.85 | Transferred | 🟨 84 days | 84 | 🟨 41 days | 41 | 🟩 43 days | 43 | 🟨 281 days | 281 | 🟩 197 days | 197 | 0.26 | 12.437 | 🟩 All good |  | ❌ End date missing | 💚 All good | 25 - Jul | 2505 | -36.84 | -131.103202846975 | -0.131103202847 | 🟩 OK! | 192.891915 | 192,891.915 | 2025 - Q3 | 2025 - Q2 | 2024 - Q3 | 0 | 6,296.25 |  |  | -24.403 | 1,352,171 | 1,352,171 | ⌚ 272 days | 0 | -24.403 | -36.84 | 145.262 | 1,352,171 | -24.403 | -24.403 | 0 | -24.403 | 1,352,171 | 2025 | 2024 | -5.75 | 251.85 | -24.403 | -0.096894977169 | -36.84 | 0 | 0 | 174.582 | 0.693198332341 | 6.021568322981 | 0 | 0 | -0.02 | -24.403 | 1.35 | -36.84 | 12.437 | 🟩 NoCs: 0 | 1.38 | -0.839475878499 | 1.35 | 145.262 | 5.465848719476 | -0.146277546158 | 1,376,574 | 5.343843167702 | 0 | 145.262 | 0 | 145.262 | 0 | 1.38 | 0.25 | 0 | 0 | 0 | 5.368953742307 | 0 | 1,376,574 | [5 empty] | NTE | thing_3479274a-c6e3-5e6b-8828-332837bc7f2b (https://www.notion.so/thing_3479274a-c6e3-5e6b-8828-332837bc7f2b-20aa1d8f955980e1a77ac7c01f5412c2?pvs=21) |  |  | Storgata 38 |  |  |  | 1250A (underfordeling på ca. 800A) | Dukat Eiendom AS (https://www.notion.so/Dukat-Eiendom-AS-1a8a1d8f955980328efff616c947b4aa?pvs=21) | Yes - all PPAs | 2390 | Moelv | Signed | https://drive.google.com/file/d/1ExrRn-Lf2wgUc5f94oh4xVdbLXtJdNnO/view | Ri Eiendomsinvest AS (https://www.notion.so/Ri-Eiendomsinvest-AS-311a1d8f955980de9cc9c919d5ea638d?pvs=21) | Rikard | 400 V | Solar as a Service | 260 | 2024-09-25 | Ådne Bergum (https://www.notion.so/dne-Bergum-1a5a1d8f955980289a7ad046c7d58755?pvs=21) | Tilkomst fra bakkeplan med fastmontert stige. Låst med hengelås | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Siri Ørewall (https://www.notion.so/Siri-rewall-1a5a1d8f95598060b317ea989f1d26ed?pvs=21) | Uploaded FDV | Approved |  | Retrofit - GoO earnout | Retrofit not completed | 2025-09-17 | Done | ELVIA | Done | Completed |  | Default | 4x Sungrow SG50CX-P2 |  | Roof OK | Retrofit | 03.07.25: Søknad om ferdigmelding sendt. | Approved | 7359992892875960 (https://www.notion.so/7359992892875960-11aa1d8f9559805f8edde156d2a87e5b?pvs=21) |  |  | Not relevant |  | 2024 | 438x575W LONGi LR5 72HDTR | Done | In operation | 02.02.26: bedt om signerte erklæringer og sendt samtykke fra bank til byggeier. Sendt samtykke til banken. | Installed | Kjetil |  |  |  |  | 180.764 | 1,195,810
In operation (COD) | Industrivegen 55, 2212 Kongsvinger |  | 253.7 | 2024-10-10 | 2024-12-03 | 2024-10-10 | 2024-10-28 | 2024-12-03 | 253.52 | Transferred | 🟩 54 days | 54 | 🟩 18 days | 18 | 🟩 36 days | 36 | 🟩 55 days | 55 | 🟩 1 days | 1 | 0.25 | 0 | 🟩 All good |  | 🟩 1400 days left | 💚 All good | 24 - Dec | 2410 | 0 | 2,140.727272727273 | 2.140727272727 | 🟥 SUM! | 200.2808 | 200,280.8 | 2024 - Q4 | 2024 - Q4 | 2024 - Q4 | 0 | 6.338 |  |  | 0 | 0 | 1,150,660 | ⌚ 484 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | -0.18 | 253.52 | 117.74 | 0.464420952982 | 117.74 | 0 | 0 | 468.25 | 1.846994319975 | 7.630626724478 | 0 | 0 | 0.12 | 117.74 | 1.15 | 540.247 | 0 | 🟨 NoCs: 1 | 2026-03-01 | -1.382573366993 | 1.15 | 0 | 4.074313663616 | 0.464420952982 | 1,467,640 | 5.784942845881 | 0 | 0 | 0 | 0 | 422.507 | 2026-03-01 | 0.25 | 0 | 0 | 422.507 | 4.538734616598 | -434.72 | 1,032,920 | [5 empty] | NTE | thing_d4465ade-c302-5147-afa3-cac478c74831 (https://www.notion.so/thing_d4465ade-c302-5147-afa3-cac478c74831-13da1d8f955980f4b87fc595eaeffd79?pvs=21) | Done |  | Industrivegen 55 |  |  |  | 1250A | Expo Property AS (https://www.notion.so/Expo-Property-AS-1a8a1d8f955980fa8f4dfb5c93f95a42?pvs=21) | Yes - all PPAs | 2212 | Kongsvinger | Signed |  | Kongsvinger Eiendomsinvest AS (https://www.notion.so/Kongsvinger-Eiendomsinvest-AS-311a1d8f9559807899b5e09322bb0706?pvs=21) | Rikard | 400 V | Solar as a Service | 253.7 | 2024-10-09 | Hans Inge Thomsen (https://www.notion.so/Hans-Inge-Thomsen-1a5a1d8f955980c5825ed7efbe483906?pvs=21) | Via innsiden av bygget. | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21) | Uploaded FDV | Approved | 2030-01-31 | GoO priced in APA | Not relevant | 2025-01-31 | Done | ELVIA | Done | Completed |  | Default | 2x Solis 110 kW | Lost Elhub access (https://www.notion.so/Lost-Elhub-access-229a1d8f955980fb9a1eed553b517412?pvs=21) | Roof OK | Yes | Ikke søknadspliktig. | Approved | 7359992901842204 (https://www.notion.so/7359992901842204-162a1d8f955980319e7ae946ddf12713?pvs=21), 7359992901842785 (https://www.notion.so/7359992901842785-1faa1d8f9559804f98eecfa02c5905fd?pvs=21) |  |  | Not relevant | PVC |  | 394x590W LONGi LR5-72HTH-590M, 36x585W LONGi LR5-72HTH-585M | Done | Not started | Tinglyst 27.08.2025 | Installed | Kjetil |  |  |  |  | 125 | 1,342,640
In operation (COD) | Skytterheia 3, 4790 Lillesand |  | 338.35 | 2024-12-12 | 2025-03-05 | 2024-12-12 | 2025-02-10 | 2025-03-05 | 338.35 | Transferred | 🟨 83 days | 83 | 🟨 60 days | 60 | 🟩 23 days | 23 | 🟩 135 days | 135 | 🟩 52 days | 52 | 0.34 | 7.561 | 🟩 All good |  | 🟩 1516 days left | 💚 All good | 25 - Mar | 2502 | 618.653 | 4,582.614814814815 | 4.582614814815 | 🟩 OK! | 299.1014 | 299,101.4 | 2025 - Q1 | 2024 - Q4 | 2024 - Q4 | 104.342 | 8,458.75 |  |  | 521.872 | 2,320,872 | 2,320,872 | ⌚ 392 days | 104.342 | 521.872 | 618.653 | 0 | 2,320,872 | 521.872 | 521.872 | 0 | 521.872 | 2,320,872 | 2025 | 2024 | 0 | 338.35 | 521.872 | 1.542402837299 | 618.653 | 104.342 | 104.342 | 521.872 | 1.542402837299 | 6.859382296439 | 0 | 0 | 0.52 | 521.872 | 2.32 | 618.653 | 7.561 | 🟩 NoCs: 0 | 2026-08-01 | 0.2860381262 | 2.32 | 0 | 5.31697945914 | 1.828440963499 | 1,799,000 | 5.31697945914 | 0 | 0 | 0 | 0 | 0 | 2026-08-01 | 0.34 | 104.342 | 0 | 0 | 6.859382296439 | 0 | 1,799,000 | 2024-10-15 | Deployment/Skytterheia_3_-_Energieffektivisering_med_solcelleanlegg.pdf | 2026-05-05 |  | 50% | NTE | thing_2958bec3-2e42-5d75-8597-84764f932ba0 (https://www.notion.so/thing_2958bec3-2e42-5d75-8597-84764f932ba0-1a4a1d8f95598000a086fe26139dabbf?pvs=21) | Done | 208.684 | Skytterheia 3 | Marianne @ Løyning | Yes | Payment received | 315A | HR Eiendom AS (https://www.notion.so/HR-Eiendom-AS-1a8a1d8f955980e2adfdde90c66ee1b2?pvs=21) | Yes - all PPAs | 4790 | Lillesand | Signed |  | Agderbyen 2 AS (https://www.notion.so/Agderbyen-2-AS-311a1d8f955980e78bdec159252b70d0?pvs=21) | Johan | 400 V | Solar as a Service | 345.68 | 2024-10-21 | Thomas Regin Tednes (https://www.notion.so/Thomas-Regin-Tednes-1a5a1d8f955980eb8bc5cc5dc9a067d6?pvs=21) | Stige fra terasse | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved | 2030-05-27 | GoO priced in APA | Not relevant | 2025-05-27 | Not started | GLITRE | Done | Completed |  | Default | 2x Sungrow TN-nett 3-fas 125 kW | No production inverter 2 (https://www.notion.so/No-production-inverter-2-1b5a1d8f95598093bb91f51dd71a4e9d?pvs=21), SP meter not installed correctly (https://www.notion.so/SP-meter-not-installed-correctly-1eda1d8f9559803eaee8d8d8e336137a?pvs=21) | Roof OK | Yes |  | Approved | 5706567346177510 (https://www.notion.so/5706567346177510-1e0a1d8f955980c8ac5ae0da81002ac0?pvs=21), 5706567303418502 (https://www.notion.so/5706567303418502-1e0a1d8f955980b0a97aec3fb3f7c103?pvs=21) |  |  | Not relevant | Papp (Icopal Mono). Har fått eget databla fra kunde, se Drive. | 2020 | 670x505W Runergy bifacial glass/glass | Done | Not started |  | To be installed | Siri |  |  |  |  | 180 | 1,619,000
In operation (COD) | Industriparkveien 35, 7246 Sandstad |  | 371.2 | 2025-02-05 | 2025-10-26 | 2025-02-05 | 2025-04-14 | 2025-10-26 | 368.88 | Transferred | 🟥 263 days | 263 | 🟥 68 days | 68 | 🟥 195 days | 195 | 🟨 299 days | 299 | 🟩 36 days | 36 | 0.37 | 19.723 | 🟩 All good |  | 🟩 1790 days left | 💚 All good | 25 - Oct | 2504 | 304.587 | 1,018.685618729097 | 1.018685618729 | 🟩 OK! | 247.6770984 | 247,677.0984 | 2025 - Q4 | 2025 - Q1 | 2024 - Q4 | 95.48 | 9.222 |  |  | 228.83 | 2,214,750 | 2,214,750 | ⌚ 157 days | 95.48 | 228.83 | 304.587 | 0 | 2,214,750 | 228.83 | 228.83 | 0 | 228.83 | 2,214,750 | 2025 | 2024 | -2.32 | 368.88 | 228.83 | 0.620337237042 | 304.587 | 95.48 | 95.48 | 921.041 | 2.496858056821 | 7.831252693966 | 0 | 0 | 0.23 | 228.83 | 2.21 | 304.587 | 19.723 | 🟩 NoCs: 0 | 1.99 | -1.671150509651 | 2.21 | 0 | 5.383647798742 | 0.82570754717 | 1,985,920 | 5.35 | 0 | 0 | 0 | 0 | 0 | 1.99 | 0.37 | 95.48 | 0 | 0 | 6.003985035784 | 0 | 1,985,920 | 2024-10-15 |  | 5.95 |  | 100% | NTE | thing_05b2ff04-e94c-5f8a-a859-cdbce22a7df2 (https://www.notion.so/thing_05b2ff04-e94c-5f8a-a859-cdbce22a7df2-1c2a1d8f95598014b16febfa177e5ea7?pvs=21) |  | 95.48 | Industriparkveien 35 |  | Yes | Payment received | 2784A | Logistea AS (https://www.notion.so/Logistea-AS-1a8a1d8f955980458a0ef7caf1e1a0fa?pvs=21) | Yes - all PPAs | 7246 | Sandstad | Signed | https://drive.google.com/file/d/1PaFqN6mU2ieoNb1ajbGtZKG7FjQGn8Tv/view | Logistea Hitra AS (https://www.notion.so/Logistea-Hitra-AS-311a1d8f955980079887d627bb98114a?pvs=21) | Johan | 400 V | Solar as a Service | 371.2 | 2024-12-31 | Ole Petter Ervik (https://www.notion.so/Ole-Petter-Ervik-1a5a1d8f955980a98ea6eb7ec975005d?pvs=21) | Fastmontert stige på fasaden med ryggbøyle. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | In progress | TENSIO TS | Done | Completed |  | Default | 2x Growatt 125kW |  | Roof OK | Yes |  | Approved | 6970631409398218 (https://www.notion.so/6970631409398218-1bda1d8f9559804eb383ec89ad39e3cf?pvs=21), 6970631402846822 (https://www.notion.so/6970631402846822-1bda1d8f9559805da77ff831243c157d?pvs=21), 6970631402846754 (https://www.notion.so/6970631402846754-1bda1d8f955980269691d0e096e3cd17?pvs=21), 6970631407708880 (https://www.notion.so/6970631407708880-2aea1d8f955980ab8f4af81b0f0b64cd?pvs=21) |  | Received | Not relevant |  | 2023 | 636x580W PhonoSolar Premium glass-glass | Done | In operation |  | Installed | Kjetil |  |  |  |  | 190 | 1,795,920
In operation (COD) | Selbuvegen 715, 7584 Selbustrand |  | 371.2 | 2024-10-31 | 2025-09-23 | 2024-10-31 | 2025-02-03 | 2025-09-23 | 371.2 | Transferred | 🟥 327 days | 327 | 🟥 95 days | 95 | 🟥 232 days | 232 | 🟥 349 days | 349 | 🟩 22 days | 22 | 0.37 | 29.272 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-09-25 | 2502 | 440.576 | 1,262.39541547278 | 1.262395415473 | 🟩 OK! | 249.0752 | 249,075.2 | 2025 - Q3 | 2024 - Q4 | 2024 - Q4 | 0 | 9.28 | 9.28 | 2.32 | 469.848 | 2,569,848 | 2,569,848 | ⌚ 190 days | 0 | 469.848 | 440.576 | 0 | 2,569,848 | 469.848 | 469.848 | 0 | 469.848 | 2,569,848 | 2025 | 2024 | 0 | 371.2 | 469.848 | 1.265754310345 | 440.576 | 0 | 0 | 469.848 | 1.265754310345 | 6.923081896552 | 0 | 0 | 0.47 | 469.848 | 2.57 | 440.576 | 29.272 | 🟩 NoCs: 0 | 2026-01-02 | -0.078857758621 | 2.57 | 0 | 5.657327586207 | 1.186896551724 | 2,100,000 | 5.657327586207 | 0 | 0 | 0 | 0 | 0 | 2026-01-02 | 0.37 | 0 | 0 | 0 | 6.923081896552 | 0 | 2,100,000 |  | Deployment/Selbuvegen_715_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  |  | NTE | thing_3b8f3750-40ad-5561-b617-a0340466f625 (https://www.notion.so/thing_3b8f3750-40ad-5561-b617-a0340466f625-1b3a1d8f955980cc89c5d3eb32b52f8b?pvs=21) | Done |  | Selbuvegen 715 |  | Yes |  | 2500A | Sifa AS (https://www.notion.so/Sifa-AS-1a7a1d8f955980b5ae24f5dc3bd417bc?pvs=21) | Yes - all PPAs | 7584 | Selbustrand | Signed |  | Selbu Næringsselskap Kf (https://www.notion.so/Selbu-N-ringsselskap-Kf-311a1d8f95598077975cea6d0405a550?pvs=21) | Ole Bjørn | 400 V | Solar as a Service | 371.2 | 2024-10-09 | Ole Petter Ervik (https://www.notion.so/Ole-Petter-Ervik-1a5a1d8f955980a98ea6eb7ec975005d?pvs=21) | Fastmontert stige med ryggsøyle fra bakkeplan, men innenfor port til området. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | Done | TENSIO TS | Done | Completed |  | Default | 2x Growatt MAX 125 kW |  | Roof OK | Yes | Ikke søknadspliktig. | Approved | 6970631408833994 (https://www.notion.so/6970631408833994-27da1d8f95598088ac1eee39f78718a9?pvs=21), 6970631405216042 (https://www.notion.so/6970631405216042-27da1d8f95598012a343db60703b30f4?pvs=21) |  | Received | Not relevant | PVC | Ny hall: 2022 Gammel hall: 2019 | 640x580W PhonoSolar | Done | In operation | 28.02.26: sent til Kartverket med samtykker 27.01.26: sendt samtykker for Sifa og Selbu kommune til Arnt i Sifa. Styremøte i morgen så han mener det skal gå fort. 24.07: trenger samtykke fra kommunen. Innhenter parallelt som vi prøver å sende inn på nytt. 03.06.25: mangler, kan ikke tinglyses. Trenger samtykke fra Selbu kommune. Verdt å prøve å sende inn på nytt mens vi innhenter. Siri: sendt 28.04 Kjetil har etterspurt signatur. Kunde har sagt signatur er på vei | Installed | Kjetil |  |  |  |  | 189 | 1,911,000
In operation (COD) | Lindebergveien 10, 2016 Frogner |  | 420.16 | 2024-11-19 | 2024-12-09 | 2024-11-19 | 2024-11-25 | 2024-12-09 | 420.16 | Transferred | 🟩 20 days | 20 | 🟩 6 days | 6 | 🟩 14 days | 14 | 🟩 60 days | 60 | 🟩 40 days | 40 | 0.42 | 8.21 | 🟩 All good |  | 🟩 1386 days left | 💚 All good | 24 - Dec | 2411 | -8.21 | 6,372.883333333333 | 6.372883333333 | 🟥 SUM! | 326.88448 | 326,884.48 | 2024 - Q4 | 2024 - Q4 | 2024 - Q4 | 0 | 10.504 |  |  | 0 | 0 | 2,549,033 | ⌚ 478 days | 0 | 0 | -8.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0 | 420.16 | 280.033 | 0.666491336634 | 382.373 | 110.55 | 110.55 | 280.033 | 0.666491336634 | 6.066815022848 | 0 | 0 | 0.28 | 280.033 | 2.55 | 382.373 | 8.21 | 🟩 NoCs: 0 | 2.27 | 0.243573876618 | 2.55 | 0 | 5.400323686215 | 0.910065213252 | 2,269,000 | 5.400323686215 | 0 | 172.671 | 0 | 172.671 | 0 | 2.27 | 0.42 | 110.55 | 0 | 0 | 6.066815022848 | 0 | 2,269,000 | 2024-10-15 | Deployment/Lindebergveien_10_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  | 50% | NTE | thing_6a9e69ba-0bc0-5f4a-a013-313ba2ebc2f5 (https://www.notion.so/thing_6a9e69ba-0bc0-5f4a-a013-313ba2ebc2f5-14ca1d8f955980cf922ed7c9f7e8d475?pvs=21) | Done | 221.1 | Lindebergveien 10 |  |  | Payment received | 1250A | Hero Eiendom AS (https://www.notion.so/Hero-Eiendom-AS-2f1a1d8f955980f784bccc6a062456b6?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  | Lindebergveien 10 AS (https://www.notion.so/Lindebergveien-10-AS-2cca1d8f9559806eb54cfe5df3789ebf?pvs=21) | Ole Bjørn | 400 V | Solar as a Service | 402 | 2024-10-10 | Anders Skarstein (https://www.notion.so/Anders-Skarstein-1a5a1d8f955980dba84efbe2baa22926?pvs=21), Morten Muri (https://www.notion.so/Morten-Muri-1a4a1d8f955980eea2edd1f8ab28bd6b?pvs=21) | Spiraltrapp fra bakkeplan og nesten helt opp. Siste delen må man ha stige til. Det finnes stige på innsiden av døren. Nøkkel til dør er til venstre for hovedinngangen med kodelås 5714 | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved | 2030-01-17 | Retrofit - GoO earnout | Retrofit not completed | 2025-01-17 | Done | ELVIA | Done | Completed |  | Default | 2x 125 kW Sungrow 1x 40 kW Sungrow | INV2: Alarm run: PV Reserve Connection Alarm + Fault: PV Reserve Connection Fault (https://www.notion.so/INV2-Alarm-run-PV-Reserve-Connection-Alarm-Fault-PV-Reserve-Connection-Fault-1aea1d8f955980dc81b2cf95a2296961?pvs=21), Inverter cap at 269kW (https://www.notion.so/Inverter-cap-at-269kW-207a1d8f955980619c04fcfd6f36bc08?pvs=21) | Roof OK | Retrofit |  | Approved | 7359992894584334 (https://www.notion.so/7359992894584334-160a1d8f95598080be21dc876a44e09b?pvs=21) |  | Received | In progress | Takpapp (god stand) | 2020 | 832x505W Runergy | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 290 | 1,979,000
In operation (COD) | Lagårdsveien 78-80, 4010 Stavanger |  | 115 |  |  |  |  | 2025-02-16 | 115 | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 107 days | 107 | 🟥 516 days (ongoing) | 516 | 0.12 | 1.92 | 🟧 Est. FID missing | 100 | ❌ End date missing | ❌ Missing | 2026-02-25 |  | -1.92 | -17.943925233645 | -0.017943925234 | 🟥 SUM! | 91.195 | 91.195 | 2025 - Q1 |  | 2024 - Q4 | 0 | 11.5 | 11.5 | 8.625 | 0 | 0 |  | ⌚ 409 days | 0 | 0 | -1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 2024 | 0 | 115 | 0 | 0 | -1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.92 | 1.92 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | -0.016695652174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Premium | thing_b7496afb-c6ef-5a32-9f97-b979656b323a (https://www.notion.so/thing_b7496afb-c6ef-5a32-9f97-b979656b323a-151a1d8f955980128eedf4885909af20?pvs=21) | Done |  | Lagårdsveien 78-80 |  |  |  |  | Niam AS (https://www.notion.so/Niam-AS-1a8a1d8f955980ab804cd460bed4c604?pvs=21) |  | 4010 | Stavanger | Signed |  |  | Not set |  | SaaS |  | 2024-11-01 |  |  |  |  | N/A |  |  | Not relevant |  |  | Not started |  | No status | Completed | [5 empty] | TBD |  | Not applicable | [7 empty] | Not relevant |  |  | To be installed | Alex |  |  |  |  | 0 | 0
In operation (COD) | Tiltaksvegen 22, 7300 Orkanger |  | 326 | 2024-12-19 | 2025-05-13 | 2024-12-19 | 2025-02-04 | 2025-05-13 | 320.11 | Transferred | 🟨 145 days | 145 | 🟨 47 days | 47 | 🟨 98 days | 98 | 🟩 186 days | 186 | 🟩 41 days | 41 | 0.33 | 64.005 | 🟩 All good |  | ❌ End date missing | 💚 All good | 25 - May | 2502 | 538.731 | 2,896.403225806452 | 2.896403225806 | 🟩 OK! | 222.47645 | 222,476.45 | 2025 - Q2 | 2024 - Q4 | 2024 - Q4 | 152.181 | 8,002.75 |  |  | 450.555 | 2,189,765 | 2,189,765 | ⌚ 323 days | 152.181 | 450.555 | 538.731 | 0 | 2,189,765 | 450.555 | 450.555 | 0 | 450.555 | 2,189,765 | 2025 | 2024 | -5.89 | 320.11 | 450.555 | 1.407500546687 | 538.731 | 152.181 | 152.181 | 490.847 | 1.533369779138 | 6.840665644172 | 0 | 0 | 0.45 | 450.555 | 2.19 | 538.731 | 64.005 | 🟩 NoCs: 0 | 1.74 | 0.149586079785 | 2.19 | 0 | 5.433163600012 | 1.682955858923 | 1,739,210 | 5.335 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0.32 | 152.181 | 0 | 0 | 6.8406641467 | 0 | 1,739,210 | 2025-01-30 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Tiltaksvegen_22.pdf |  |  | 50% | NTE | thing_104ddfdb-ca7c-5423-8388-c19a02ab42fc (https://www.notion.so/thing_104ddfdb-ca7c-5423-8388-c19a02ab42fc-1a5a1d8f95598076a579d89beccd16f1?pvs=21) | Done | 304.362 | Tiltaksvegen 22 | Christina Carboni, Rambøll | Yes | Payment received | 560A | Salvesen & Thams Eiendom AS (https://www.notion.so/Salvesen-Thams-Eiendom-AS-1a8a1d8f955980efa47cfb05b0a2c1fe?pvs=21) | Yes - all PPAs | 7300 | Orkanger | Signed |  | Salvesen & Thams Eiendom AS (https://www.notion.so/Salvesen-Thams-Eiendom-AS-1a8a1d8f955980efa47cfb05b0a2c1fe?pvs=21) | Johan | 400 V | Solar as a Service | 327.12 | 2024-11-08 |  | Innvendig trapp med stige / utgang | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21) | Uploaded FDV | Approved |  | GoO priced in APA | Not relevant | 2025-09-17 | Not started | NETTSELSKAPET AS | Done | Completed |  | Default | 2x Solis 110 W, Solis 110K-5G-PRO | Virtual sharing not correct (https://www.notion.so/Virtual-sharing-not-correct-206a1d8f95598087a553e9d66c0e193b?pvs=21), Wrong invoice setup (https://www.notion.so/Wrong-invoice-setup-217a1d8f955980328cbbd0c556d06bda?pvs=21) | Roof OK | Yes |  | Approved | 7359992939275937 (https://www.notion.so/7359992939275937-1f8a1d8f9559801fb848ec2530ac2a8d?pvs=21), 20235 (https://www.notion.so/20235-1f8a1d8f955980eaa2e8d7f6302cf147?pvs=21), 7359992932890762 (https://www.notion.so/7359992932890762-1f8a1d8f95598082bde9e0a388cccc14?pvs=21) |  |  | Not relevant | TBC | 2023 | 538x595W Longi LR7-72HGD | Done | In operation | 27.01.26: Sendt til Kartverket. 02.10: fått i retur pga hjemmel til eiendomsrett er flyttet til Orkland Handelspark. Snakket med Kartverket som krever både ny erklæring og samtykke. Har sendt begge deler til Salvesen og Thams/Orkland Handelspark som skal signere og sender til oss. | To be installed | Siri |  |  |  |  | 66 | 1,673,210
In operation (COD) | Tjøllingveien 45, 3262 Larvik |  | 387.65 | 2025-05-30 | 2025-11-14 | 2025-05-30 | 2025-08-11 | 2025-11-14 | 404.47 | Transferred | 🟥 168 days | 168 | 🟥 73 days | 73 | 🟨 95 days | 95 | 🟥 333 days | 333 | 🟩 165 days | 165 | 0.39 | 18.61 | 🟩 All good |  | ❌ End date missing | 💚 All good | 2026-11-25 | 2508 | 555.285 | 1,667.522522522523 | 1.667522522523 | 🟩 OK! | 484.8705466 | 484,870.5466 | 2025 - Q4 | 2025 - Q2 | 2024 - Q4 | 0 | 10,111.75 |  |  | 573.895 | 4,329,995 | 4,329,995 | ⌚ 138 days | 0 | 573.895 | 555.285 | 0 | 4,329,995 | 573.895 | 573.895 | 0 | 573.895 | 4,329,995 | 2025 | 2024 | 16.82 | 404.47 | 573.895 | 1.418881499246 | 555.285 | 0 | 0 | 514.746 | 1.272643212105 | 11.017273313556 | 0 | 0 | 0.57 | 573.895 | 4.33 | 555.285 | 18.61 | 🟩 NoCs: 0 | 3.76 | 0.100227458155 | 4.33 | 0 | 9.286473656884 | 1.37287067026 | 3,756,100 | 9.689410550755 | 0 | 0 | 0 | 0 | 0 | 3.76 | 0.4 | 0 | 0 | 0 | 10.70535515613 | 0 | 3,756,100 | [5 empty] | NTE | thing_416578b1-d98c-5e16-93df-d319c5b15421 (https://www.notion.so/thing_416578b1-d98c-5e16-93df-d319c5b15421-281a1d8f9559800ca507f8c3d6e324e7?pvs=21) | Done |  | Tjøllingveien 45 |  | Yes | Applied by client | 1000A | L. A. Lund AS (https://www.notion.so/L-A-Lund-AS-1a8a1d8f955980839237d19eada32d61?pvs=21) | Yes - all PPAs | 3262 | Larvik | Signed | https://drive.google.com/file/d/1jtVWZ0Alq_puXBjD38a0tjXl6zVvSO-6/view | Lund Øya AS (https://www.notion.so/Lund-ya-AS-2cda1d8f95598014aa3cd806f2a33861?pvs=21) | Ole Bjørn | 400 V | Solar as a Service | 383.58 | 2024-12-16 |  | Trapp og stige hele veien fra bakkeplan. Kodelås: 1881 | Isola Solar AS (https://www.notion.so/Isola-Solar-AS-1a7a1d8f95598048a3c5c037d15fbcdd?pvs=21) | Thomas Sørensen (https://www.notion.so/Thomas-S-rensen-1a5a1d8f95598014a5f3f7c3f1ad86fd?pvs=21) | Uploaded FDV | To be applied |  | GoO priced in APA | Not relevant |  | Done | LEDE | Done | Completed |  | Default | 4x Growatt MAX 100 KTL3-X LV |  | Roof OK | Yes | Ferdigattest OK | Approved | 7359992894585577 (https://www.notion.so/7359992894585577-201a1d8f9559804d9edffd4c2627723e?pvs=21), 7359992894592322 (https://www.notion.so/7359992894592322-201a1d8f955980f9a1c6e450e7922020?pvs=21), 7359992903262673 (https://www.notion.so/7359992903262673-20aa1d8f95598009b8e1d36a8681304a?pvs=21), 7359992898896549 (https://www.notion.so/7359992898896549-20aa1d8f955980febe8edc26b07e0d81?pvs=21), 7359992933171198 (https://www.notion.so/7359992933171198-2bca1d8f9559808b8d56ecdb45413948?pvs=21) |  | Received | Not relevant | PVC | 2025 | Tak: 420x720W Huasun HS-210-B132-DS720 Fasade: 246x415W Trina Solar VERTEX S 415W TSM-DE09R.05 | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 0 | 3,756,100
In operation (COD) | Gamle Ringeriksvei 34, 1357 Stabekk |  | 113.16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 113.16 | Transferred | 🟩 0 days | 0 | 🟩 0 days | 0 | 🟩 0 days | 0 | 🟩 0 days | 0 | 🟩 0 days | 0 | 0.11 | 0 | 🟩 All good |  | ❌ End date missing | 💚 All good | 24 - Dec | 2412 | 0 |  | 0 | 🟥 SUM! | 87.58584 | 87,585.84 | 2024 - Q4 | 2024 - Q4 | 2024 - Q4 | 0 | 2.829 |  |  | 0 | 0 | 611.679 | ⌚ 467 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0 | 113.16 | 159.679 | 1.41109049134 | 159.679 | 0 | 0 | 159.679 | 1.41109049134 | 5.405434782609 | 0 | 0 | 0.16 | 159.679 | 0.61 | 159.679 | 0 | 🟩 NoCs: 0 | 0.45 | 0 | 0.61 | 0 | 3.994344291269 | 1.41109049134 | 452 | 3.994344291269 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.11 | 0 | 0 | 0 | 5.405434782609 | 0 | 452 | [5 empty] | NTE | thing_8d6ca5ed-25b0-5bf0-b027-76acec6468a4 (https://www.notion.so/thing_8d6ca5ed-25b0-5bf0-b027-76acec6468a4-151a1d8f955980849571e6e9595e2f97?pvs=21) | In progress |  | Gamle Ringeriksvei 34 |  |  |  | 2500A | Oro Eiendom AS (https://www.notion.so/Oro-Eiendom-AS-1a7a1d8f9559808ab717e86d2a8f3c16?pvs=21) | No | 1357 | Stabekk | Signed |  | Bekkestua Senter AS (https://www.notion.so/Bekkestua-Senter-AS-311a1d8f9559805c8486d7e254ce27f2?pvs=21) | Jonas | 400 V | Solar as a Service | 113 | 2024-12-20 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) |  | Uploaded FDV | Approved |  | Retrofit - GoO earnout | Retrofit not completed | 2025-09-17 | Done | ELVIA | Done | Completed | GR34 2024 (https://www.notion.so/GR34-2024-188a1d8f955980559e1cdc192169566c?pvs=21) | Default | 1x Solis 110K-5G-PRO |  | Roof OK | Retrofit |  | Approved | 7359992899902201 (https://www.notion.so/7359992899902201-184a1d8f955980638f91c6ac27f85697?pvs=21) |  |  | To be started |  |  | 246x460W JA Solar JAM72S20-460/MR | Not relevant | Not interested | 02.02.26: må ha samtykke fra sameiet. Har sendt samtykke til sameiet og de tar det opp på styremøte 03.02. 24.07: har mangler, men sendt inn på nytt i dag. Hovland enig i at det kan gå gjennom. Siri: sendt til Kartverket 28.04 Jonas sender mail (Aleks laget uktast 27.01) til kunde og får de til å sende erklæring -› @Siri Bjørnstad Jensen følger opp og purrer på kunde ila. feks. en uke. | Installed | Kjetil |  |  |  |  | 0 | 452
On hold | Lilletuneveien 3, 3105 Sarpsborg |  | 1,304.1 | 2025-05-14 | 2026-06-30 | 2025-05-14 | 2025-06-23 |  |  | Signed APA | 🟥 322 days (ongoing) | 322 | 🟩 40 days | 40 | 🟥 282 days (ongoing) | 282 | 🟥 456 days (ongoing) | 456 | 🟩 134 days | 134 | 2026-03-01 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2506 | 92,876.94 | 1,408.826754385965 | 1.408826754386 | 🟩 OK! | 1,100.569113 | 1,100,569.113 |  | 2025 - Q2 | 2024 - Q4 | 76,738.14 | 0 |  |  | 158,782.8 | 2,277,460.5 | 7,591,535 | ❌ COD not set | 76,738.14 | 158,782.8 | 92,876.94 | 561.076 | 2,277,461 | -4,784,798 | -4,784,798.5 | 449,697.5 | 529.276 | 2,277,460.5 |  | 2024 | -1,304.1 | 1,304.1 | 529.276 | 0.405855379189 | 642.425 | 255,793.8 | 255,793.8 | 1,409,155 | 1.080557472586 | 6.495984970478 | 0 | 0 | 0 | 529.276 | 7.59 | 386.632 | 142.644 | 🟩 NoCs: 0 | 2026-06-07 | -0.587938041561 | 7.59 | 561,075.8 | 5.415427497891 | 0.492619431025 | 7,062,259 | 5.415427497891 | 255,793.8 | 0 | 305.282 | 561,075.8 | 305.282 | 2026-06-07 | 0 | 0 | 0 | 0 |  | 0 | 7,062,259 | 2025-03-21 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Lilletuneveien_3.pdf | 7 |  | 20% |  |  |  | 1,278,969 | Lilletuneveien 3 | Termoenergi |  | Progess report sent | 2000A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 3105 | Sarpsborg | Signed | https://drive.google.com/file/d/1Q7D-pHhS2ae8POpo1Iji6n5UWcrWw5cH/view | Lilletuneveien 3 AS (https://www.notion.so/Lilletuneveien-3-AS-311a1d8f95598025ac62c6893bba5ab6?pvs=21) | Rikard | 400 V | Solar as a Service | 1.364 | 2024-12-31 |  | Innsiden av bygget via Power. | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | In progress | ELVIA | No status | Completed |  |  | 8x Solis 110K-5G-PRO |  | Roof OK | No | Ikke søknadspliktig | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Asfaltpapp og PVC |  | 1908x575W Sunova 360x575W LONGi LR5-72HTDR | Done | Not interested |  | To be installed | Kjetil |  |  |  |  | 908.6 | 6,153,659
Cancelled | Varnaveien 30, 3103 Moss |  | 558 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.56 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 0 | 0 | 🟥 SUM! | 469.836 | 469.836 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 4,118,032 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | -558 | 558 | 0 | 0 | 0 | 0 | 0 | 4,118,032 | 7.379985663082 | 7.379985663082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 2026-12-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Varnaveien 30 |  |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) |  | 3103 | Moss | Signed |  | Varnaveien Handelspark AS (https://www.notion.so/Varnaveien-Handelspark-AS-311a1d8f95598086827fc5fb88048a63?pvs=21) | Rikard |  | Solar as a Service | 558 | 2024-12-31 |  |  |  |  | Not uploaded | [5 empty] | Not started |  | No status | Completed | [7 empty] | To be applied | [11 empty] | Kjetil
On hold | Smibakken 2, 6018 Ålesund |  | 1,598.8 | 2026-05-04 | 2026-08-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 2026-06-01 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -31.594 | 2,220.120614035088 | 2.220120614035 | 🟩 OK! | 1,074.15378 | 1,074,153.78 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 9,413,216 | ❌ COD not set | 0 | 0 | -31.594 | 0 | 0 | 0 | 0 | 809.9 | 0 | 0 |  | 2024 | -1,598.8 | 1,598.8 | 1,043,969 | 0.652970352765 | 1,012,375 | 0 | 0 | 1,043,969 | 0.652970352765 | 5.887675756818 | 0 | 0 | 0 | 0 | 0 | -31.594 | 31.594 | 🟩 NoCs: 0 | 8.37 | -0.019761070804 | 9.41 | 0 | 5.234705404053 | 0.633209281961 | 8,369,247 | 5.234705404053 | 0 | 0 | 0 | 0 | 0 | 8.37 | 0 | 0 | 0 | 0 |  | 0 | 8,369,247 | [9 empty] | Smibakken 2 |  | TBD | Waiting for calc | 1250A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 6018 | Ålesund | Signed |  | Breiviksenteret AS (https://www.notion.so/Breiviksenteret-AS-311a1d8f955980e4a009c183aa043b48?pvs=21) | Rikard | 400 V | Solar as a Service | 500 | 2024-12-31 |  |  | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) |  | Not uploaded | To be applied |  |  |  |  | Not started | Linja | No status | Completed |  |  | 8 x Solis 125 kW |  | Roof OK | TBD | 15.05: søknad godkjent. Har brukt Sørconsult til å søke | Approved |  | Multiconsult ASA (https://www.notion.so/Multiconsult-ASA-1a6a1d8f955980fd95b5d7a99ad7d568?pvs=21) | Received |  |  |  | 1810 x Longi 575 Wp 900 x Longi 620 Wp | No status | Not started |  |  | Siri |  |  |  |  | 600 | 7,769,247
In operation (COD) | Smibakken 10, 6018 Ålesund |  | 763.6 | 2025-07-03 | 2025-10-15 | 2025-07-03 | 2025-08-05 | 2025-10-15 | 762.45 | Transferred | 🟨 104 days | 104 | 🟩 33 days | 33 | 🟨 71 days | 71 | 🟨 288 days | 288 | 🟩 184 days | 184 | 0.76 | 27.68 | 🟩 All good |  | 🟩 1790 days left | 💚 All good | 25 - Oct | 2508 | 465.617 | 1,616.725694444444 | 1.616725694444 | 🟩 OK! | 511.985175 | 511,985.175 | 2025 - Q4 | 2025 - Q3 | 2024 - Q4 | 0 | 19,061.25 |  |  | 493.297 | 4,502,111 | 4,502,111 | ⌚ 168 days | 0 | 493.297 | 465.617 | 0 | 4,502,111 | 493.297 | 493.297 | 0 | 493.297 | 4,502,111 | 2025 | 2024 | -1.15 | 762.45 | 493.297 | 0.646989310774 | 465.617 | 0 | 0 | 507.273 | 0.665319693095 | 5.914205081194 | 0 | 0 | 0.49 | 493.297 | 2026-05-04 | 465.617 | 27.68 | 🟩 NoCs: 0 | 2026-01-04 | -0.054634402256 | 2026-05-04 | 0 | 5.257805757755 | 0.610685290839 | 4,008,814 | 5.249887375589 | 0 | 0 | 0 | 0 | 0 | 2026-01-04 | 0.76 | 0 | 0 | 0 | 5.904795068529 | 0 | 4,008,814 | [5 empty] | NTE | thing_6bc2a07c-3c3c-5955-96e3-632a827e027e (https://www.notion.so/thing_6bc2a07c-3c3c-5955-96e3-632a827e027e-25aa1d8f955980068076cf9b5a6ecc9d?pvs=21) |  |  | Smibakken 10 |  | No | Does not qualify | 1250A (justert til 625A, justeres opp til 725A) | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Pending | 6018 | Ålesund | Signed | https://drive.google.com/file/d/1DYg-wfNbgf3fF_oxRG4U4BQ19sQL73T0/view | Breiviksenteret AS (https://www.notion.so/Breiviksenteret-AS-311a1d8f955980e4a009c183aa043b48?pvs=21) | Rikard | 400 V | Solar as a Service | 428 | 2024-12-31 |  | Innvendig adkomst til taket | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Johan Baumann (https://www.notion.so/Johan-Baumann-22ca1d8f955980848ccaf63510c225bf?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | Not started | Linja | Done | Completed |  | Default | 10 x Sungrow 50 kW |  | Roof OK | No | 21.05: godkjent søknad. | Approved | 5706567298011528 (https://www.notion.so/5706567298011528-29ca1d8f95598067883cdd519b25bd80?pvs=21), 36805186 (https://www.notion.so/36805186-29ca1d8f955980aaa46dc7cbb1b61a32?pvs=21) | Multiconsult ASA (https://www.notion.so/Multiconsult-ASA-1a6a1d8f955980fd95b5d7a99ad7d568?pvs=21) | Received | Not relevant |  | 2013 (små reparasjoner gjort av Langas før anlegget ble installert) | 1326 x Sunova 575Wp | Done | Not interested | Erklæring + samtykke klar på drive. Trenger samtykke fra DNB Bank ASA (org nr 984 851 006) |  | Siri |  |  |  |  | 300 | 3,708,814
In operation (COD) | Mellomriksvegen 4869, 7530 Meråker |  | 293 | 2025-10-14 | 2025-12-19 | 2025-10-14 | 2025-10-16 | 2025-12-19 | 294.84 | Signed APA | 🟨 66 days | 66 | 🟩 2 days | 2 | 🟨 64 days | 64 | 🟥 353 days | 353 | 🟨 287 days | 287 | 0.29 | 12.831 | 🟩 All good |  | ❌ End date missing | 💚 All good | 25 - Dec | 2510 | 206,535.6 | 585.084985835694 | 0.585084985836 | 🟩 OK! | 190.0568124 | 190,056.8124 | 2025 - Q4 | 2025 - Q4 | 2024 - Q4 | 61,057.6 | 0 |  |  | 158.309 | 1,754,573 | 1,754,573 | ⌚ 103 days | 61,057.6 | 158.309 | 206,535.6 | 337.56 | 1,754,573 | 158.309 | 158.309 | 0 | 158.309 | 1,754,573 | 2025 | 2024 | 1.84 | 294.84 | 158.309 | 0.536931895265 | 206.535 | 61,057.6 | 61,057.6 | 107.498 | 0.364597747931 | 5.814887372014 | 0 | 0 | 0.16 | 158.309 | 1.75 | 145.478 | 12.831 | 🟩 NoCs: 0 | 2026-06-01 | 0.335900827568 | 1.75 | 337,559.6 | 5.414000814001 | 0.700498575499 | 1,596,264 | 5.448 | 61,057.6 | 0 | 276.502 | 337,559.6 | 276.502 | 2026-06-01 | 0.29 | 0 | 0 | 0 | 5.950932709266 | 0 | 1,596,264 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Mellomriksvegen_4869.pdf | 7 |  | 20% | NTE | thing_473af535-2f4d-5d93-8db1-7ba37dbbd76b (https://www.notion.so/thing_473af535-2f4d-5d93-8db1-7ba37dbbd76b-294a1d8f9559809999d5edc9fed1d6a3?pvs=21) |  | 305.288 | Mellomriksvegen 4869 | Termoenergi | Yes | Application: Successful | 400A, innstilt på 300A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - not all PPAs | 7530 | Meråker | Signed |  | Handelseiendom Meråker AS (https://www.notion.so/Handelseiendom-Mer-ker-AS-311a1d8f955980b9acfcf562e12e96f8?pvs=21) | Rikard | 400 V | Solar as a Service | 240 | 2024-12-31 |  |  | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Kristoffer Liset (https://www.notion.so/Kristoffer-Liset-27fa1d8f955980aab65aefd37f755467?pvs=21), Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | TENSIO TS | Planned | Completed |  | Default | 2x Solis 110kW |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 6970631405215236 (https://www.notion.so/6970631405215236-313a1d8f9559809fbdd0e11577eb3a7a?pvs=21), 6970631407709337 (https://www.notion.so/6970631407709337-313a1d8f9559807f9916df300d845da8?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received |  |  |  | 504 x TWMND-72HD Bifacial 585 Wp | Done | Planned |  |  | Siri |  |  |  |  | 95 | 1,501,264
Ready to build | Rolvsøyveien 402, 1666 Rolvsøy |  | 116.15 | 2026-08-03 | 2026-10-30 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 478 days (ongoing) | 478 | 🟥 478 days (ongoing) | 478 | 0.12 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -17.405 | 501.985355648536 | 0.501985355649 | 🟩 OK! | 99.0213595 | 99,021.3595 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 925.319 | ❌ COD not set | 0 | 0 | -17.405 | 0 | 0 | 0 | 0 | 119,974.5 | 0 | 0 |  | 2024 | -116.15 | 116.15 | 240.354 | 2.06934136892 | 239.949 | 17 | 17 | 240.354 | 2.06934136892 | 7.966586310805 | 0 | 0 | 0 | 0 | 0 | -17.405 | 17.405 | 🟩 NoCs: 0 | 0.68 | -0.003486870427 | 0.93 | 0 | 5.897244941885 | 2.065854498493 | 684.965 | 5.897244941885 | 17 | 0 | 0 | 17 | 0 | 0.68 | 0 | 0 | 0 | 0 |  | 0 | 684.965 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Rolvsyveien_402.pdf, Deployment/Tilskuddsbrev_Rolvsyveien_402.pdf | 5.99 |  | 20% |  |  |  | 85 | Rolvsøyveien 402 | Termoenergi | Yes | Application: Successful | 630 A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) |  | 1666 | Rolvsøy | Signed | https://drive.google.com/file/d/1VowXNk2LAhKiKBQ6aqq0f-WxS-bhuxLb/view | Rolvsøyveien 402 AS (https://www.notion.so/Rolvs-yveien-402-AS-311a1d8f9559808b89b4f8ae5b4baab4?pvs=21) | Rikard | 400 V | Solar as a Service | 212 | 2024-12-09 |  | Ingen adkomst til tak. Må bruke lift. |  |  | Not uploaded | To be applied |  |  |  |  | Not started | NORGESNETT | No status | Completed |  |  |  |  | In process | Yes | Ikke søknadspliktig | Not applicable |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Booked | Not relevant |  | 2023 på REMA, eldre på Vianor. |  | No status | Not started |  |  | Siri |  |  |  |  | 122.151 | 562.814
Ready to build | Billingstadsletta 11, 1396 Billingstad |  | 207.3 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.21 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 333.179824561404 | 0.333179824561 | 🟩 OK! | 160.8648 | 160,864.8 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,264,302 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.386 | 0 | 0 |  | 2024 | -207.3 | 207.3 | 151.93 | 0.732899179932 | 151.93 | 0 | 0 | 151.93 | 0.732899179932 | 6.098900144718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-11-01 | 0 | 1.26 | 0 | 5.366000964785 | 0.732899179932 | 1,112,372 | 5.366000964785 | 0 | 0 | 0 | 0 | 0 | 2026-11-01 | 0 | 0 | 0 | 0 |  | 0 | 1,112,372 | [9 empty] | Billingstadsletta 11 | Termoenergi |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 1396 | Billingstad | Signed |  | Billingstadsletta 11 AS (https://www.notion.so/Billingstadsletta-11-AS-311a1d8f955980619c0fc4b3ff9b2638?pvs=21) | Rikard |  | Solar as a Service | 132 | 2024-12-31 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | No status | TBD |  | To be applied |  |  | No status |  |  |  |  | No status | Not started |  |  | Siri |  |  |  |  | 97.638 | 1,014,734
In operation (COD) | Semsvegen 40A, 3676 Notodden |  | 132.21 | 2025-09-18 | 2026-03-06 | 2025-09-18 | 2025-10-14 | 2026-03-06 | 132.21 | Transferred | 🟥 169 days | 169 | 🟩 26 days | 26 | 🟥 143 days | 143 | 🟥 430 days | 430 | 🟨 261 days | 261 | 0.13 | 14.722 | 🟩 All good |  | ❌ End date missing | 💚 All good | 26 - Mar | 2510 | 204,900.5 | 533.262790697674 | 0.533262790698 | 🟩 OK! | 98.7621921 | 98,762.1921 | 2026 - Q1 | 2025 - Q3 | 2024 - Q4 | 0 | 0 |  |  | 219,622.5 | 872,958.6 | 969.954 | ⌚ 26 days | 0 | 219,622.5 | 204,900.5 | 0 | 872.959 | 147.03 | 147,029.6 | 22,930.3 | 244.025 | 872,958.6 | 2026 | 2024 | 0 | 132.21 | 244.025 | 1.845737841313 | 229.303 | 0 | 0 | 242.554 | 1.834611602753 | 7.325338476666 | 0 | 0 | 0.24 | 244.025 | 0.97 | 229.303 | 14.722 | 🟩 NoCs: 0 | 0.73 | -0.100226911731 | 0.97 | 0 | 5.490726873913 | 1.734384691022 | 725.929 | 5.490726873913 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0.13 | 0 | 0 | 0 | 7.336464715226 | 0 | 725.929 | [6 empty] | thing_4829ab0b-b202-5b33-805d-33b089139ef4 (https://www.notion.so/thing_4829ab0b-b202-5b33-805d-33b089139ef4-2a3a1d8f955980b791e3ffc07f3c151f?pvs=21) | Not started |  | Semsvegen 40A |  | No | Does not qualify | 800A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 3676 | Notodden | Signed | https://drive.google.com/file/d/1gKHosUaF_RLUiSbrX0buR8jv1Qps-iXP/view | Notodden Butikkeiendom AS (https://www.notion.so/Notodden-Butikkeiendom-AS-311a1d8f955980ecac83e0f5584cca17?pvs=21) | Rikard | 230 V | Solar as a Service | 130 | 2024-12-31 |  | Skal nylig være stige installert her: opp fra trappen på østsiden av bygget | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Uploaded FDV | To be applied |  |  |  |  | Done | Everket AS | Done | Completed |  | Default | 2x Growatt 50KTL3-XL |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 7359992921142612 (https://www.notion.so/7359992921142612-308a1d8f955980da9c41cae079c288ac?pvs=21), 7359992902072884 (https://www.notion.so/7359992902072884-313a1d8f955980708eeaf8dc71161f8c?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 226x585W Tongwei TWMND-72HD | Done | In operation |  | Installed | Kjetil |  |  |  |  | 90 | 635.929
In operation (COD) | Vestsidevegen 6, 2420 Trysil |  | 177 | 2025-11-27 | 2026-03-19 | 2025-11-27 | 2026-01-13 | 2026-03-19 | 177 | Signed APA | 🟨 112 days | 112 | 🟨 47 days | 47 | 🟨 65 days | 65 | 🟥 443 days | 443 | 🟥 331 days | 331 | 0.18 | 21.508 | 🟩 All good |  | ❌ End date missing | ❌ Missing | 26 - Mar | 2601 | 17.878 | 395.986455981941 | 0.395986455982 | 🟩 OK! | 126.89484 | 126,894.84 | 2026 - Q1 | 2025 - Q4 | 2024 - Q4 | 6,981.8 | 0 |  |  | 32,404.2 | 235,604.2 | 1,178,021 | ⌚ 13 days | 6,981.8 | 32,404.2 | 17.878 | 34.909 | 235.604 | -780.396 | -780,395.8 | 140,337.6 | 162.021 | 235,604.2 | 2026 | 2024 | 0 | 177 | 162.021 | 0.915372881356 | 175.422 | 34.909 | 34.909 | 134.809 | 0.761632768362 | 6.501745762712 | 0 | 8.21 | 0.16 | 162.021 | 1.18 | 140.513 | 21.508 | 🟩 NoCs: 0 | 2026-02-01 | 0.229451977401 | 1.18 | 34.909 | 5.74011299435 | 0.991084745763 | 1,016,000 | 5.74011299435 | 34.909 | 0 | 0 | 34.909 | 0 | 2026-02-01 | 0.18 | 0 | 0 | 0 | 6.655485875706 | 0 | 1,016,000 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Vestsidevegen_6.pdf | 7 |  | 20% | NTE | thing_546f6724-0b3b-5115-a3eb-b173a4806d5b (https://www.notion.so/thing_546f6724-0b3b-5115-a3eb-b173a4806d5b-2e3a1d8f9559802d8de9ec831c7a1f67?pvs=21) |  | 174.545 | Vestsidevegen 6 | Termoenergi |  | Application: Successful | 900A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 2420 | Trysil | Signed | https://drive.google.com/file/d/1ru2LxKBf-A7A-z4umhGwraeMQwJYROZi/view | Vido Eiendom AS (https://www.notion.so/Vido-Eiendom-AS-311a1d8f955980e29203c5298c04f397?pvs=21) | Rikard | 400 V | Solar as a Service | 124 | 2024-12-31 |  | Ingen tilgang til tak, men fått tilbud fra Trygg Stiger på å etablere dette. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Amund Ims Myhre (https://www.notion.so/Amund-Ims-Myhre-2bca1d8f9559804db986df6106327617?pvs=21) | Not uploaded | To be applied |  |  |  |  | In progress | ELVIA | No status | Completed |  | Different | 1x Growatt MAX 125KTL3-X LV |  | Roof OK | Yes | Godkjent | Approved | 7359992901841733 (https://www.notion.so/7359992901841733-2e8a1d8f95598081b1e6e2914f9edb90?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 300x590W PhonoSolar Premium glass-glass | Not relevant | Ordered | Erklæring + samtykke klar på drive. Trenger samtykke fra DNB Bank ASA (org nr 984 851 006) | Delivered to installer | Kjetil | 8.21 |  |  |  | 0 | 1,016,000
In operation (COD) | Johan Falkbergets veg 2, 2407 Elverum |  | 136.7 | 2025-09-22 | 2025-11-18 | 2025-09-22 | 2025-10-21 | 2025-11-18 | 136.7 | Transferred | 🟩 57 days | 57 | 🟩 29 days | 29 | 🟩 28 days | 28 | 🟥 322 days | 322 | 🟨 265 days | 265 | 0.14 | 26.564 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-11-25 | 2510 | 129,839.8 | 403.226708074534 | 0.403226708075 | 🟩 OK! | 105.375195 | 105,375.195 | 2025 - Q4 | 2025 - Q3 | 2024 - Q4 | 19,456.8 | 3,417.5 | 3,417.5 | 284.791666666667 | 136.947 | 882.947 | 882.947 | ⌚ 134 days | 19,456.8 | 136.947 | 129,839.8 | 19.457 | 882.947 | 136.947 | 136.947 | 0 | 136.947 | 882.947 | 2025 | 2024 | 0 | 136.7 | 136.947 | 1.001806876372 | 129.839 | 19,456.8 | 19,456.8 | 46.783 | 0.342231163131 | 5.799436722751 | 0 | 0 | 0.14 | 136.947 | 0.88 | 110.383 | 26.564 | 🟩 NoCs: 0 | 0.75 | 0.607578639356 | 0.88 | 19,456.8 | 5.45720555962 | 0.949809802487 | 746 | 5.45720555962 | 19,456.8 | 0 | 0 | 19,456.8 | 0 | 0.75 | 0.14 | 0 | 0 | 0 | 6.459012435991 | 0 | 746 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Johan_Falkbergets_Veg_2.pdf | 7 |  | 20% | NTE | thing_34628494-7f9b-5dbd-be15-e43bcb99b297 (https://www.notion.so/thing_34628494-7f9b-5dbd-be15-e43bcb99b297-299a1d8f95598083bbf4c6426c050003?pvs=21) |  | 97.284 | Johan Falkbergets veg 2 | Termoenergi | Yes | Payment received | 300A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 2407 | Elverum | Signed | https://drive.google.com/file/d/1tPOBRu_5M-_EacXW3xPFFLsLkyG0E7XO/view | Hanstad Næringseiendom AS (https://www.notion.so/Hanstad-N-ringseiendom-AS-311a1d8f9559808399bdea0e29c9ac5f?pvs=21) | Rikard | 400 V | Solar as a Service | 122 | 2024-12-31 |  | Innvendig trapp | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | Not started | ELVIA | Done | Completed |  | Default | 1 x Sungrow SG125CX-P2 |  | Roof OK | No | Godkjent | Approved | 7359992892869341 (https://www.notion.so/7359992892869341-2afa1d8f95598065af72efd584f19265?pvs=21) |  |  | Not relevant |  |  | 186 x Longi LR7-72HVH-645 | Done | In operation |  |  | Siri |  |  |  |  | 0 | 746
In operation (COD) | Torpavegen 2, 2607 Vingrom |  | 174.64 | 2025-11-27 | 2026-03-22 | 2025-11-27 | 2026-01-12 | 2026-03-22 | 174.64 | Signed APA | 🟨 115 days | 115 | 🟨 46 days | 46 | 🟨 69 days | 69 | 🟥 446 days | 446 | 🟥 331 days | 331 | 0.17 | 25.688 | 🟩 All good |  | ❌ End date missing | 💚 All good | 26 - Mar | 2601 | 13,831.8 | 385.45067264574 | 0.385450672646 | 🟩 OK! | 127.784088 | 127,784.088 | 2026 - Q1 | 2025 - Q4 | 2024 - Q4 | 0 | 0 |  |  | 39,519.8 | 237,528.8 | 1,187,644 | ⌚ 10 days | 0 | 39,519.8 | 13,831.8 | 0 | 237.529 | -752.516 | -752,516.2 | 137,528.8 | 197.599 | 237,528.8 | 2026 | 2024 | 0 | 174.64 | 197.599 | 1.131464727439 | 171.911 | 0 | 0 | 97.541 | 0.558526110857 | 6.227588181402 | 0 | 8.21 | 0.2 | 197.599 | 1.19 | 171.911 | 25.688 | 🟩 NoCs: 0 | 0.99 | 0.425847457627 | 1.19 | 0 | 5.669062070545 | 0.984373568484 | 990.045 | 5.669062070545 | 0 | 0 | 0 | 0 | 0 | 0.99 | 0.17 | 0 | 0 | 0 | 6.800526797984 | 0 | 990.045 | [5 empty] | NTE | thing_0e539b69-f934-5713-b542-93a74023cf5f (https://www.notion.so/thing_0e539b69-f934-5713-b542-93a74023cf5f-2e3a1d8f9559808893d3cbe809aa0438?pvs=21) |  |  | Torpavegen 2 |  |  | Does not qualify | 800A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 2607 | Vingrom | Signed | https://drive.google.com/file/d/14jaVcdESZt4HfHQFPGcz3cPcxAOrP5g3/view | Vingrom Butikkeiendom AS (https://www.notion.so/Vingrom-Butikkeiendom-AS-311a1d8f95598074a83ee884528f6368?pvs=21) | Rikard | 400 V | Solar as a Service | 116 | 2024-12-31 |  | Her er det tilgang til tak. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Amund Ims Myhre (https://www.notion.so/Amund-Ims-Myhre-2bca1d8f9559804db986df6106327617?pvs=21) | Not uploaded | To be applied |  |  |  |  | Done | ELVIA | Planned | Completed |  | Default | 1x Growatt MAX 125KTL3-X LV |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 7359992899911364 (https://www.notion.so/7359992899911364-2e8a1d8f955980418966da9cd43f4e7e?pvs=21), 7359992926728958 (https://www.notion.so/7359992926728958-330a1d8f955980bb95eefbb824adce6a?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 296x590W PhonoSolar Premium glass-glass | Not relevant | Ordered | Erklæring + samtykke klar på drive. Trenger samtykke fra DNB Bank ASA (org nr 984 851 006) | Installed | Kjetil | 8.21 |  |  |  | 0 | 990.045
Signed | Biskop Jens Nilssøns gate 5, 0659 Oslo |  | 102.1 |  |  |  |  | 2026-03-31 |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 455 days | 455 | 🟥 456 days (ongoing) | 456 | 0.1 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Mar |  | -11.344 | 181.191208791209 | 0.181191208791 | 🟥 SUM! | 80.1485 | 80,148.5 | 2026 - Q1 |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 844.197 | ⌚ 1 days | 0 | 0 | -11.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2024 | -102.1 | 102.1 | 93.786 | 0.918570029383 | 82.442 | 0 | 0 | 93.786 | 0.918570029383 | 8.26833496572 | 0 | 0 | 0 | 0 | 0 | -11.344 | 11.344 | 🟩 NoCs: 0 | 0.75 | -0.11110675808 | 0.84 | 0 | 7.349764936337 | 0.807463271303 | 750.411 | 7.349764936337 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 |  | 0 | 750.411 | [9 empty] | Biskop Jens Nilssøns gate 5 | Termoenergi |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) |  | 659 | Oslo | Signed |  | Biskop Jens Nilssønsgt AS (https://www.notion.so/Biskop-Jens-Nilss-nsgt-AS-311a1d8f955980f087baedbd16bf9c12?pvs=21) | Rikard | 230 V | Solar as a Service | 95 | 2024-12-31 |  |  |  |  | Not uploaded | [5 empty] | Not started | ELVIA | No status | Completed |  |  |  |  | Roof OK | TBD |  | To be applied |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | [8 empty] | Siri |  |  |  |  | 140.481 | 609.93
In operation (COD) | Sentrumsveien 40, 3748 Siljan |  | 96.8 | 2025-09-22 | 2025-11-06 | 2025-09-22 | 2025-10-24 | 2025-11-06 | 96.8 | Transferred | 🟩 45 days | 45 | 🟩 32 days | 32 | 🟩 13 days | 13 | 🟥 310 days | 310 | 🟨 265 days | 265 | 0.1 | 20.661 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-11-25 | 2510 | 128,590.2 | 414.806451612903 | 0.414806451613 | 🟩 OK! | 78.80972 | 78,809.72 | 2025 - Q4 | 2025 - Q3 | 2024 - Q4 | 21,230.2 | 2.42 | 2.42 | 201.666666666667 | 128.021 | 708.021 | 708.021 | ⌚ 146 days | 21,230.2 | 128.021 | 128,590.2 | 0 | 708.021 | 128.021 | 128.021 | 0 | 128.021 | 708.021 | 2025 | 2024 | 0 | 96.8 | 128.021 | 1.322530991736 | 128.59 | 21,230.2 | 21,230.2 | 128.021 | 1.322530991736 | 7.314266528926 | 0 | 0 | 0.13 | 128.021 | 0.71 | 128.59 | 20.661 | 🟩 NoCs: 0 | 0.58 | 0.005878099173 | 0.71 | 0 | 5.99173553719 | 1.328409090909 | 580 | 5.99173553719 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0.1 | 21.23 | 0 | 0 | 7.314266528926 | 0 | 580 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Sentrumsveien_40.pdf | 7 |  | 20% | NTE | thing_4f8f513f-a255-58ed-991c-4df916cc580b (https://www.notion.so/thing_4f8f513f-a255-58ed-991c-4df916cc580b-29ca1d8f955980dc9014e2737070b786?pvs=21) |  | 106.151 | Sentrumsveien 40 | Termoenergi | Yes | Payment received | 400 A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 3748 | Siljan | Signed | https://drive.google.com/file/d/1gEZ2cLMTFcnCkZIeEDNSSEhUVX5Kehdq/view | Siljan Butikkeiendom AS (https://www.notion.so/Siljan-Butikkeiendom-AS-311a1d8f955980ffa05dff9f0b598cf5?pvs=21) | Rikard | 400 V | Solar as a Service | 75 | 2024-12-31 |  | Stige fra bakkeplan til tak | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Rea Londo (https://www.notion.so/Rea-Londo-27ea1d8f955980c3adedd35b2d71061d?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | Not started | LEDE | Done | Completed |  | Default | 1 x Sungrow SG125-CX |  | Roof OK | No | Ikke søknadspliktig | Not applicable | 7359992907648077 (https://www.notion.so/7359992907648077-2afa1d8f955980a0ae22e67e3479c978?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 150 x Longi LR7-72HVH-645 | Done | In operation |  |  | Siri |  |  |  |  | 0 | 580
Signed | Hognestadvegen 90, 4344 Bryne |  | 150.65 | 2025-09-29 | 2026-04-10 | 2025-09-29 | 2025-11-06 |  |  | Signed APA | 🟥 184 days (ongoing) | 184 | 🟩 38 days | 38 | 🟥 146 days (ongoing) | 146 | 🟥 456 days (ongoing) | 456 | 🟨 272 days | 272 | 0.15 | 0 | 🟩 All good | 0 | ❌ End date missing | 💛 Chill |  | 2511 | 229,591.3 | 564.578947368421 | 0.564578947368 | 🟩 OK! | 128.2679295 | 128,267.9295 |  | 2025 - Q3 | 2024 - Q4 | 8.28 | 0 | 0 | 0 | 242,430.3 | 1,040,268.6 | 1,155,854 | ❌ COD not set | 8.28 | 242,430.3 | 229,591.3 | 9.2 | 1,040,269 | 153.782 | 153,781.6 | 25,744.8 | 269.367 | 1,040,268.6 |  | 2024 | -150.65 | 150.65 | 269.367 | 1.788031861932 | 257.448 | 9.2 | 9.2 | 253.591 | 1.683312313309 | 7.547812811152 | 0 | 0 | 0 | 269.367 | 1.16 | 248.248 | 21.119 | 🟨 NoCs: 1 | 0.89 | 0.025602389645 | 1.16 | 9.2 | 5.884414205111 | 1.708914702954 | 883.487 | 5.864500497843 | 9.2 | 0 | 0 | 9.2 | 0 | 0.89 | 0 | 0 | 0 | 0 |  | 3 | 886.487 | 2025-09-22 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Hognestadvegen_90.pdf | 5 |  | 20% | NTE | thing_cda1356d-fd14-5bdd-8c0a-10319b07a92b (https://www.notion.so/thing_cda1356d-fd14-5bdd-8c0a-10319b07a92b-2a2a1d8f95598023ae30c04139d7dae2?pvs=21) |  | 46 | Hognestadvegen 90 | TermoEnergi / Piotr | Yes | Application: Successful | 800A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 4344 | Bryne | Signed | https://drive.google.com/file/d/1BhZSxTuMsl2WY_oJbrdHGHJ-OvhV5jks/view | Hognestadvegen 90 Jæren AS (https://www.notion.so/Hognestadvegen-90-J-ren-AS-311a1d8f95598048abfef77c2e85bf66?pvs=21) | Rikard | 400 V | Solar as a Service | 74 | 2024-12-31 |  | Spiraltrapp fra bakkeplan. | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | LNETT | Done | Completed |  |  | 1x Solis S6-GC125K |  | Roof OK | Yes | Unntatt søknadsplikt | Approved | 7359992922183454 (https://www.notion.so/7359992922183454-2afa1d8f95598030a97fd241ad5608f3?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 262x575W LONGi | Done | In operation |  | Delivered to installer | Kjetil |  |  |  |  | 120.121 | 763.366
Cancelled | Betzy Kjeldsbergs vei 9, 0486 Oslo |  | 61.9 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.06 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | -56.934210526316 | -0.056934210526 | 🟥 SUM! | 48.5296 | 48,529.6 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 436.477 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | -61.9 | 61.9 | -25.962 | -0.419418416801 | -25.962 | 0 | 0 | -25.962 | -0.419418416801 | 7.051324717286 | 0 | 0 | 0 | -25.962 | 0.44 | -25.962 | 0 | 🟩 NoCs: 0 | 0.46 | 0 | 0.44 | 0 | 7.470743134087 | -0.419418416801 | 462.439 | 7.470743134087 | 0 | 0 | 0 | 0 | 0 | 0.46 | 0 | 0 | 0 | 0 |  | 0 | 462.439 | [9 empty] | Betzy Kjeldsbergs vei 9 | Termoenergi |  |  | 630A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) |  | 486 | Oslo | Signed |  | Betzy Kjeldsbergs Vei 9 AS (https://www.notion.so/Betzy-Kjeldsbergs-Vei-9-AS-311a1d8f955980f1b68ad670a87d8133?pvs=21) | Rikard | 230 V | Solar as a Service | 56 | 2024-12-31 |  |  |  |  | Not uploaded | [5 empty] | Not started |  | No status | Completed |  |  |  |  | Roof OK | TBD |  | To be applied | [11 empty] | Siri |  |  |  |  | 89.801 | 372.638
Signed | Arnebråtveien 159, 0771 Oslo |  | 68.4 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.07 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 96.074561403509 | 0.096074561404 | 🟥 SUM! | 55.062 | 55.062 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 489.453 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2024 | -68.4 | 68.4 | 43.81 | 0.640497076023 | 43.81 | 0 | 0 | 43.81 | 0.640497076023 | 7.155745614035 | 0 | 0 | 0 | 43.81 | 0.49 | 43.81 | 0 | 🟩 NoCs: 0 | 0.45 | 0 | 0.49 | 0 | 6.515248538012 | 0.640497076023 | 445.643 | 6.515248538012 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0 | 0 | 0 |  | 0 | 445.643 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Arnebratveien_159.pdf | 7 | [5 empty] | 72.226 | Arnebråtveien 159 | Termoenergi | Yes | Cancelled | 630A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) |  | 771 | Oslo | Signed |  | Arnebråtveien AS (https://www.notion.so/Arnebr-tveien-AS-311a1d8f955980f98fe4d919a7906419?pvs=21) | Rikard | 230 V | TBD | 53 | 2024-12-31 |  | Adkomst via innvendig trapp | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Not uploaded | [5 empty] | Not started |  | No status | Completed |  |  | 1 x Solis-50k-LV-DC |  | Roof OK | No | Godkjent | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received |  | Eldre del: Singel belastet 2 lagstekking med derbigum takbelegg. Nyere del: 1 lagstekking med atb | Eldre del (1.etg): 2002, nyere del (2.etg): 2012/2013 | 106 x Longi LR7-72HVH-645 |  |  |  |  | Siri |  |  |  |  | 89.604 | 356.039
In operation (COD) | Høvågveien 199, 4639 Kristiansand |  | 391.88 | 2025-01-20 | 2025-06-16 | 2025-01-20 | 2025-04-25 | 2025-06-16 | 391.88 | Transferred | 🟨 147 days | 147 | 🟥 95 days | 95 | 🟩 52 days | 52 | 🟩 178 days | 178 | 🟩 31 days | 31 | 0.39 | 6.781 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Jun | 2504 | 734,841.5 | 4,128.320224719101 | 4.128320224719 | 🟩 OK! | 349.94884 | 349,948.84 | 2025 - Q2 | 2025 - Q1 | 2024 - Q4 | 188,618.5 | 9.797 | 9.797 | 4,898.5 | 553.004 | 2,652,004 | 2,652,004 | ⌚ 289 days | 188,618.5 | 553.004 | 734,841.5 | 0 | 2,652,004 | 553.004 | 553.004 | 0 | 553.004 | 2,652,004 | 2025 | 2024 | 0 | 391.88 | 553.004 | 1.411156476472 | 734.841 | 188,618.5 | 188,618.5 | 553.004 | 1.411156476472 | 6.767387975911 | 0 | 0 | 0.55 | 553.004 | 2.65 | 734.842 | 6.781 | 🟩 NoCs: 0 | 2026-01-02 | 0.464011942432 | 2.65 | 0 | 5.356231499439 | 1.875168418904 | 2,099,000 | 5.356231499439 | 0 | 0 | 0 | 0 | 0 | 2026-01-02 | 0.39 | 188.619 | 0 | 0 | 6.767387975911 | 0 | 2,099,000 | 2024-11-22 | Deployment/Hvagveien_199_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  | 50% | NTE | thing_7a41e0ba-5bc3-5b0c-9a99-8fed7f0abb9a (https://www.notion.so/thing_7a41e0ba-5bc3-5b0c-9a99-8fed7f0abb9a-1eca1d8f955980b9b561fcbdd70680e9?pvs=21) | Not started | 377.237 | Høvågveien 199 |  | Yes | Payment received | 630A (stilt inn til 400A) | Oksøy Eiendom AS (https://www.notion.so/Oks-y-Eiendom-AS-1a7a1d8f95598021981fd7c95fbbc35e?pvs=21) | Yes - all PPAs | 4639 | Kristiansand | Signed |  |  | Ole Bjørn | 400 V | Solar as a Service | 391.88 | 2024-12-20 | Terje Gundersen (https://www.notion.so/Terje-Gundersen-1a5a1d8f955980a1beabc7ac3064361d?pvs=21) | Tilkomst til taket via teknisk rom i bygget. | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved |  | GoO priced in APA | Not relevant | 2025-09-17 | Done | GLITRE | Done | Completed |  | Default | 2x 125kW Sungrow SG125CX-P2 1x 40kW Sungrow SG40CX-P2 |  | Roof OK | Yes | Solceller er illustrert og forutsatt i byggesak. Trengs ikke egen søknad på dette da. | Approved | 5706567346205923 (https://www.notion.so/5706567346205923-214a1d8f9559801fa4aed817ff62a943?pvs=21), 5706567362128350 (https://www.notion.so/5706567362128350-217a1d8f9559804a9344ecbd188658c2?pvs=21) |  | Received | Not relevant | Derbigum | 2024 | 776x505W Runergy HY-DH120N9 | Done | Not interested | 12.02.26: fått erklæringer og samtykke digitalt… Bedt om å få de tilsendt i posten. Får tilbakemelding i uke 7-8 ish. 28.01.26: etterspurt signatur på erklæring + på samtykke fra bank. HUSK å sladde adresse i takleieavtale (den stemmer ikke med adresse hos kartverket) - avtalen er printet ut. | Installed | Kjetil |  |  |  |  | 190 | 1,909,000
Signed | Stasjonsgata 32, 1820 Spydeberg |  | 244.7 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.24 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 347.326754385965 | 0.347326754386 | 🟩 OK! | 200.654 | 200.654 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,457,963 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31,676.2 | 0 | 0 |  | 2024 | -244.7 | 244.7 | 158.381 | 0.647245606866 | 158.381 | 0 | 0 | 158.381 | 0.647245606866 | 5.958165100123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-03-01 | 0 | 1.46 | 0 | 5.310919493257 | 0.647245606866 | 1,299,582 | 5.310919493257 | 0 | 0 | 0 | 0 | 0 | 2026-03-01 | 0 | 0 | 0 | 0 |  | 0 | 1,299,582 | [9 empty] | Stasjonsgata 32 |  |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 1820 | Spydeberg | Signed |  | Spydeberg Eiendomsinvest AS (https://www.notion.so/Spydeberg-Eiendomsinvest-AS-311a1d8f9559805fa7d4d2e4aec008da?pvs=21) | Rikard |  | Solar as a Service | 175 | 2024-12-31 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | No status | TBD | 10.04: Fått beskjed at vi må søke. 31.03: Sendt layout til kommunen. 27.03: PBE har bedt om layout. 03.03: Søkt om unntak. | To be applied |  |  | No status |  |  |  |  | No status | Not started |  |  | Siri |  |  |  |  | 115.234 | 1,184,348
Signed | Brokelandsheia 31, 4993 Sundebru |  | 160 | 2026-06-01 | 2026-08-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 467 days (ongoing) | 467 | 🟥 467 days (ongoing) | 467 | 0.16 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 411.404710920771 | 0.411404710921 | 🟩 OK! | 136.48 | 136.48 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,036,726 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153,700.8 | 0 | 0 |  | 2024 | -160 | 160 | 161.526 | 1.0095375 | 192.126 | 30.6 | 30.6 | 161.526 | 1.0095375 | 6.4795375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.88 | 0.19125 | 2026-04-01 | 0 | 5.47 | 1.2007875 | 875.2 | 5.47 | 30.6 | 0 | 0 | 30.6 | 0 | 0.88 | 0 | 0 | 0 | 0 |  | 0 | 875.2 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Brokelandsheia_31.pdf, Deployment/Tilskuddsbrev_Brokelandsheia_31.pdf | 5.97 |  | 20% |  |  |  | 153 | Brokelandsheia 31 | Termoenergi |  | Application: Successful | 300A, men stilt inn på 260A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 4993 | Sundebru | Signed |  | Brokelandsheia AS (https://www.notion.so/Brokelandsheia-AS-311a1d8f9559804ea4a1c0ec6cc09ca8?pvs=21) | Rikard | 400 V | Solar as a Service | 160 | 2024-12-20 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  |  |  | No status | Yes | Ikke søknadspliktig | Approved |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil |  |  |  |  | 59.2 | 816
In operation (COD) | Havnegata 16, 7503 Stjørdal |  | 704.48 | 2025-02-05 | 2025-10-22 | 2025-02-05 | 2025-05-13 | 2025-10-22 | 702.1 | Transferred | 🟥 259 days | 259 | 🟥 97 days | 97 | 🟥 162 days | 162 | 🟨 295 days | 295 | 🟩 36 days | 36 | 0.7 | 636.891 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Oct | 2505 | -153.226 | -519.410169491525 | -0.519410169492 | 🟩 OK! | 479.969602 | 479,969.602 | 2025 - Q4 | 2025 - Q1 | 2024 - Q4 | 0 | 17,552.5 | 17,552.5 | 2,925.416666666667 | 483.665 | 4,145,205 | 4,145,205 | ⌚ 161 days | 0 | 483.665 | -153.226 | 0 | 4,145,205 | 483.665 | 483.665 | 0 | 483.665 | 4,145,205 | 2025 | 2024 | -2.38 | 702.1 | 483.665 | 0.68888334995 | -153.226 | 0 | 0 | 1,264,673 | 1.80127189859 | 6.992693901885 | 0 | 0 | 0.48 | 483.665 | 4.15 | -153.226 | 636.891 | 🟩 NoCs: 0 | 3.66 | -2.019511465603 | 4.15 | 0 | 5.21512605042 | -0.218239567013 | 3,661,540 | 5.197507381331 | 0 | 0 | 0 | 0 | 0 | 3.66 | 0.7 | 0 | 0 | 0 | 5.90400940037 | 0 | 3,661,540 | [5 empty] | NTE | thing_39e27e48-e1fb-53b9-9a2c-6c6713b23290 (https://www.notion.so/thing_39e27e48-e1fb-53b9-9a2c-6c6713b23290-20aa1d8f9559809dad40c04b49f55e81?pvs=21) | In progress |  | Havnegata 16 |  |  |  | 2500A (nedjustert til 1250A) | Logistea AS (https://www.notion.so/Logistea-AS-1a8a1d8f955980458a0ef7caf1e1a0fa?pvs=21) | Yes - all PPAs | 7503 | Stjørdal | Signed | https://drive.google.com/file/d/1LeNFvEY1PBge0FCcP2c3oiQdN8eGZWpf/view | Logistea Havnegata 16 AS (https://www.notion.so/Logistea-Havnegata-16-AS-311a1d8f955980e3a391dc576f60b00a?pvs=21) | Johan | 400 V | Solar as a Service | 684.4 | 2024-12-31 | Ole Petter Ervik (https://www.notion.so/Ole-Petter-Ervik-1a5a1d8f955980a98ea6eb7ec975005d?pvs=21), Jan Håvard Evjen Vold (https://www.notion.so/Jan-H-vard-Evjen-Vold-293a1d8f955980d79fa2cf945d488407?pvs=21) | Utvendig stige til begge tak. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | To be applied |  | GoO priced in APA | Not relevant |  | In progress | TENSIO TN | Done | Completed |  | Default | 3x Growatt MAX125KTL3, 1x Growatt MAX100KTL3 |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 177218 (https://www.notion.so/177218-1bca1d8f955980149566e322eb3669d7?pvs=21) |  | Received | Not relevant | Papp | 2025* (Nytt tak som en del av dette prosjektet) | 1180x595W JA Solar JAM72D40 MB | Done | In operation | Johan følger opp | Installed | Kjetil |  |  |  |  | 390 | 3,271,540
Signed | Vestmovegen 5, 2420 Trysil |  | 167 | 2026-10-01 | 2026-12-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 467 days (ongoing) | 467 | 🟥 467 days (ongoing) | 467 | 0.17 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 190.61670235546 | 0.190616702355 | 🟩 OK! | 122.578 | 122.578 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 982.978 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.509 | 0 | 0 |  | 2024 | -167 | 167 | 67.818 | 0.406095808383 | 89.018 | 21.2 | 21.2 | 67.818 | 0.406095808383 | 5.886095808383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.92 | 0.126946107785 | 0.98 | 0 | 5.48 | 0.533041916168 | 915.16 | 5.48 | 21.2 | 0 | 0 | 21.2 | 0 | 0.92 | 0 | 0 | 0 | 0 |  | 0 | 915.16 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Vestmovegen_5.pdf, Deployment/Tilskuddsbrev_Vestmovegen_5.pdf | 5.91 |  | 20% |  |  |  | 106 | Vestmovegen 5 | Termoenergi |  | Application: Successful |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 2420 | Trysil | Signed |  | Trysil Eiendom AS (https://www.notion.so/Trysil-Eiendom-AS-311a1d8f955980c386a6dbec952f8836?pvs=21) | Rikard |  | Solar as a Service | 167 | 2024-12-20 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | No status | TBD | Må søke. | To be applied |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil |  |  |  |  | 60.12 | 855.04
In operation (COD) | Fiboveien 12b, 4580 Lyngdal |  | 202 | 2025-05-07 | 2025-06-17 | 2025-05-07 | 2025-05-26 | 2025-06-17 | 202 | Transferred | 🟩 41 days | 41 | 🟩 19 days | 19 | 🟩 22 days | 22 | 🟩 168 days | 168 | 🟩 127 days | 127 | 0.2 | 14.899 | 🟩 All good |  | ❌ End date missing | 💚 All good | 25 - Jun | 2505 | 254,250.2 | 1,513.392857142857 | 1.513392857143 | 🟩 OK! | 171.902 | 171.902 | 2025 - Q2 | 2025 - Q2 | 2024 - Q4 | 34,583.2 | 5.05 |  |  | 234.566 | 1,399,496 | 1,399,496 | ⌚ 288 days | 34,583.2 | 234.566 | 254,250.2 | 0 | 1,399,496 | 234.566 | 234.566 | 0 | 234.566 | 1,399,496 | 2025 | 2024 | 0 | 202 | 234.566 | 1.161217821782 | 254.25 | 34,583.2 | 34,583.2 | 173.587 | 0.859341584158 | 6.626321782178 | 0 | 0 | 0.23 | 234.566 | 2026-04-01 | 254.25 | 14.899 | 🟩 NoCs: 0 | 1.16 | 0.399321782179 | 2026-04-01 | 0 | 5.76698019802 | 1.258663366337 | 1,164,930 | 5.76698019802 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0.2 | 34.583 | 0 | 0 | 6.928198019802 | 0 | 1,164,930 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Fiboveien_12b.pdf | 7 |  | 20% | NTE | thing_f83a5e78-4096-5c29-8c4b-c4e8ac8ad0ec (https://www.notion.so/thing_f83a5e78-4096-5c29-8c4b-c4e8ac8ad0ec-209a1d8f955980b0bba1f5259ee0eced?pvs=21) | Not started | 172.916 | Fiboveien 12b | Termoenergi | Yes | Payment received | 225A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 4580 | Lyngdal | Signed | https://drive.google.com/file/d/1cETAUpCxAw9RecJORqxfQP9W_DkkQpxW/view | Romeid 24 AS (https://www.notion.so/Romeid-24-AS-311a1d8f955980239bb0cc6a9bbde312?pvs=21) | Rikard | 400 V | Solar as a Service | 200 | 2024-12-31 | Daniel Tønnessen (https://www.notion.so/Daniel-T-nnessen-1f9a1d8f955980fcb918c2550c6ffa30?pvs=21) | Ingen adkomst fra verken inne i bygget eller ute. Lars (Ragde) og Jysk undersøker om noen av de andre butikkene i bygget har adkomst på noe vis, noe de burde ha mtp at det er flere solcelleanlegg der. | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21), Laila Haugeland (https://www.notion.so/Laila-Haugeland-284a1d8f955980b09ff8ee42fe0d9f41?pvs=21) | Uploaded FDV | Approved |  | GoO priced in APA | Not relevant | 2025-09-17 | Not started | GLITRE | Done | Completed |  | Default | 1 x Sungrow SG125CX-P2 |  | Roof OK | Yes | Ikke søknadsplikt | Approved | 5706567335714863 (https://www.notion.so/5706567335714863-1eca1d8f955980cb8ab5dc327b799251?pvs=21), 5706567346176872 (https://www.notion.so/5706567346176872-21ea1d8f955980e985d4d02103bab544?pvs=21) | Consult Gruppen (https://www.notion.so/Consult-Gruppen-1eea1d8f955980bb894dfd0537eb64bf?pvs=21) | Received | Not relevant |  | 2022 (ca) | 400 x DMEGC DM505M10RT-B60HSW 505Wp Bifacial | Done | Not started | Erklæring klar på drive. Ikke behov for samtykke. | Installed | Siri |  |  |  |  | 162 | 1,002,930
Signed | Sandesletta 14, 4050 Sola |  | 235 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 456 days (ongoing) | 456 | 🟥 456 days (ongoing) | 456 | 0.24 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 702.664473684211 | 0.702664473684 | 🟩 OK! | 195.99 | 195.99 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,652,865 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.083 | 0 | 0 |  | 2024 | -235 | 235 | 320.415 | 1.363468085106 | 320.415 | 0 | 0 | 320.415 | 1.363468085106 | 7.033468085106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.33 | 0 | 1.65 | 0 | 5.67 | 1.363468085106 | 1,332,450 | 5.67 | 0 | 0 | 0 | 0 | 0 | 1.33 | 0 | 0 | 0 | 0 |  | 0 | 1,332,450 | [9 empty] | Sandesletta 14 |  |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 4050 | Sola | Signed |  | Ckm Eiendom AS (https://www.notion.so/Ckm-Eiendom-AS-311a1d8f955980138470ed0d2e9cf731?pvs=21) | Rikard |  | Solar as a Service | 235 | 2024-12-31 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | LNETT | No status | Completed |  |  |  |  | No status | TBD | Ikke søknadsplikt | Approved |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil |  |  |  |  | 119.85 | 1,212,600
Signed | Fiboveien 4, 4580 Lyngdal |  | 193.9 | 2026-06-01 | 2026-08-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 467 days (ongoing) | 467 | 🟥 467 days (ongoing) | 467 | 0.19 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 294.087794432548 | 0.294087794433 | 🟩 OK! | 165.2028 | 165,202.8 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,189,921 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109,871.2 | 0 | 0 |  | 2024 | -193.9 | 193.9 | 114.939 | 0.592774626096 | 137.339 | 22.4 | 22.4 | 114.939 | 0.592774626096 | 6.136776689015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-07-01 | 0.115523465704 | 1.19 | 0 | 5.544002062919 | 0.7082980918 | 1,074,982 | 5.544002062919 | 22.4 | 0 | 0 | 22.4 | 0 | 2026-07-01 | 0 | 0 | 0 | 0 |  | 0 | 1,074,982 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Fiboveien_4.pdf, Deployment/Tilskuddsbrev_Fiboveien_4.pdf | 5.95 |  | 20% |  |  |  | 112 | Fiboveien 4 | Termoenergi |  | Application: Successful | 250A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 4580 | Lyngdal | Signed |  | Romeid 3 AS (https://www.notion.so/Romeid-3-AS-311a1d8f9559801aa6ebcc75977917d5?pvs=21) | Rikard | 400 V | Solar as a Service | 162 | 2024-12-20 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  |  |  | No status | Yes | Ikke søknadsplikt | Approved |  |  | No status |  |  |  |  | No status | Not started |  |  | Siri |  |  |  |  | 78.142 | 996.84
Signed | Skreppestadveien 28, 3261 Larvik |  | 149 | 2026-10-01 | 2026-12-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 467 days (ongoing) | 467 | 🟥 467 days (ongoing) | 467 | 0.15 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 444.111349036403 | 0.444111349036 | 🟩 OK! | 130.077 | 130.077 |  |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,019,250 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.7 | 0 | 0 |  | 2024 | -149 | 149 | 177.4 | 1.190604026846 | 207.4 | 30 | 30 | 177.4 | 1.190604026846 | 6.840604026846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.84 | 0.201342281879 | 2026-02-01 | 0 | 5.65 | 1.391946308725 | 841.85 | 5.65 | 30 | 0 | 0 | 30 | 0 | 0.84 | 0 | 0 | 0 | 0 |  | 0 | 841.85 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Skreppestadveien_28.pdf, Deployment/Tilskuddsbrev_Skreppestadveien_28.pdf | 5.97 |  | 20% |  |  |  | 150 | Skreppestadveien 28 | Termoenergi |  | Application: Successful |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 3261 | Larvik | Signed |  |  | Rikard |  | Solar as a Service | 148 | 2024-12-20 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | LEDE | No status | Completed |  |  |  |  | No status | TBD | 28.02: Må søke | To be applied |  |  | No status |  |  |  |  | No status | Planned |  |  | Kjetil |  |  |  |  | 59.6 | 782.25
Cancelled | Gangveien 10, 3960 Stathelle |  | 838.9 |  |  |  |  | 2026-03-31 |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 455 days | 455 | 🟥 456 days (ongoing) | 456 | 0.84 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Mar |  | 0 | 4,326.832967032967 | 4.326832967033 | 🟥 SUM! | 725.6485 | 725,648.5 | 2026 - Q1 |  | 2024 - Q4 | 0 | 0 |  |  | 0 | 0 | 6,398,189 | ⌚ 1 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2024 | -838.9 | 838.9 | 1,968,709 | 2.34677434736 | 1,968,709 | 0 | 0 | 1,968,709 | 2.34677434736 | 7.626879246632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 4.43 | 0 | 2026-04-06 | 0 | 5.280104899273 | 2.34677434736 | 4,429,480 | 5.280104899273 | 0 | 0 | 0 | 0 | 0 | 4.43 | 0 | 0 | 0 | 0 |  | 0 | 4,429,480 | [9 empty] | Gangveien 10 |  |  |  |  | Alti Forvaltning AS (https://www.notion.so/Alti-Forvaltning-AS-1a8a1d8f95598018a497d9c5a7ae9ab8?pvs=21) |  | 3960 | Stathelle | Signed |  | Alti Brotorvet AS (https://www.notion.so/Alti-Brotorvet-AS-311a1d8f955980fa9424f71b045812e5?pvs=21) | Rikard | 400 V | Solar as a Service | 839 | 2024-12-31 |  |  | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) |  | Not uploaded | [5 empty] | Not started |  | No status | Completed | [6 empty] | 31.01: Venter avklaring med Alti på om de eller vi skal søke. Antageligvis blir det oss og de ønsker at vi SKAL søke. | To be applied | [8 empty] | Not interested |  |  | Kjetil |  |  |  |  | 402.68 | 4,026,800
Signed | Lasta 2, 4207 Flekkefjord |  | 121 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 407 days (ongoing) | 407 | 🟥 407 days (ongoing) | 407 | 0.12 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | -4.17 | 375.457002457002 | 0.375457002457 | 🟩 OK! | 99.704 | 99.704 |  |  | 2025 - Q1 | 0 | 0 |  |  | 0 | 0 | 926.981 | ❌ COD not set | 0 | 0 | -4.17 | 0 | 0 | 0 | 0 | 30,562.2 | 0 | 0 |  | 2025 | -121 | 121 | 156.981 | 1.297363636364 | 152.811 | 0 | 0 | 156.981 | 1.297363636364 | 7.661 | 0 | 0 | 0 | 0 | 0 | -4.17 | 4.17 | 🟩 NoCs: 0 | 0.77 | -0.034462809918 | 0.93 | 0 | 6.363636363636 | 1.262900826446 | 770 | 6.363636363636 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 |  | 0 | 770 | [9 empty] | Lasta 2 |  |  |  |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | No | 4207 | Flekkefjord | Signed | https://drive.google.com/file/d/1KvW_Dq1bcS91DWy9h4-99Y38io-Bs3No/view | Flekkefjord Næring AS (https://www.notion.so/Flekkefjord-N-ring-AS-311a1d8f9559804f9d2ce230ba4e5c9e?pvs=21) | Rikard |  | Solar as a Service | 121 | 2025-02-18 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  |  |  | Roof OK | TBD | 20.02: generell henvendelse sendt til kommunen | To be applied |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received |  |  |  |  | No status | Not started |  |  | Siri |  |  |  |  | 0 | 770
In operation (COD) | Fossumveien 70, 1359 Eiksmarka |  | 466.4 | 2025-09-04 | 2025-11-19 | 2025-09-04 | 2025-09-22 | 2025-11-19 | 466.4 | Transferred | 🟨 76 days | 76 | 🟩 18 days | 18 | 🟩 58 days | 58 | 🟨 254 days | 254 | 🟩 178 days | 178 | 0.47 | 80.347 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-11-25 | 2509 | 369.791 | 1,455.870078740158 | 1.45587007874 | 🟩 OK! | 376.160928 | 376,160.928 | 2025 - Q4 | 2025 - Q3 | 2025 - Q1 | 182.259 | 11.66 | 11.66 | 971.666666666667 | 267.879 | 2,787,152 | 2,787,152 | ⌚ 133 days | 182.259 | 267.879 | 369.791 | 182.259 | 2,787,152 | 267.879 | 267.879 | 0 | 267.879 | 2,787,152 | 2025 | 2025 | 0 | 466.4 | 267.879 | 0.574354631218 | 369.791 | 182.259 | 182.259 | 391.307 | 0.838994425386 | 6.204560463122 | 0 | 0 | 0.27 | 267.879 | 2.79 | 187.532 | 80.347 | 🟨 NoCs: 2 | 2.52 | -0.046132075472 | 2.79 | 182.259 | 5.401528730703 | 0.792862349914 | 2,502,500 | 5.365566037736 | 182.259 | 0 | 0 | 182.259 | 0 | 2.52 | 0.47 | 0 | 0 | 0 | 5.975883361921 | 16.773 | 2,519,273 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_og_tetting___lekkasjetest_til_Fossumveien_70.pdf | 3.64 |  | 25% | NTE | thing_2da477d6-8287-5d77-962f-8f16009b19ca (https://www.notion.so/thing_2da477d6-8287-5d77-962f-8f16009b19ca-27ea1d8f9559808ab0a2f011a7e70da3?pvs=21) |  | 729.036 | Fossumveien 70 |  | Yes | Applied by client | 800A | Løvenskiold-Vækerø AS (https://www.notion.so/L-venskiold-V-ker-AS-1b3a1d8f955980b8b785e75c63be99e1?pvs=21) | Yes - all PPAs | 1359 | Eiksmarka | Signed | https://drive.google.com/file/d/1Y-qQNELHBsJSetFyzyl6N17OipmDaDmz/view |  | Ole Bjørn | 230 V | Solar as a Service | 462 | 2025-03-10 | Jon Ivar Schanche (https://www.notion.so/Jon-Ivar-Schanche-224a1d8f955980b3b8efde84917998cb?pvs=21) | Innvendig trapp | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Retrofit not completed | 2026-02-25 | Not started | ELVIA | Done | Completed |  | Default | Solis 5 x 60kW inverter, 230V |  | Roof OK | Retrofit | 22.08.25: Godkjent søknad. | Approved | 7359992909430472 (https://www.notion.so/7359992909430472-1c1a1d8f955980cd959ff74113aa3aee?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | To be started |  |  | 880 x JASolar 530Wp bifacial glass/glass paneler. | Done | Not started | 03.02.26: Etterspurt signatur og snakket med Harald. Erklæring og samtykke ligger på drive klar for å sendes. |  | Siri |  |  |  |  | 363.5 | 2,139,000
In operation (COD) | Nordre Bliksrud Vei 2, 1940 Bjørkelangen |  | 343.2 | 2025-06-06 | 2025-07-24 | 2025-06-06 | 2025-06-19 | 2025-07-24 | 343.2 | Transferred | 🟩 48 days | 48 | 🟩 13 days | 13 | 🟩 35 days | 35 | 🟩 136 days | 136 | 🟩 88 days | 88 | 0.34 | 29.748 | 🟩 All good |  | 🟩 1790 days left | 💚 All good | 25 - Jul | 2506 | 166.388 | 1,223.441176470588 | 1.223441176471 | 🟩 OK! | 263.038776 | 263,038.776 | 2025 - Q3 | 2025 - Q2 | 2025 - Q1 | 0 | 8.58 |  |  | 196.136 | 1,873,636 | 1,873,636 | ⌚ 251 days | 0 | 196.136 | 166.388 | 0 | 1,873,636 | 196.136 | 196.136 | 0 | 196.136 | 1,873,636 | 2025 | 2025 | 0 | 343.2 | 196.136 | 0.571491841492 | 166.388 | 0 | 0 | 217.5 | 0.633741258741 | 5.521561771562 | 0 | 0 | 0.2 | 196.136 | 1.87 | 166.388 | 29.748 | 🟩 NoCs: 0 | 1.68 | -0.148927738927 | 1.87 | 0 | 4.887820512821 | 0.484813519814 | 1,677,500 | 4.887820512821 | 0 | 0 | 0 | 0 | 0 | 1.68 | 0.34 | 0 | 0 | 0 | 5.459312354312 | 0 | 1,677,500 | [5 empty] | NTE | thing_3fd64e64-0c25-51fa-a406-c42445a140d2 (https://www.notion.so/thing_3fd64e64-0c25-51fa-a406-c42445a140d2-24ca1d8f955980ce9b3bd5a99020665e?pvs=21) | Done |  | Nordre Bliksrud Vei 2 |  | No | Applied by client | 630A | Løvenskiold-Vækerø AS (https://www.notion.so/L-venskiold-V-ker-AS-1b3a1d8f955980b8b785e75c63be99e1?pvs=21) | Pending | 1940 | Bjørkelangen | Signed | https://drive.google.com/file/d/1fZRvNdxm9M63I-vNc0DLGhu8KkHHMe2A/view |  | Ole Bjørn | 400 V | Solar as a Service | 238 | 2025-03-10 | Jon Ivar Schanche (https://www.notion.so/Jon-Ivar-Schanche-224a1d8f955980b3b8efde84917998cb?pvs=21) | Tilkomst fra bakkeplan opp til taket via vindeltrapp. Får nøkkel i kassa. | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | Done | Høland og Setskog Elverk | Done | Completed |  | Default | 2x Sungrow SG125CX | SundayBox not working (https://www.notion.so/SundayBox-not-working-24ca1d8f955980a8be72f521c21243dd?pvs=21) | Roof OK | Yes | Ikke søknadspliktig. | Approved | 7359992891907686 (https://www.notion.so/7359992891907686-1c1a1d8f9559803cb979df8e2b82bf05?pvs=21), 7359992901796323 (https://www.notion.so/7359992901796323-23fa1d8f9559801fb2a1f8c8d589f83a?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  | ca 2021 | 528x650W Longi LR7-72HVH-650 SDM1 | Done | In operation | 03.02.26: sendt erklæring til Harald. Erklæring klar på drive (ikke behov for samtykke) | Installed | Siri |  |  |  |  | 202.5 | 1,475,000
In operation (COD) | Per Krohgs vei 2, 1065 Oslo |  | 272.55 | 2025-08-29 | 2025-11-19 | 2025-08-29 | 2025-10-03 | 2025-11-19 | 272.55 | Transferred | 🟨 82 days | 82 | 🟩 35 days | 35 | 🟩 47 days | 47 | 🟨 254 days | 254 | 🟩 172 days | 172 | 0.27 | 24.639 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-11-25 | 2510 | 230.462 | 907.330708661417 | 0.907330708661 | 🟩 OK! | 217.184193 | 217,184.193 | 2025 - Q4 | 2025 - Q3 | 2025 - Q1 | 0 | 6,813.75 | 6,813.75 | 567.8125 | 255.101 | 1,774,904 | 1,774,904 | ⌚ 133 days | 0 | 255.101 | 230.462 | 0 | 1,774,904 | 255.101 | 255.101 | 0 | 255.101 | 1,774,904 | 2025 | 2025 | 0 | 272.55 | 255.101 | 0.935978719501 | 230.462 | 0 | 0 | 157.4 | 0.577508713997 | 6.103335167859 | 0 | 0 | 0.26 | 255.101 | 1.77 | 230.462 | 24.639 | 🟨 NoCs: 1 | 1.52 | 0.268068244359 | 1.77 | 0 | 5.57623555311 | 0.845576958356 | 1,506,064 | 5.525826453862 | 0 | 0 | 0 | 0 | 0 | 1.52 | 0.27 | 0 | 0 | 0 | 6.512214272611 | 13.739 | 1,519,803 | [5 empty] | NTE | thing_7f4282c5-6d36-556a-8fbc-9f0ca37c2c7a (https://www.notion.so/thing_7f4282c5-6d36-556a-8fbc-9f0ca37c2c7a-2afa1d8f9559802e896fc7903a274a49?pvs=21) |  |  | Per Krohgs vei 2 |  | Yes | Waiting for calc | 630A (justert til 500A av Eltera under installasjonen når de byttet hele hovedsikringen) | Løvenskiold-Vækerø AS (https://www.notion.so/L-venskiold-V-ker-AS-1b3a1d8f955980b8b785e75c63be99e1?pvs=21) | Yes - all PPAs | 1065 | Oslo | Signed | https://drive.google.com/file/d/1yx7d7B7p_GdVCe7pZ2y3MF3sYxI_Alo4/view |  | Ole Bjørn | 230 V | Solar as a Service | 272.55 | 2025-03-10 | Jon Ivar Schanche (https://www.notion.so/Jon-Ivar-Schanche-224a1d8f955980b3b8efde84917998cb?pvs=21) | Stige fra terrasse i 2. etg | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Retrofit not completed | 2026-02-25 | Not started | ELVIA | Done | Completed |  | Default | Solis 3 x 60 kW, 230 V |  | Roof OK | Retrofit | Ikke søknadspliktig. | Approved | 7359992895580892 (https://www.notion.so/7359992895580892-1c1a1d8f955980199c06edd496c1222b?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Booked | To be started |  | Tekkes om før installasjonen - 2025 | 474 x Longi 575W | Done | In operation | 03.02.26: snakket med Harald og sendt erklæring + samtykke Erklæring og samtykke ligger på drive klar for å sendes. |  | Siri |  |  |  |  | 253.85 | 1,252,214
Signed | Ole Deviks vei 40, 0668 Oslo |  | 448 | 2026-04-10 | 2026-04-30 |  | 2026-04-01 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | 🟩 0 days (on-going) | 0 | 🟥 387 days (ongoing) | 387 | 🟥 387 days (ongoing) | 387 | 0.45 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2604 | -25.325 | -66.077519379845 | -0.06607751938 | 🟩 OK! | 347.41056 | 347,410.56 |  |  | 2025 - Q1 | 0 | 0 |  |  | 0 | 0 | 2,479,753 | ❌ COD not set | 0 | 0 | -25.325 | 0 | 0 | 0 | 0 | -25.572 | 0 | 0 |  | 2025 | -448 | 448 | -247 | -0.000551339286 | -25.572 | 0 | 0 | -247 | -0.000551339286 | 5.535162946429 | 0 | 0 | 0 | -247 | 2.48 | -25.572 | 25.325 | 🟩 NoCs: 0 | 2.48 | -0.056529017857 | 2.48 | 0 | 5.535714285714 | -0.057080357143 | 2,480,000 | 5.535714285714 | 0 | 0 | 0 | 0 | 0 | 2.48 | 0 | 0 | 0 | 0 |  | 0 | 2,480,000 | [6 empty] | thing_c6a780d5-9ea3-51df-a9d3-95e2d4a53ef6 (https://www.notion.so/thing_c6a780d5-9ea3-51df-a9d3-95e2d4a53ef6-27ea1d8f9559802bbf3eeea6350f374e?pvs=21) |  |  | Ole Deviks vei 40 |  | TBD | Does not qualify | 1250A | Løvenskiold-Vækerø AS (https://www.notion.so/L-venskiold-V-ker-AS-1b3a1d8f955980b8b785e75c63be99e1?pvs=21) | Yes - all PPAs | 668 | Oslo | Signed | https://drive.google.com/file/d/1SJ2vMZFsufRVs2SaWOolOsle8vcn9IeF/view |  | Ole Bjørn | 230 V | Solar as a Service | 180 | 2025-03-10 | Jon Ivar Schanche (https://www.notion.so/Jon-Ivar-Schanche-224a1d8f955980b3b8efde84917998cb?pvs=21) | Stige på nordsiden av bygget. Husk å ta med en liten stige som må brukes for å komme seg opp på den sørlige delen av taket. |  |  | Not uploaded | To be applied |  | GoO priced in APA |  |  | Not started | ELVIA | No status | Completed |  |  | 4 x Solis 75k-LV |  | Roof OK | Yes | Godkjent | Approved | 7359992903025841 (https://www.notion.so/7359992903025841-1c1a1d8f955980148ad6dd30d008a5c7?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  | Tekket om av Takmesteren november 2024. | 684 x Longi LR7-72HVH-655 SDM1 | No status | Not started | 03.02.26: sendt samtykker og erklæring til Harald. Husk at hjemmel må være overført til ODV næringseiendom før du tinglyser. Om ikke trenger vi samtykke… |  | Siri |  |  |  |  | 380 | 2,100,000
In operation (COD) | Holmaveien 19, 1339 Vøyenenga |  | 313.3 | 2025-09-01 | 2025-10-17 | 2025-09-01 | 2025-09-17 | 2025-10-17 | 313.3 | Transferred | 🟩 46 days | 46 | 🟩 16 days | 16 | 🟩 30 days | 30 | 🟨 221 days | 221 | 🟩 175 days | 175 | 0.31 | 73.22 | 🟩 All good |  | 🟩 1790 days left | 💚 All good | 25 - Oct | 2509 | 79.346 | 359.031674208145 | 0.359031674208 | 🟩 OK! | 240.595602 | 240,595.602 | 2025 - Q4 | 2025 - Q3 | 2025 - Q1 | 18.75 | 7,832.5 |  |  | 133.816 | 1,740,136 | 1,740,136 | ⌚ 166 days | 18.75 | 133.816 | 79.346 | 0 | 1,740,136 | 133.816 | 133.816 | 0 | 133.816 | 1,740,136 | 2025 | 2025 | 0 | 313.3 | 133.816 | 0.427117778487 | 79.346 | 18.75 | 18.75 | 145.739 | 0.465173954676 | 5.550555378232 | 0 | 0 | 0.13 | 133.816 | 1.74 | 79.346 | 73.22 | 🟨 NoCs: 1 | 1.61 | -0.211915097351 | 1.74 | 0 | 5.127098627514 | 0.253258857325 | 1,593,250 | 5.085381423556 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0.31 | 18.75 | 0 | 0 | 5.554216406001 | 13.07 | 1,606,320 | 2025-05-15 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Holmaveien_19.pdf | 6.24 |  | 25% | NTE | thing_763917e8-2d88-594c-9641-5a74814f964a (https://www.notion.so/thing_763917e8-2d88-594c-9641-5a74814f964a-27ea1d8f955980f4b299f6a983a68863?pvs=21) |  | 75 | Holmaveien 19 |  | Yes | Payment received | 630A justert til 500A | Løvenskiold-Vækerø AS (https://www.notion.so/L-venskiold-V-ker-AS-1b3a1d8f955980b8b785e75c63be99e1?pvs=21) | Yes - all PPAs | 1339 | Vøyenenga | Signed | https://drive.google.com/file/d/1v6vSBAKkAjqIVj5M4M9YoL5pWebxquRi/view |  | Ole Bjørn | 400 V | Solar as a Service | 313.3 | 2025-03-10 | Jon Ivar Schanche (https://www.notion.so/Jon-Ivar-Schanche-224a1d8f955980b3b8efde84917998cb?pvs=21) | Utvendig stige på østsiden av bygget. | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | Retrofit - GoO earnout | Retrofit not completed | 2026-02-25 | Not started | ELVIA | Done | Completed |  | Default | Sungrow 2 x SG125CX |  | Roof OK | Retrofit | 25.06.25: søknad sendt. | Approved | 7359992909294869 (https://www.notion.so/7359992909294869-1c1a1d8f955980589abefe329bd32cef?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | To be started |  | 2009 | 482 x Longi LR7-72HVH-650 SDM1 | Done | Not interested | 03.02.26: sendt erklæring og samtykke til Harald. Husk: sladd adresse i takleieavtale. Installasjonen er på Holmaveien 19, men samme gnr/bnr. Erklæring og samtykke ligger på drive klar for å sendes. |  | Siri |  |  |  |  | 228.25 | 1,365,000
Signed | Deliveien 10, 1540 Vestby |  | 4,347.2 | 2025-10-15 | 2026-05-29 | 2025-10-15 | 2025-10-22 |  |  | Signed APA | 🟥 168 days (ongoing) | 168 | 🟩 7 days | 7 | 🟥 161 days (ongoing) | 161 | 🟥 306 days (ongoing) | 306 | 🟩 138 days | 138 | 4.35 | 2.619 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2510 | 3,156,975.5 | 11,599.26797385621 | 11.599267973856 | 🟩 OK! | 3,569.181616 | 3,569,181.616 |  | 2025 - Q4 | 2025 - Q2 | 729,392.4 | 0 |  |  | 2,802,212.1 | 19,836,815.4 | 22,040,906 | ❌ COD not set | 729,392.4 | 2,802,212.1 | 3,156,975.5 | 810.436 | 19,836,815 | 909.478 | 909,478.4 | 354,937.6 | 3,113,569 | 19,836,815.4 |  | 2025 | -4,347.2 | 4,347.2 | 3,113,569 | 0.716224006257 | 3,549,376 | 810.436 | 810.436 | 3,113,569 | 0.716224006257 | 5.070138479941 | 0 | 2.619 | 0 | 3,113,569 | 2026-04-22 | 2,738,940 | 374.629 | 🟩 NoCs: 0 | 18.93 | 0.100250046007 | 2026-04-22 | 810.436 | 4.353914473684 | 0.816474052264 | 18,927,337 | 4.353914473684 | 810.436 | 0 | 0 | 810.436 | 0 | 18.93 | 0 | 0 | 0 | 0 |  | 0 | 18,927,337 | 2025-05-30 | Deployment/Deliveien_10_-_Sknad_30.05.2025.pdf | 2026-02-06 |  | 11.3% |  |  |  | 7,172,000 | Deliveien 10 | TermoEnergi / Nadia | Yes | Application: Successful | 3200A | Niam AS (https://www.notion.so/Niam-AS-1a8a1d8f955980ab804cd460bed4c604?pvs=21) | Yes - all PPAs | 1540 | Vestby | Signed | https://drive.google.com/file/d/16QpBKPOn7QcbFSeh6ik-NJd7nobOm11U/view |  | Johan | 400 V | Solar as a Service | 4.201 | 2025-05-30 | Christopher Olsen Martinsen (https://www.notion.so/Christopher-Olsen-Martinsen-292a1d8f955980dea22de07b51a778ce?pvs=21) | Innsiden av bygget sør på bygget via kontordelen og spiraltrapp på nordsiden | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | In progress | ELVIA | No status | Completed |  |  | 27x KACO Blueplanet 105kW |  | Roof OK | No | Ikke søknadspliktig | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 6688x650W LONGi LR7-72HVH 650Wp | Done | Not started | 07.07.25: signaturer mottatt 01.07.25, Siri: Purret på signatur og samtykke | To be installed | Kjetil |  |  | 2.619 |  | 2,127,337 | 16,800,000
In operation (COD) | Ringeriksveien 191C, 1339 Vøyenenga |  | 402.32 | 2025-10-21 | 2025-11-28 | 2025-10-21 | 2025-10-24 | 2025-11-28 | 406.6 | Transferred | 🟩 38 days | 38 | 🟩 3 days | 3 | 🟩 35 days | 35 | 🟩 182 days | 182 | 🟩 144 days | 144 | 0.4 | 46.847 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 2026-11-25 | 2510 | 626,843.4999999999 | 3,444.192307692308 | 3.444192307692 | 🟩 OK! | 313.086066 | 313,086.066 | 2025 - Q4 | 2025 - Q4 | 2025 - Q2 | 156,513.49999999994 | 10.165 | 10.165 | 847.083333333333 | 517.177 | 2,450,573 | 2,450,573 | ⌚ 124 days | 156,513.49999999994 | 517.177 | 626,843.4999999999 | 156.513 | 2,450,573 | 517.177 | 517.177 | 0 | 517.177 | 2,450,573 | 2025 | 2025 | 4.28 | 406.6 | 517.177 | 1.271955238564 | 626.843 | 156,513.49999999994 | 156,513.49999999994 | 310.747 | 0.764257255288 | 5.494996520183 | 0 | 0 | 0.52 | 517.177 | 2.45 | 470.33 | 46.847 | 🟨 NoCs: 2 | 1.93 | 0.777412690605 | 2.45 | 156,513.49999999994 | 4.755031972455 | 1.541669945893 | 1,900,000 | 4.722608868562 | 156,513.49999999994 | 0 | 0 | 156,513.49999999994 | 0 | 1.93 | 0.41 | 0 | 0 | 0 | 6.026987211018 | 33.396 | 1,933,396 | 2025-05-30 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Ringeriksveien_191C.pdf | 2026-05-06 |  | 42.028329752954% | NTE | thing_766f6bca-ff4b-52a6-a02b-44e06ed28648 (https://www.notion.so/thing_766f6bca-ff4b-52a6-a02b-44e06ed28648-294a1d8f9559809c8303c7da5f7439d3?pvs=21) |  | 372.4 | Ringeriksveien 191C |  | Yes | Payment received | 1600A | Abel Eiendomsforvaltning AS (https://www.notion.so/Abel-Eiendomsforvaltning-AS-24ea1d8f955980bfb687c0083aeaf9dd?pvs=21) | Yes - all PPAs | 1339 | Vøyenenga |  | https://drive.google.com/file/d/1ZgQsRZf8ZumRu98WV1QYs9QvxHWTSDTW/view |  | Ole Bjørn | 400 V | Solar as a Service | 413.09 | 2025-05-30 |  |  | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Kristoffer Liset (https://www.notion.so/Kristoffer-Liset-27fa1d8f955980aab65aefd37f755467?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Retrofit not completed | 2026-02-25 | Done | ELVIA | Done | Completed |  | Default | 2 x Solis S6-GC125K |  | In process | Retrofit | Godkjent | Approved | 7359992930268891 (https://www.notion.so/7359992930268891-28ca1d8f955980d4bb18edd6a7ee5942?pvs=21), 7359992906553440 (https://www.notion.so/7359992906553440-2bda1d8f955980fc9cb6d840aa3d37c4?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Booked | To be started |  |  | 760 x JA Solar 535 Wp Bifacial | Done | In operation | 16.03.26: Joakim purrer i morgen. 20.01.26: sendt erklæring til kunde |  | Siri |  |  |  |  | 125 | 1,775,000
Signed | Mjåvannssløyfen 244, 4628 Kristiansand |  | 1,447.71 | 2026-04-30 | 2026-06-30 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟥 321 days (ongoing) | 321 | 🟥 321 days (ongoing) | 321 | 1.45 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -20.899 | 4,427.280373831775 | 4.427280373832 | 🟩 OK! | 1,292.80503 | 1,292,805.03 |  |  | 2025 - Q2 | 0 | 0 |  |  | 0 | 0 | 8,438,056 | ❌ COD not set | 0 | 0 | -20.899 | 0 | 0 | 0 | 0 | 1,279,041.3 | 0 | 0 |  | 2025 | -1,447.71 | 1,447.71 | 1,285,056 | 0.887647387944 | 1,421,157 | 157 | 157 | 1,285,056 | 0.887647387944 | 5.828554061242 | 0 | 0 | 0 | 0 | 0 | -20.899 | 20.899 | 🟩 NoCs: 0 | 7.15 | 0.094011231531 | 8.44 | 0 | 4.940906673298 | 0.981658619475 | 7,153,000 | 4.940906673298 | 157 | 0 | 0 | 157 | 0 | 7.15 | 0 | 0 | 0 | 0 |  | 0 | 7,153,000 | 2025-05-21 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Mjvannsslyfen_244.pdf | 2026-03-06 |  | 20% |  |  |  | 785 | Mjåvannssløyfen 244 | Løyning / Marianne | Yes | Application: Successful | 2200A (stilt ned fra 2500) | S.O.G. Eiendom AS (https://www.notion.so/S-O-G-Eiendom-AS-24ea1d8f955980ea8a9fc3033d44a28a?pvs=21) | Pending | 4628 | Kristiansand | Signed |  |  | Ole Bjørn | 400 V | Solar as a Service | 1,147.95 | 2025-05-15 |  |  | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) |  | Not uploaded | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  | 8x 125 kW Sungrow SG125CX-P2 |  | Roof OK | No | Godkjent | Approved | 5706567290642492 (https://www.notion.so/5706567290642492-2e0a1d8f95598041857dc48221efe400?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 2706 stk 535 JaSolar, JAM60D42 LB | No status |  |  |  | Siri |  |  |  |  | 750 | 6,403,000
Signed | , | [9 empty] | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2024-11-22 | Deployment/Vikaveien_421_(2119)_-_Energieffektivisering_med_solcelleanlegg.pdf |  |  | 0% |  |  |  | 270.4 |  |  |  | Application: Successful | [17 empty] | Not uploaded | [5 empty] | Not started | [8 empty] | TBD
In operation (COD) | Almedalsveien 6, 1391 Vollen |  | 102.38 | 2025-04-24 | 2025-06-30 | 2025-04-24 | 2025-05-21 | 2025-06-30 | 101.85 | Transferred | 🟨 67 days | 67 | 🟩 27 days | 27 | 🟩 40 days | 40 | 🟥 370 days | 370 | 🟥 303 days | 303 | 0.1 | 28.015 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Jun | 2505 | -55.053 | -148.791891891892 | -0.148791891892 | 🟩 OK! | 83.396817 | 83,396.817 | 2025 - Q2 | 2025 - Q2 | 2024 - Q2 | 0 | 2,546.25 | 2,546.25 | 1,273.125 | -27.038 | 581.581 | 581.581 | ⌚ 275 days | 0 | -27.038 | -55.053 | 49.996 | 581.581 | -27.038 | -27.038 | 0 | -27.038 | 581.581 | 2025 | 2024 | -0.53 | 101.85 | -27.038 | -0.265468826706 | -55.053 | 4.996 | 0 | -24.012 | -0.235758468336 | 5.710168001563 | 0 | 0 | -0.03 | -27.038 | 0.58 | -18.17 | 28.015 | 🟩 NoCs: 0 | 0.61 | -0.304771723122 | 0.58 | 49.996 | 5.975640648012 | -0.540530191458 | 608.619 | 5.944705997265 | 4.996 | 45 | 0 | 49.996 | 36.883 | 0.61 | 0.1 | 0 | 0 | 36.883 | 5.710171821306 | 0 | 608.619 | 2025-03-20 | Deployment/Energieffektivisering_med_solcelleanlegg_og_tetting___lekkasjetest_til_Almedalsveien_6.pdf | 7 |  | 20% | NTE | thing_a70abf10-ec88-541c-82a9-996d95b54aae (https://www.notion.so/thing_a70abf10-ec88-541c-82a9-996d95b54aae-209a1d8f95598018bd13d2dba23e9a12?pvs=21) | Not started | 24.98 | Almedalsveien 6 |  | No | Cancelled | Maxbo: 710A E-motive: 250A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21), E-motive Technology AS (https://www.notion.so/E-motive-Technology-AS-22aa1d8f9559805b87aaf38d2cac348e?pvs=21) | Yes - all PPAs | 1391 | Vollen | Signed | https://drive.google.com/file/d/1I1fn5cYLmv6GiHm8wKENuUwUmjSAW7Wx/view |  | Rikard | 230 V | Solar as a Service | 280 | 2024-06-25 |  | Må leie lift | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Torgeir Borgen (https://www.notion.so/Torgeir-Borgen-1a5a1d8f95598055ad3feee627e5cdb1?pvs=21), Jørn Sikkeland (https://www.notion.so/J-rn-Sikkeland-22aa1d8f955980d38e1becfd11a1974c?pvs=21) | Uploaded FDV | Approved |  | Retrofit - GoO earnout | Retrofit not completed | 2025-09-17 | Done | ELVIA | Done | Completed |  | Default | 1x Solis 60K-LV-230V | No production data registered on meter (https://www.notion.so/No-production-data-registered-on-meter-249a1d8f955980bfac9bfbb1b876aac5?pvs=21) | Roof OK | Retrofit | 15.08.25: Ferdigattest godkjent | Approved | 7359992904978764 (https://www.notion.so/7359992904978764-11aa1d8f95598066b3dff76377463adb?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | To be started | Asfaltpapp | Skal legges nytt tak | 194x525W JA solar JAM60D42 LB | Done | Not interested | Erklæring + samtykke klar på drive. Trenger samtykke fra SPAREBANK 1 SØR-NORGE ASA, org nr. 937 895 321 | Installed | Kjetil |  |  |  |  | 47.5 | 561.119
In operation (COD) | Vollaveien 17, 0668 Oslo |  | 56.115 | 2024-05-30 | 2025-07-08 | 2024-05-30 | 2025-02-24 | 2025-07-08 | 56.115 | N/A | 🟥 404 days | 404 | 🟥 270 days | 270 | 🟥 134 days | 134 | 🟥 686 days | 686 | 🟨 282 days | 282 | 0.06 | 5.178 | 🟩 All good | 50 | ❌ End date missing | ❌ Missing | 25 - Jul | 2502 | 3 | 0.004373177843 | 0.000004373178 | 🟩 OK! | 43.99416 | 43,994.16 | 2025 - Q3 | 2024 - Q2 | 2023 - Q3 | 0 | 2,805.75 | 2,805.75 | 1,169.0625 | 5.181 | 462.774 | 462.774 | ⌚ 267 days | 0 | 5.181 | 3 | 0 | 462.774 | 5.181 | 5.181 | 0 | 5.181 | 462.774 | 2025 | 2023 | 0 | 56.115 | 5.181 | 0.092328254477 | 3 | 0 | 0 | 27.769 | 0.494858772164 | 8.246885859396 | 0 | 0 | 0.01 | 5.181 | 0.46 | 3 | 5.178 | 🟥 NoCs: 4 | 0.46 | -0.494805310523 | 0.46 | 0 | 8.154557604918 | 0.000053461641 | 435.005 | 7.752027087232 | 0 | 0 | 0 | 0 | 0 | 0.46 | 0.06 | 0 | 0 | 0 | 8.246885859396 | 22,588.2575 | 457.593 | [5 empty] | Premium | thing_b002b186-1995-5e60-b697-2d0aab2d10ac (https://www.notion.so/thing_b002b186-1995-5e60-b697-2d0aab2d10ac-1eaa1d8f95598059b982d40911865a69?pvs=21) |  |  | Vollaveien 17 |  |  |  | 1600/2000A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 374 | 2023-08-22 | Henning Kolstad (https://www.notion.so/Henning-Kolstad-1a5a1d8f9559805691c8edea660e4ba0?pvs=21) | Ingen tilkomst. Må ha lift ellet stillas | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Andrii Petrychenko (https://www.notion.so/Andrii-Petrychenko-1aba1d8f955980d1838fec488c9647d3?pvs=21) | N/A | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 1x Solis 50K-LV-5G |  | Roof OK | No | 22.09.2025: Søkt om ferdigattest. | Approved | 7359992902714487 (https://www.notion.so/7359992902714487-2e0a1d8f9559805a89add1cb3fe481da?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp og PVC | 1993-2003 | 129x435W LONGi LR5-54HTB | Done | Not started |  | Installed | Kjetil |  |  |  |  | 74.844 | 360.161
In operation (COD) | Vollaveien 17, 0668 Oslo |  | 212.28 | 2024-05-30 | 2025-07-08 | 2024-05-30 | 2025-02-24 | 2025-07-08 | 212.28 | N/A | 🟥 404 days | 404 | 🟥 270 days | 270 | 🟥 134 days | 134 | 🟥 686 days | 686 | 🟨 282 days | 282 | 0.21 | 5.178 | 🟩 All good | 50 | ❌ End date missing | ❌ Missing | 25 - Jul | 2502 | 14.417 | 21.016034985423 | 0.021016034985 | 🟩 OK! | 166.42752 | 166,427.52 | 2025 - Q3 | 2024 - Q2 | 2023 - Q3 | 0 | 10.614 | 10.614 | 4,422.5 | 19.595 | 1,750,650 | 1,750,650 | ⌚ 267 days | 0 | 19.595 | 14.417 | 0 | 1,750,650 | 19.595 | 19.595 | 0 | 19.595 | 1,750,650 | 2025 | 2023 | 0 | 212.28 | 19.595 | 0.092307329942 | 14.417 | 0 | 0 | 105.045 | 0.494841718485 | 8.246890898813 | 0 | 0 | 0.02 | 19.595 | 1.75 | 14.417 | 5.178 | 🟥 NoCs: 4 | 1.73 | -0.426926700584 | 1.75 | 0 | 8.154583568871 | 0.067915017901 | 1,645,605 | 7.752049180328 | 0 | 0 | 0 | 0 | 0 | 1.73 | 0.21 | 0 | 0 | 0 | 8.246890898813 | 85,450.169 | 1,731,055 | [5 empty] | Premium | thing_16ffe552-4e38-5d0b-b7ac-66f597668f45 (https://www.notion.so/thing_16ffe552-4e38-5d0b-b7ac-66f597668f45-24fa1d8f95598038b3e8f7be15ba5f89?pvs=21) |  |  | Vollaveien 17 |  |  |  | 1600/2000A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 374 | 2023-08-22 | Henning Kolstad (https://www.notion.so/Henning-Kolstad-1a5a1d8f9559805691c8edea660e4ba0?pvs=21) | Fastmontert stige med ryggsøyle fra bakkeplan både øst og vest på fasade | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Andrii Petrychenko (https://www.notion.so/Andrii-Petrychenko-1aba1d8f955980d1838fec488c9647d3?pvs=21) | N/A | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 2x Solis 50K-LV-5G, 1x Growatt MAX35KTL3-XL | No communication (https://www.notion.so/No-communication-23fa1d8f955980f79fa6d093eb0a6871?pvs=21) | Roof OK | No | 22.09.2025: Søkt om ferdigattest. | Approved | 7359992902714487 (https://www.notion.so/7359992902714487-2e0a1d8f9559805a89add1cb3fe481da?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp og PVC | 1993-2003 | 366x580W Tongwei TWMND-72HD | Done | Not started |  | Installed | Kjetil |  |  |  |  | 283.13 | 1,362,475
In operation (COD) | Vollaveien 20A-20B, 0668 Oslo |  | 256 | 2023-12-04 | 2024-05-27 | 2023-12-04 | 2023-12-08 | 2024-05-27 | 258.56 | N/A | 🟥 175 days | 175 | 🟩 4 days | 4 | 🟥 171 days | 171 | 🟨 278 days | 278 | 🟩 103 days | 103 | 0.26 | 0 | 🟩 All good | 51.55 | ❌ End date missing | ❌ Missing | 24 - May | 2312 | 0 | 70.093525179856 | 0.07009352518 | 🟥 SUM! | 202.71104 | 202,711.04 | 2024 - Q2 | 2023 - Q4 | 2023 - Q3 | 0 | 12.928 | 13,328.768 | 13,328.768 | 0 | 0 | 2,204,160 | ⌚ 674 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2023 | 2.56 | 258.56 | 19.486 | 0.07536355198 | 19.486 | 0 | 0 | 19.486 | 0.07536355198 | 8.61 | 0 | 0 | 0.02 | 19.486 | 2026-02-02 | 19.486 | 0 | 🟩 NoCs: 0 | 2.18 | 0 | 2026-02-02 | 0 | 8.449388923267 | 0.075363551980 | 2,184,674 | 8.5338828125 | 0 | 0 | 0 | 0 | 0 | 2.18 | 0.26 | 0 | 0 | 0 | 8.524752475248 | 0 | 2,184,674 | [5 empty] | Premium | thing_0ffaf45d-c4ff-5cfb-868e-1d9ed6669063 (https://www.notion.so/thing_0ffaf45d-c4ff-5cfb-868e-1d9ed6669063-717718517e26478fb0e7c68a4800dfbc?pvs=21) | Done |  | Vollaveien 20A-20B |  |  |  | 600A | Eiendomsspar AS (https://www.notion.so/Eiendomsspar-AS-1a5a1d8f9559808b8ce3e9333b30f6af?pvs=21) | Not relevant | 668 | Oslo | Signed |  |  | Rikard | 230 V | Project Sales | 750 | 2023-08-23 | Kristoffer Selen (https://www.notion.so/Kristoffer-Selen-1a5a1d8f955980208df3c7ff3814340e?pvs=21) | Trapp opp til tak. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | Vollaveien 20B: 3x Solis-60K-LV-5G | Dead display and no communication (https://www.notion.so/Dead-display-and-no-communication-3dcd263163244ceda65da5bc500c13d3?pvs=21), Plant is not behind meter (https://www.notion.so/Plant-is-not-behind-meter-1dfa1d8f95598092a325f16007b3f7f6?pvs=21) | Roof OK | No |  | Not applicable | 7359992903025117 (https://www.notion.so/7359992903025117-a5ee1c3ca7014f919e0ddd31caaaf203?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | Papp | 1993-2023 | Vollaveien 20A: 512x505W LONGi Vollaveien 20B: 512x505W LONGi | Done | Not started |  | Installed | Kjetil |  |  |  |  | 180 | 2,004,674
Signed | Semsvegen 46A, 3676 Notodden |  | 302.6 | 2026-02-19 | 2026-05-29 | 2026-02-19 | 2026-05-04 |  |  | To be approved | 🟩 41 days (on-going) | 41 | 🟥 74 days | 74 | ❌ ERROR / Check Date | -32 | 🟥 313 days (ongoing) | 313 | 🟨 272 days | 272 | 0.3 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2605 | -3.215 | 921.760383386582 | 0.921760383387 | 🟩 OK! | 225.924186 | 225,924.186 |  | 2026 - Q1 | 2025 - Q2 | 0 | 0 |  |  | 0 | 0 | 1,814,526 | ❌ COD not set | 0 | 0 | -3.215 | 0 | 0 | 0 | 0 | 288.511 | 0 | 0 |  | 2025 | -302.6 | 302.6 | 256.526 | 0.847739590218 | 288.511 | 35.2 | 35.2 | 156.23 | 0.516292134831 | 5.665003304693 | 0 | 0 | 0 | 256.526 | 1.81 | 253.311 | 3.215 | 🟩 NoCs: 0 | 1.56 | 0.437148050232 | 1.81 | 0 | 5.148711169861 | 0.953440185063 | 1,558,000 | 5.148711169861 | 35.2 | 0 | 0 | 35.2 | 0 | 1.56 | 0 | 0 | 0 | 0 |  | 0 | 1,558,000 | 2025-09-22 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Semsvegen_46A.pdf | 5 |  | 20% |  |  | Not started | 176 | Semsvegen 46A | TermoEnergi / Piotr | Yes | Application: Successful | 630A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Yes - all PPAs | 3676 | Notodden | Signed | https://drive.google.com/file/d/1XgmQ32_0EgQxGJeNqhclnbtFeyqY8rSZ/view | Semsvegen 46 AS (https://www.notion.so/Semsvegen-46-AS-311a1d8f95598041af8eeedd6e7e4938?pvs=21) | Rikard | 400 V | Solar as a Service | 295 | 2025-05-23 |  | Ingen tilkomst til taket. | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | In progress | Everket AS | No status | Completed |  |  | 2x Sungrow 125 kW |  | Roof OK | Yes |  | Not applicable |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 462x650W LONGi LR7-72HVH-650M | No status | Not started |  | Sent | Kjetil |  |  |  |  | 0 | 1,558,000
In operation (COD) | Semsvegen 46B, 3676 Notodden |  | 184 | 2025-09-24 | 2026-03-27 | 2025-09-24 | 2025-11-24 | 2026-03-27 |  | Signed APA | 🟥 184 days | 184 | 🟥 61 days | 61 | 🟥 123 days | 123 | 🟥 308 days | 308 | 🟩 124 days | 124 | 0.18 | 3.215 | 🟩 All good |  | ❌ End date missing | ❌ Missing | 26 - Mar | 2511 | 194,485.3 | 702.766233766234 | 0.702766233766 | 🟩 OK! | 137.54368 | 137,543.68 | 2026 - Q1 | 2025 - Q3 | 2025 - Q2 | 23.04 | 0 |  |  | 174,660.3 | 957,281.4 | 1,063,646 | ⌚ 5 days | 23.04 | 174,660.3 | 194,485.3 | 25.6 | 957.281 | 87.702 | 87,702.4 | 21,645.2 | 194.067 | 957,281.4 | 2026 | 2025 | -184 | 184 | 194.067 | 1.054711956522 | 216.452 | 25.6 | 25.6 | 194.067 | 1.054711956522 | 5.780684782609 | 0 | 0 | 0.19 | 194.067 | 2026-06-01 | 190.852 | 3.215 | 🟩 NoCs: 0 | 0.87 | 0.121657608695 | 2026-06-01 | 25.6 | 4.725972826087 | 1.176369565217 | 869.579 | 4.725972826087 | 25.6 | 0 | 0 | 25.6 | 0 | 0.87 | 0 | 0 | 0 | 0 |  | 0 | 869.579 | 2025-09-22 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Semsvegen_46B.pdf | 5 |  | 20% |  | thing_6fcaa5d3-817f-5ba7-8572-5e12d153cb13 (https://www.notion.so/thing_6fcaa5d3-817f-5ba7-8572-5e12d153cb13-2f5a1d8f955980ff81d8def1ff300e07?pvs=21) | Not started | 128 | Semsvegen 46B | TermoEnergi / Piotr | Yes | Application: Successful | 160A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21), S.O.G. Eiendom AS (https://www.notion.so/S-O-G-Eiendom-AS-24ea1d8f955980ea8a9fc3033d44a28a?pvs=21) | Yes - all PPAs | 3676 | Notodden | Signed | https://drive.google.com/file/d/1k9bPoZM7A3sENSi4RraPXVnWkU8Y8axz/view |  | Rikard | 400 V | Solar as a Service | 154 | 2025-05-23 |  |  | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | Done | Everket AS | No status | Completed |  | Default | 1x Solis S6-GC110 |  | Roof OK | Yes |  | Not applicable |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 320x575W LONGi | Done | Not started |  | Installed | Kjetil |  |  |  |  | 75 | 794.579
In operation (COD) | Hegnasletta 6, 3217 Sandefjord |  | 192.6 | 2025-09-30 | 2025-12-17 | 2025-09-30 | 2025-11-21 | 2025-12-17 | 190.8 | Transferred | 🟨 78 days | 78 | 🟨 52 days | 52 | 🟩 26 days | 26 | 🟩 197 days | 197 | 🟩 119 days | 119 | 0.19 | 11.656 | 🟩 All good | 25 | 🟩 1790 days left | 💚 All good | 25 - Dec | 2511 | 157.498 | 799.482233502538 | 0.799482233503 | 🟩 OK! | 168.6672 | 168,667.2 | 2025 - Q4 | 2025 - Q3 | 2025 - Q2 | 27.76 | 4.77 | 4.77 | 0 | 141.394 | 1,156,394 | 1,156,394 | ⌚ 105 days | 27.76 | 141.394 | 157.498 | 0 | 1,156,394 | 141.394 | 141.394 | 0 | 141.394 | 1,156,394 | 2025 | 2025 | -1.8 | 190.8 | 141.394 | 0.74105870021 | 157.498 | 27.76 | 27.76 | 146.81 | 0.769444444444 | 6.058203530633 | 0 | 0 | 0.14 | 141.394 | 1.16 | 157.498 | 11.656 | 🟨 NoCs: 1 | 2026-01-01 | 0.056016771489 | 1.16 | 0 | 5.319706498952 | 0.825461215933 | 1,020,000 | 5.295950155763 | 0 | 0 | 0 | 0 | 0 | 2026-01-01 | 0.19 | 27.76 | 0 | 0 | 6.060765199161 | -5 | 1,015,000 | 2025-09-29 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Hegnasletta_6.pdf | 5 |  | 20% | NTE | thing_6b1dc255-65d0-504d-acb9-171198210067 (https://www.notion.so/thing_6b1dc255-65d0-504d-acb9-171198210067-2a4a1d8f955980c09bdbd82c7b55cd9f?pvs=21) | N/A | 138.8 | Hegnasletta 6 | TermoEnergi / Piotr | Yes | Payment received | 320A | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Not relevant | 3217 | Sandefjord | Signed | https://drive.google.com/file/d/1_mdZog0O_-DVmVOlIOuKUpFBCsa-eyj5/view |  | Rikard | 230 V | Solar as a Service | 254 | 2025-06-03 | Kim Andre Johansen (https://www.notion.so/Kim-Andre-Johansen-1e3a1d8f9559805fb8e3f75f67b4bd0d?pvs=21) | Andre etasje via teknisk rom. | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Atle Doksrud (https://www.notion.so/Atle-Doksrud-1a5a1d8f955980cd9307ee28464c98ec?pvs=21) | Uploaded FDV | Approved | 2031-02-25 | GoO priced in APA | Not relevant | 2026-02-25 | In progress | LEDE | Done | Completed |  | Default | 1x125 kW Growatt TN-nett |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 7359992936306023 (https://www.notion.so/7359992936306023-2d1a1d8f9559807d8e4cd85992ae1b6d?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 360x530W JA Solar Premium glass-glass | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 195 | 825
In operation (COD) | Henrik Bulls veg 100, 2052 Jessheim |  | 442.05 | 2025-06-18 | 2025-07-30 | 2025-06-18 | 2025-06-30 | 2025-07-30 | 442.05 | N/A | 🟩 42 days | 42 | 🟩 12 days | 12 | 🟩 30 days | 30 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.44 | 0 | 🟩 All good | 40 | ❌ End date missing | ❌ Missing | 25 - Jul | 2506 | 274.15 |  | 0 | 🟩 OK! | 351.42975 | 351,429.75 | 2025 - Q3 | 2025 - Q2 |  | 0 | 17.682 | 17.682 | 5,893.999999999999 | 274.15 | 2,336,000 | 2,336,000 | ⌚ 245 days | 0 | 274.15 | 274.15 | 0 | 2,336,000 | 274.15 | 274.15 | 0 | 274.15 | 2,336,000 | 2025 |  | 0 | 442.05 | 274.15 | 0.620178712815 | 274.15 | 0 | 0 | 274.15 | 0.620178712815 | 5.28447008257 | 0 | 0 | 0.27 | 274.15 | 2.34 | 274.15 | 0 | 🟩 NoCs: 0 | 2026-06-02 | 0 | 2.34 | 0 | 4.664291369755 | 0.620178712815 | 2,061,850 | 4.664291369755 | 0 | 0 | 0 | 0 | 0 | 2026-06-02 | 0.44 | 0 | 0 | 0 | 5.28447008257 | 0 | 2,061,850 | [5 empty] | Smart | thing_4f1f61ce-82eb-5576-b388-80d442f084cc (https://www.notion.so/thing_4f1f61ce-82eb-5576-b388-80d442f084cc-20aa1d8f955980e5aef4fe86c7a39d54?pvs=21) |  |  | Henrik Bulls veg 100 |  |  | Applied by client | 800A | Leto Eiendom AS (https://www.notion.so/Leto-Eiendom-AS-1a8a1d8f955980679cdcdef69a253aef?pvs=21) | Not relevant | 2052 | Jessheim |  |  |  | Ole Bjørn | 400 V | Project Sales | 442.05 |  | Anders Rekdal (https://www.notion.so/Anders-Rekdal-216a1d8f9559807f8213e244c753755f?pvs=21) | Fastmontert stige fra bakkeplan til taket på nordsiden av bygget. Står låst men Leto Eiendom, Bohus og Meny har nøkkel. | Grønn Strøm AS (https://www.notion.so/Gr-nn-Str-m-AS-1a4a1d8f95598037820ad89f5dc7b136?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | ELVIA | Done | Completed |  |  | 2x Sungrow 125kW, 1x 40kW Sungrow |  | Roof OK | No | Trond Ola har bekreftet skriftlig at det IKKE er ønskelig at vi søker | Not applicable | 7359992892900112 (https://www.notion.so/7359992892900112-218a1d8f955980a7b6e9c92f4938ccf1?pvs=21), 7359992940974881 (https://www.notion.so/7359992940974881-245a1d8f9559802080bfcd0cab9b0c38?pvs=21) |  | No status | Not relevant |  |  | 842x525W JA Solar JAM60D42-525LB | Done | Not interested |  | Delivered to installer | Kjetil |  |  |  |  | 389.85 | 1,672,000
Signed | , |  | 371.45 | 2026-10-01 | 2026-12-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟨 272 days (ongoing) | 272 | 🟨 272 days (ongoing) | 272 | 0.37 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 1,332.849264705883 | 1.332849264706 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q3 | 0 | 0 |  |  | 0 | 0 | 2,063,535 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.507 | 0 | 0 |  | 2025 | -371.45 | 371.45 | 197.535 | 0.531794319558 | 362.535 | 165 | 165 | 197.535 | 0.531794319558 | 5.555350652847 | 0 | 0 | 0 | 0 | 0 | 165 | 0 | 🟩 NoCs: 0 | 1.87 | 0.444205142012 | 2026-06-02 | 0 | 5.023556333288 | 0.97599946157 | 1,866,000 | 5.023556333288 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0 | 165 | 0 | 0 |  | 0 | 1,866,000 | 2025-10-03 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Jeksleveien_120.pdf | 2026-07-05 |  | 100% |  |  |  | 165 |  |  |  | Application: Successful |  | Bulk Industrial Real Estate AS (https://www.notion.so/Bulk-Industrial-Real-Estate-AS-1a8a1d8f9559805ca7cbd0938f7b649d?pvs=21) | [6 empty] | Jonas |  | Solar as a Service | 371 | 2025-07-03 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Not completed | [5 empty] | TBD |  |  |  |  | No status | [8 empty] | Kjetil |  |  |  |  | 0 | 1,866,000
In operation (COD) | Gaupeveien 21, 1914 Ytre Enebakk |  | 273.48 | 2025-08-15 | 2025-12-12 | 2025-08-15 | 2025-09-10 | 2025-12-12 | 273.48 | N/A | 🟨 119 days | 119 | 🟩 26 days | 26 | 🟨 93 days | 93 | 🟩 123 days | 123 | 🟩 4 days | 4 | 0.27 | 0 | 🟩 All good | 60 | ❌ End date missing | ❌ Missing | 25 - Dec | 2509 | 205.11 | 1,667.560975609756 | 1.66756097561 | 🟩 OK! | 219.05748 | 219,057.48 | 2025 - Q4 | 2025 - Q3 | 2025 - Q3 | 0 | 16,408.8 | 16,408.8 | 0 | 205.11 | 1,571,110 | 1,571,110 | ⌚ 110 days | 0 | 205.11 | 205.11 | 0 | 1,571,110 | 205.11 | 205.11 | 0 | 205.11 | 1,571,110 | 2025 | 2025 | 0 | 273.48 | 205.11 | 0.75 | 205.11 | 0 | 0 | 205.11 | 0.75 | 5.744880795671 | 0 | 0 | 0.21 | 205.11 | 1.57 | 205.11 | 0 | 🟩 NoCs: 0 | 1.37 | 0 | 1.57 | 0 | 4.994880795671 | 0.75 | 1,366,000 | 4.994880795671 | 0 | 0 | 0 | 0 | 0 | 1.37 | 0.27 | 0 | 0 | 0 | 5.744880795671 | 0 | 1,366,000 | [5 empty] | Smart | thing_13c5f7d1-510c-5d2c-8a22-5f823352f23f (https://www.notion.so/thing_13c5f7d1-510c-5d2c-8a22-5f823352f23f-281a1d8f955980f7adc9d5ceff404601?pvs=21) |  |  | Gaupeveien 21 |  | Yes | Applied by client | Stor nok | Clausen Eiendom AS (https://www.notion.so/Clausen-Eiendom-AS-24fa1d8f9559806d9fb0df10067c181c?pvs=21) | Not relevant | 1914 | Ytre Enebakk | Signed |  |  | Ole Bjørn | 400 V | Project Sales | 273.48 | 2025-08-11 | Anders Rekdal (https://www.notion.so/Anders-Rekdal-216a1d8f9559807f8213e244c753755f?pvs=21) |  | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Not relevant |  |  |  |  | Done | NORGESNETT | Done | Completed |  |  | 1x Sungrow 125 kW, 1x Sungrow 50 kW |  | Roof OK | Yes | Ferdigattest OK | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 516x530W JA Solar | Not relevant | Not interested |  | Installed | Kjetil |  |  |  |  | 0 | 1,366,000
In operation (COD) | Johan Follestads vei 7, 3474 Åros |  | 144 | 2023-06-15 | 2023-10-13 | 2023-06-15 | 2023-07-10 | 2023-10-13 | 144 | Transferred | 🟨 120 days | 120 | 🟩 25 days | 25 | 🟨 95 days | 95 | 🟥 378 days | 378 | 🟨 258 days | 258 | 0.14 | 0 | 🟩 All good | 25 | 🟩 1019 days left | 💚 All good | 23 - Oct | 2307 | 0 | 902.116402116402 | 0.902116402116 | 🟥 SUM! | 118.08 | 118.08 | 2023 - Q4 | 2023 - Q2 | 2022 - Q3 | 0 | 3.6 | 3.6 | 3.6 | 0 | 0 | 1,219,258 | ⌚ 901 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 2022 | 0 | 144 | 341 | 2.368055555556 | 341 | 0 | 0 | 341 | 2.368055555556 | 8.467069444444 | 0 | 0 | 0.34 | 341 | 1.22 | 361.155 | 0 | 🟩 NoCs: 0 | 0.88 | 0 | 1.22 | 0 | 6.099013888889 | 2.368055555556 | 878.258 | 6.099013888889 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0.14 | 0 | 20.155 | 0 | 8.467069444444 | 0 | 878.258 | [5 empty] | NTE | thing_e59e7cc9-8b19-52d5-8279-5f86fe48d4c1 (https://www.notion.so/thing_e59e7cc9-8b19-52d5-8279-5f86fe48d4c1-226a1d8f955980679df5d741c4952e16?pvs=21), thing_5e794ff7-2dc9-54c5-b04e-b82870bb78a5 (https://www.notion.so/thing_5e794ff7-2dc9-54c5-b04e-b82870bb78a5-226a1d8f955980d3a8e6f2971779637c?pvs=21) | Done |  | Johan Follestads vei 7 |  |  | Does not qualify |  | Xania Group AS (https://www.notion.so/Xania-Group-AS-1a8a1d8f955980b8a252c1e587125d45?pvs=21) | Yes - all PPAs | 3474 | Åros | Signed |  |  | Jonas | 400 V | Solar as a Service | 144 | 2022-09-30 | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | Ingen stige eller tilkomst. Verken gårdeier eller leietaker vil dele på kostnad med oss om å sette opp permanent stige. Må leie lift der gårdeier kan gi oss tilbud. | Solcellespesialisten AS (https://www.notion.so/Solcellespesialisten-AS-1a5a1d8f9559803f8716eb523392f5dd?pvs=21) | Reber Saley (https://www.notion.so/Reber-Saley-1a5a1d8f9559805ba052e4412c56e887?pvs=21) | N/A | Approved | 2029-01-15 | Retrofit - GoO earnout | Applied |  | Done | NORGESNETT | Done | Completed | JF7 2024 (https://www.notion.so/JF7-2024-188a1d8f955980f7a04bf9c16ef8eb30?pvs=21), JF7 2025 (https://www.notion.so/JF7-2025-213a1d8f955980339006e0f716fae369?pvs=21) | Default | 1x Solis S5-GC110K-5G | No data from Solar log (https://www.notion.so/No-data-from-Solar-log-86c6f5f480fd4c52a8428b4ee8075c66?pvs=21), Strange production curve (https://www.notion.so/Strange-production-curve-e74918f92ece4343bf75b45679cc83f7?pvs=21), No ‘plusskunde’ on AMS (https://www.notion.so/No-plusskunde-on-AMS-bd08900697c74709a83e0193889cd0a2?pvs=21), Three broken modules (https://www.notion.so/Three-broken-modules-1e7a1d8f955980689f59fe9fa4c21c59?pvs=21), «Tilsynssak» (https://www.notion.so/Tilsynssak-28da1d8f955980debac4c854199c0933?pvs=21) | Roof OK | Retrofit | Ferdigattest sendt. | Approved | 5706567331885062 (https://www.notion.so/5706567331885062-11aa1d8f9559803bb381f5e7f30764cd?pvs=21), 5706567337624177 (https://www.notion.so/5706567337624177-250a1d8f955980628840d729987ed451?pvs=21) |  |  | Done | Papp | 2023 | 288x500W LONGi LR5-66HPH-500M | Done | Not interested |  | Installed | Kjetil |  |  |  |  | 60 | 818.258
In operation (COD) | Majorvegen 8, 3040 Nannestad |  | 1.425 | 2025-10-09 | 2025-12-09 | 2025-10-09 | 2025-10-20 | 2025-12-09 | 1,424.71 | Transferred | 🟨 61 days | 61 | 🟩 11 days | 11 | 🟩 50 days | 50 | 🟩 109 days | 109 | 🟩 48 days | 48 | 1.43 | 40.59 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Dec | 2510 | 2,052,058 | 18,826.22018348624 | 18.826220183486 | 🟩 OK! | 1,133.5420173 | 1,133,542.0173 | 2025 - Q4 | 2025 - Q4 | 2025 - Q3 | 358.033 | 35,617.75 | 35,617.75 | 0 | 1,734,615 | 8,554,295 | 8,554,295 | ⌚ 113 days | 358.033 | 1,734,615 | 2,052,058 | 0 | 8,554,295 | 1,734,615 | 1,734,615 | 0 | 1,734,615 | 8,554,295 | 2025 | 2025 | -0.29 | 1,424.71 | 1,734,615 | 1.217521460508 | 2,052,058 | 358.033 | 358.033 | 1,259,075 | 0.883741252606 | 5.669301754386 | 0 | 0 | 1.73 | 1,734,615 | 8.55 | 2,052,058 | 40.59 | 🟩 NoCs: 0 | 6.82 | 0.556592569716 | 8.55 | 0 | 4.786714489264 | 1.440333822322 | 6,819,680 | 4.785740350877 | 0 | 0 | 0 | 0 | 0 | 6.82 | 1.42 | 358.033 | 0 | 0 | 6.004235949772 | 0 | 6,819,680 | 2024-10-15 | Deployment/Energieffektivisering_med_solcelleanlegg_Bjrnerudveien_14%201.pdf |  |  | 50% | NTE | thing_9a73a61e-e399-557e-b106-120243411471 (https://www.notion.so/thing_9a73a61e-e399-557e-b106-120243411471-294a1d8f95598053a05fe70de4d28d6d?pvs=21) |  | 716.066 | Majorvegen 8 | Agnalt & Holmen | Yes | Payment received | 1280 A | Asian Food Import AS (https://www.notion.so/Asian-Food-Import-AS-1a7a1d8f9559801eaee3d4b49d2d3f8f?pvs=21) | Yes - all PPAs | 3040 | Nannestad |  | https://drive.google.com/file/d/1a8s0q3-nEiNZLQYcYQcTwjZxaV3vkog2/view |  | Ole Bjørn | 400 V | Solar as a Service | 1,365.52 | 2025-08-22 |  |  | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Kristoffer Liset (https://www.notion.so/Kristoffer-Liset-27fa1d8f955980aab65aefd37f755467?pvs=21) | Uploaded FDV | Applied |  | GoO priced in APA | Retrofit not completed |  | Done | ELVIA | Done | Completed |  | Default | Tak: 7 x Solplanet ASW110K-LT Fasade: 1 x Solplanet ASW110K-LT |  | Roof OK | Retrofit | 03.11.25: Godkjent søknad. | Approved | 7359992936316930 (https://www.notion.so/7359992936316930-28ba1d8f955980fbb903e1bcf04d07fa?pvs=21) |  | No status | To be started |  |  | Tak: 2542 x 535 Wp Bifacial Ja Solar Fasade: 156 x 415 Wp TRINA VERTEX S 415 all black | Done | Not started | 10.03.26: fått i retur fordi selve takleieavtalen ikke er i original. Prøver å sende inn på nytt og håper på en annen saksbehandler 29.01.26: sendt til Kartverket. 28.01.26: mottatt signert erklæring, men bare 1. Skal til Thommesen 29.01. 26.01.2026: sendt erklæring til Nhi |  | Siri |  |  |  |  | 510 | 6,309,680
Signed | Stamveien 1, 1481 Hagan |  | 890.1 | 2025-09-30 | 2026-04-10 | 2025-09-30 | 2025-10-26 |  |  | Signed APA | 🟥 183 days (ongoing) | 183 | 🟩 26 days | 26 | 🟥 157 days (ongoing) | 157 | 🟩 184 days (on-going) | 184 | 🟩 1 days | 1 | 0.89 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2510 | 826,980.9 | 5,017.239130434783 | 5.017239130435 | 🟩 OK! | 721.363743 | 721,363.743 |  | 2025 - Q3 | 2025 - Q3 | 0 | 0 |  |  | 865,719.9 | 6,120,297.9 | 6,800,331 | ❌ COD not set | 0 | 865,719.9 | 826,980.9 | 0 | 6,120,298 | 281.878 | 281,877.9 | 92,317.2 | 961.911 | 6,120,297.9 |  | 2025 | -890.1 | 890.1 | 961.911 | 1.080677451972 | 923.172 | 0 | 0 | 545.306 | 0.612634535445 | 7.171920008988 | 0 | 0 | 0 | 961.911 | 2026-08-06 | 923.172 | 38.739 | 🟩 NoCs: 0 | 5.84 | 0.424520840355 | 2026-08-06 | 0 | 6.559285473542 | 1.0371553758 | 5,838,420 | 6.559285473542 | 0 | 0 | 0 | 0 | 0 | 5.84 | 0 | 0 | 0 | 0 |  | 0 | 5,838,420 | [9 empty] | Stamveien 1 |  |  |  | 2500 | Oro Eiendom AS (https://www.notion.so/Oro-Eiendom-AS-1a7a1d8f9559808ab717e86d2a8f3c16?pvs=21), Elenergi AS (https://www.notion.so/Elenergi-AS-287a1d8f955980d19f44e4f4cadcde18?pvs=21) | Yes - all PPAs | 1481 | Hagan |  | https://drive.google.com/file/d/1SUA7PMeWJ-QeahDwDUm0JQv6DtPU9Vn0/view | Stamveien 1 Eiendom AS (https://www.notion.so/Stamveien-1-Eiendom-AS-27da1d8f955980d1bdfbf339a83b9c5b?pvs=21) | Johan | 400 V | Solar as a Service | 890.1 | 2025-09-29 | Svein Rognhaug (https://www.notion.so/Svein-Rognhaug-287a1d8f955980c1b46cfcda25cad0c9?pvs=21) | Innvendig trapp | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Nihal Shrivastava (https://www.notion.so/Nihal-Shrivastava-1a5a1d8f95598027be77f3407f3e9ab8?pvs=21), Carl Langstrand (https://www.notion.so/Carl-Langstrand-28da1d8f95598062a226ea672f75c240?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  | 5x 125 kW snøsmeltevekselretter (INVT) |  | Roof OK | Yes | Ikke søknadspliktig | Approved | 7359992899899235 (https://www.notion.so/7359992899899235-2efa1d8f955980fca77ef5656ede3eac?pvs=21), 7359992892863547 (https://www.notion.so/7359992892863547-2efa1d8f955980fc9202fb3d0ff686a9?pvs=21), 7359992895580755 (https://www.notion.so/7359992895580755-2efa1d8f95598033a669fdd70bf5fb09?pvs=21) | Afry AS (https://www.notion.so/Afry-AS-305a1d8f9559800b839ec7325f13ab74?pvs=21) | Received | Not relevant | PVC | Ca 2022 / 2023 | 1548 stk 575Wp Longi | Done | Not started | 20.01.2026: sendt erklæring til Herman. Vi får denne på overlevering av anlegget. |  | Siri |  |  |  |  | 711.49 | 5,126,930
In operation (COD) | Stasjonsvegen 28, 3800 Bø |  | 387.34 | 2025-10-15 | 2025-12-11 | 2025-10-15 | 2025-11-14 | 2025-12-11 | 387.34 | Transferred | 🟩 57 days | 57 | 🟩 30 days | 30 | 🟩 27 days | 27 | 🟩 87 days | 87 | 🟩 30 days | 30 | 0.39 | 20.908 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 25 - Dec | 2511 | 886.286 | 10,187.19540229885 | 10.187195402299 | 🟩 OK! | 308.3536272 | 308,353.6272 | 2025 - Q4 | 2025 - Q4 | 2025 - Q3 | 0 | 9,683.5 | 9,683.5 | 0 | 907.194 | 2,880,194 | 2,880,194 | ⌚ 111 days | 0 | 907.194 | 886.286 | 0 | 2,880,194 | 907.194 | 907.194 | 0 | 907.194 | 2,880,194 | 2025 | 2025 | 0 | 387.34 | 907.194 | 2.342112872412 | 886.286 | 0 | 0 | 822.599 | 2.123713016988 | 7.217429132029 | 0 | 0 | 0.91 | 907.194 | 2.88 | 886.286 | 20.908 | 🟩 NoCs: 0 | 1.97 | 0.164421438529 | 2.88 | 0 | 5.093716115041 | 2.288134455517 | 1,973,000 | 5.093716115041 | 0 | 0 | 0 | 0 | 0 | 1.97 | 0.39 | 0 | 0 | 0 | 7.435828987453 | 0 | 1,973,000 | [5 empty] | NTE | thing_d717418e-9bf5-5085-a994-399e75087885 (https://www.notion.so/thing_d717418e-9bf5-5085-a994-399e75087885-2b2a1d8f95598032887fff06a3c9915b?pvs=21) |  |  | Stasjonsvegen 28 |  | Yes | Applied by client | 1600 A | Scala Eiendom AS (https://www.notion.so/Scala-Eiendom-AS-26fa1d8f95598047b4f7de9313996c37?pvs=21), Scala Bø AS (https://www.notion.so/Scala-B-AS-28ca1d8f95598053be8cd4499e63bed1?pvs=21) | Yes - all PPAs | 3800 | Bø |  | https://drive.google.com/file/d/1qNN_fnTvkrqh1yDUre-QQiqSjkyEuCDq/view |  | Ole Bjørn | 400 V | Solar as a Service | 380.1 | 2025-09-15 |  | Utvendig trapp | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Uploaded FDV | Applied |  | GoO priced in APA | Not relevant |  | Not started | Føre | Done | Completed |  | Default | 2 x 125 kW Sungrow 400V TN |  | Roof OK | Yes | Ikke søknadsplikt | Not applicable | 7359992899136668 (https://www.notion.so/7359992899136668-28ca1d8f955980cb89ced5e9de783183?pvs=21), 7359992894583719 (https://www.notion.so/7359992894583719-28ca1d8f95598038b13ec982bcce4eb0?pvs=21), 7359992894565111 (https://www.notion.so/7359992894565111-28ca1d8f95598032ac08fb16aed1a745?pvs=21), 7359992894575806 (https://www.notion.so/7359992894575806-2aba1d8f9559800791c0fbaf334cac72?pvs=21), 7359992895822091 (https://www.notion.so/7359992895822091-2aba1d8f955980369380c01858ec49ab?pvs=21), 7359992894566583 (https://www.notion.so/7359992894566583-2aba1d8f955980a5a7c9f83eb8ec272f?pvs=21), 7359992930283429 (https://www.notion.so/7359992930283429-2c5a1d8f95598072b981e4980f0085b9?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  | 724 x 535Wp Jasolar bifacial glass/glass | Done | In operation | 29.01.26: sendt erklæring og samtykke. Trenger samtykke fra bank. Erklæring og samtykke ligger utfylt på drive. Ikke tinglys før vi har overdratt eierskap |  | Siri | [5 empty] | 1,973,000
Signed | Semsvegen 36, 3676 Notodden |  | 913.07 | 2026-01-07 | 2026-06-30 | 2026-01-07 | 2026-05-18 |  |  | To be approved | 🟨 84 days (ongoing) | 84 | 🟥 131 days | 131 | ❌ ERROR / Check Date | -46 | 🟩 145 days (on-going) | 145 | 🟩 61 days | 61 | 0.91 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2605 | -16.502 | 6,760.448275862069 | 6.760448275862 | 🟩 OK! | 685.3777341 | 685,377.7341 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 5,746,767 | ❌ COD not set | 0 | 0 | -16.502 | 0 | 0 | 0 | 0 | 980.265 | 0 | 0 |  | 2025 | -913.07 | 913.07 | 996.767 | 1.091665480193 | 980.265 | 0 | 0 | 996.767 | 1.091665480193 | 6.293895320184 | 0 | 0 | 0 | 0 | 0 | -16.502 | 16.502 | 🟩 NoCs: 0 | 4.75 | -0.018073094067 | 5.75 | 0 | 5.20222983999 | 1.073592386126 | 4,750,000 | 5.20222983999 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 |  | 0 | 4,750,000 | [9 empty] | Semsvegen 36 |  | Client applies | Applied by client | 1600A | Scala Eiendom AS (https://www.notion.so/Scala-Eiendom-AS-26fa1d8f95598047b4f7de9313996c37?pvs=21) | Yes - not all PPAs | 3676 | Notodden |  |  |  | Ole Bjørn | 230 V | SolaaS buy-back | 830.32 | 2025-11-07 |  |  | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Thomas Skazedonigg (https://www.notion.so/Thomas-Skazedonigg-1a5a1d8f9559802bbd40f91695cb4c08?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA | Not relevant |  | Not started | Everket AS | No status | Completed |  |  | 8x Solis 75 kW |  | Roof OK | Yes | Notodden kommune: ikke søknadspliktig | Not applicable | 7359992902102604 (https://www.notion.so/7359992902102604-2bda1d8f955980e9a19df32fde6d0832?pvs=21), 7359992894594715 (https://www.notion.so/7359992894594715-2bda1d8f955980268f76e1bf16afce19?pvs=21), 7359992902102956 (https://www.notion.so/7359992902102956-2bda1d8f955980f4b46cd084ce598c63?pvs=21) | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  | Tak tekkes om i 2026 for eldre del. Ny del er fra 2024/2025. | 1394x655 W Longi | No status | Not started | 29.01.26: sendt erklæring og samtykke. Trenger samtykke fra bank. Erklæring og samtykke ligger utfylt på drive. Ikke tinglys før vi har overdratt eierskap |  | Siri | [5 empty] | 4,750,000
Signed | Tornsangerveien 25, 1360 Fornebu |  | 454 | 2026-05-04 | 2026-08-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 188 days (on-going) | 188 | 🟩 188 days (on-going) | 188 | 0.45 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -18.6 | 3,129.457446808511 | 3.129457446809 | 🟩 OK! | 362.30562 | 362,305.62 |  |  | 2025 - Q3 | 0 | 0 |  |  | 0 | 0 | 2,971,308 | ❌ COD not set | 0 | 0 | -18.6 | 0 | 0 | 0 | 0 | 529,504.2 | 0 | 0 |  | 2025 | -454 | 454 | 567.378 | 1.249731277533 | 588.338 | 39.56 | 39.56 | 567.378 | 1.249731277533 | 6.544731277533 | 0 | 0 | 0 | 0 | 0 | -18.6 | 18.6 | 🟩 NoCs: 0 | 2026-04-02 | 0.046167400881 | 2.97 | 0 | 5.295 | 1.295898678414 | 2,403,930 | 5.295 | 39.56 | 0 | 0 | 39.56 | 0 | 2026-04-02 | 0 | 0 | 0 | 0 |  | 0 | 2,403,930 | 2025-10-09 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Tornsangerveien_25.pdf | 4.95 |  | 20% |  |  |  | 197.8 | Tornsangerveien 25 | TermoEnergi / Piotr | Yes | Application: Successful |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Pending | 1360 | Fornebu | Signed |  |  | Rikard |  | Solar as a Service | 567 | 2025-09-25 |  | Ikke adkomst, må ha stige. |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | In process | Yes | 30.12.25 godkjent søknad | Approved |  | WSP Norge AS (https://www.notion.so/WSP-Norge-AS-27ea1d8f9559807e8cd2cf701d564da3?pvs=21) | Received |  |  | 2012-2018 |  | No status | Not started |  |  | Siri |  |  |  |  | 0 | 2,403,930
Signed | Wirgenes Vei 12, 3157 Barkåker |  | 441.91 | 2026-09-01 | 2026-10-01 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 175 days (on-going) | 175 | 🟩 175 days (on-going) | 175 | 0.44 | 8.21 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -12 | 3,634.285714285714 | 3.634285714286 | 🟩 OK! | 379.15878 | 379,158.78 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,710,000 | ❌ COD not set | 0 | 0 | -12 | 0 | 0 | 0 | 0 | 508.8 | 0 | 0 |  | 2025 | -441.91 | 441.91 | 450 | 1.018306895069 | 636 | 198 | 198 | 450 | 1.018306895069 | 6.132470412527 | 0 | 8.21 | 0 | 0 | 0 | -12 | 12 | 🟩 NoCs: 0 | 2.26 | 0.420900183295 | 2.71 | 0 | 5.114163517458 | 1.439207078364 | 2,260,000 | 5.114163517458 | 198 | 0 | 0 | 198 | 0 | 2.26 | 0 | 0 | 0 | 0 |  | 0 | 2,260,000 | 2025-10-10 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Wirgenes_Vei_12.pdf | 4.95 |  | 50% |  |  |  | 396 | Wirgenes Vei 12 | Løyning / Marianne | Yes | Application: Successful | 800 | Coproperty AS (https://www.notion.so/Coproperty-AS-2a8a1d8f955980eea9c4f436bdbb688c?pvs=21) | Pending | 3157 | Barkåker | Signed | https://drive.google.com/file/d/18bc3KKa-GTvew1lkEryiDlML1vdf_zh8/view?usp=drive_link | Coproperty AS (https://www.notion.so/Coproperty-AS-2a8a1d8f955980eea9c4f436bdbb688c?pvs=21) | Johan | 400 V | Solar as a Service | 490 | 2025-10-08 |  | Innvendig stige |  |  |  | To be applied |  |  |  |  | Not started | LEDE | No status | Completed |  |  | Solplanet |  | No status | Yes |  | To be applied |  |  | No status |  | PVC | 2023 | Jasolar 535w |  |  |  |  | Siri | 8.21 |  |  |  | 210 | 2,050,000
Signed | Wirgenes Vei 14, 3157 Barkåker |  | 152.64 | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-04-01 |  |  | To be approved | 🟩 41 days (on-going) | 41 | 🟨 41 days | 41 | 🟩 0 days (on-going) | 0 | 🟩 175 days (on-going) | 175 | 🟩 134 days | 134 | 0.15 | 2.45 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2604 | -13.95 | 1,428.857142857143 | 1.428857142857 | 🟩 OK! | 130.96512 | 130,965.12 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,055,000 | ❌ COD not set | 0 | 0 | -13.95 | 0 | 0 | 0 | 0 | 250.05 | 0 | 0 |  | 2025 | -152.64 | 152.64 | 190 | 1.244758909853 | 250.05 | 74 | 74 | 190 | 1.244758909853 | 6.911687631027 | 0 | 2.45 | 0 | 0 | 0 | -13.95 | 13.95 | 🟩 NoCs: 0 | 0.87 | 0.393409329141 | 2026-06-01 | 0 | 5.666928721174 | 1.638168238994 | 865 | 5.666928721174 | 74 | 0 | 0 | 74 | 0 | 0.87 | 0 | 0 | 0 | 0 |  | 0 | 865 | 2025-10-10 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Wirgenes_Vei_14.pdf | 4.94 |  | 50% |  |  |  | 148 | Wirgenes Vei 14 | Løyning / Marianne | Yes | Application: Successful | 800 | Coproperty AS (https://www.notion.so/Coproperty-AS-2a8a1d8f955980eea9c4f436bdbb688c?pvs=21) | Yes - all PPAs | 3157 | Barkåker | Signed | https://drive.google.com/file/d/1U5vWCNFMkHrI6MzaFpREmAm8SdKUBG5R/view?usp=drive_link | Coproperty AS (https://www.notion.so/Coproperty-AS-2a8a1d8f955980eea9c4f436bdbb688c?pvs=21) | Johan | 400 V | Solar as a Service | 195 | 2025-10-08 |  | Stige | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) | Kristoffer Liset (https://www.notion.so/Kristoffer-Liset-27fa1d8f955980aab65aefd37f755467?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | Not started | LEDE | No status | Completed |  |  | 1x Solplanet 110 kW |  | Roof OK | Yes | Søknad sendt 25.02.26 | Sent | 7359992909300652 (https://www.notion.so/7359992909300652-2fea1d8f955980e3bd36d201f78ee1e2?pvs=21) |  | No status |  | PVC | 2024 | 288 x Jasolar 530W | No status | Not started |  |  | Siri |  |  |  | 2.45 | 95 | 770
Signed | , |  | 512.12 | 2026-07-01 | 2026-12-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 174 days (on-going) | 174 | 🟩 174 days (on-going) | 174 | 0.51 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 4,359.327586206897 | 4.359327586207 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,821,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227,556.9 | 0 | 0 |  | 2025 | -512.12 | 512.12 | -241.477 | -0.471524252128 | 758.523 | 1,000,000 | 1,000,000 | -241.477 | -0.471524252128 | 5.508474576271 | 0 | 0 | 0 | 0 | 0 | 1,000,000 | 0 | 🟩 NoCs: 0 | 2026-06-03 | 1.952667343591 | 2.82 | 0 | 5.9799988284 | 1.481143091463 | 3,062,477 | 5.9799988284 | 0 | 0 | 0 | 0 | 0 | 2026-06-03 | 0 | 1,000,000 | 0 | 0 |  | 0 | 3,062,477 | 2025-10-09 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Havet_45.pdf | 6.98 |  | 100% |  |  |  | 1,000,000 |  | Entro (for Logistea) | Yes | Application: Successful |  | Logistea AS (https://www.notion.so/Logistea-AS-1a8a1d8f955980458a0ef7caf1e1a0fa?pvs=21) | [6 empty] | Johan |  | Solar as a Service | 512.12 | 2025-10-09 | [10 empty] | Not started |  |  | Not completed |  |  |  |  | In process | Yes |  |  |  |  | No status | [8 empty] | Kjetil |  |  |  |  | 0 | 3,062,477
Signed | Kinnlimarka 20, 2360 Rudshøgda |  | 985.56 | 2026-04-17 | 2026-04-26 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 174 days (on-going) | 174 | 🟩 174 days (on-going) | 174 | 0.99 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | -18 | 5,675.287356321839 | 5.675287356322 | 🟩 OK! | 773.6646 | 773,664.6 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 6,853,000 | ❌ COD not set | 0 | 0 | -18 | 0 | 0 | 0 | 0 | 987.5 | 0 | 0 |  | 2025 | -985.56 | 985.56 | 833 | 0.845204756687 | 987.5 | 172.5 | 172.5 | 833 | 0.845204756687 | 6.953407199968 | 0 | 0 | 0 | 0 | 0 | -18 | 18 | 🟩 NoCs: 0 | 2026-02-06 | 0.156763667356 | 6.85 | 0 | 6.108202443281 | 1.001968424043 | 6,020,000 | 6.108202443281 | 172.5 | 0 | 0 | 172.5 | 0 | 2026-02-06 | 0 | 0 | 0 | 0 |  | 0 | 6,020,000 | 2025-10-09 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Kinnlimarka_20.pdf | 5.25 |  | 25% |  |  |  | 690 | Kinnlimarka 20 | TermoEnergi | Yes | Application: Successful | 800A | Coop Innlandet SA (https://www.notion.so/Coop-Innlandet-SA-2a0a1d8f955980ff985ad729214cb55f?pvs=21) | Yes - all PPAs | 2360 | Rudshøgda | Signed | https://drive.google.com/drive/folders/1CnKg4c3AMhmJWqgPz4X56soEtTwHajY8 |  | Ole Bjørn | 400 V | Solar as a Service | 984.96 | 2025-10-09 |  |  | Ecosol AS (https://www.notion.so/Ecosol-AS-1aba1d8f95598094847fc6a923fd88b4?pvs=21) | Tormod Engesæth (https://www.notion.so/Tormod-Enges-th-1a5a1d8f95598010addac6474e46ce10?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | Not started | ELVIA | No status | Completed |  |  | 6x125 kW INVT snow melting |  | No status | Yes | Godkjent søknad | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Booked | Not relevant |  |  | 1528x645W LONGi LR8-66HVD-645M | No status | Not started |  | To be installed | Kjetil |  |  |  |  | 0 | 6,020,000
In operation (COD) | Snipetjernveien 3, 1405 Langhus |  | 512.9 | 2025-07-08 | 2026-01-20 | 2025-07-08 | 2025-08-20 | 2026-01-20 | 506 | Transferred | 🟥 196 days | 196 | 🟨 43 days | 43 | 🟥 153 days | 153 | 🟨 235 days | 235 | 🟩 39 days | 39 | 0.51 | 0 | 🟩 All good | 25 | ❌ End date missing | 💚 All good | 2026-01-26 | 2508 | -348,395.4 | -1,647.259574468085 | -1.647259574468 | 🟩 OK! | 413.1743 | 413,174.3 | 2026 - Q1 | 2025 - Q3 | 2025 - Q2 | 246,934.8 | 12.65 | 12.65 | 0 | -595,330.2 | 3,092,301 | 3,435,890 | ⌚ 71 days | 246,934.8 | -595,330.2 | -348,395.4 | 0 | 3,092,301 | -1,005,067 | -1,005,067 | -38,710.6 | -661.478 | 3,092,301 | 2026 | 2025 | -6.9 | 506 | -661.478 | -1.307268774704 | -387.106 | 274.372 | 274.372 | -2,886,215 | -5.703982213439 | 0 | 0 | 0 | -0.66 | -661.478 | 3.44 | -387.106 | 0 | 🟨 NoCs: 2 | 2026-01-04 | 4.938950592886 | 3.44 | 0 | 8.097565217391 | -0.765031620553 | 2,886,215 | 5.627247026711 | 0 | 0 | 0 | 0 | 0 | 2026-01-04 | 0.51 | 274.372 | 0 | 0 | 6.790296442688 | 1,211,153 | 4,097,368 | 2025-05-30 | Deployment/Tilskuddsbrev-3.pdf, Deployment/Signering_steg_2_av_2_-_Tilskuddsbrev-2.pdf |  |  | 100% | NTE | thing_d8cd8718-810c-5f05-aaa3-6e1fdd48c824 (https://www.notion.so/thing_d8cd8718-810c-5f05-aaa3-6e1fdd48c824-292a1d8f955980be93d1f3f169c7f072?pvs=21) | Not started | 274.372 | Snipetjernveien 3 | Malling & Co Energi og Miljø AS v/ Andreas Søraas Goldenheim | Yes | Application: Successful | 500A | Bulk Industrial Real Estate AS (https://www.notion.so/Bulk-Industrial-Real-Estate-AS-1a8a1d8f9559805ca7cbd0938f7b649d?pvs=21) | Yes - all PPAs | 1405 | Langhus |  | https://drive.google.com/file/d/1BZf8kfjnGn7_2PEHOyYmzcocsk1JpU9c/view |  | Jonas | 400 V | Solar as a Service | 2,044.7 | 2025-05-30 | Marjan Radovic (https://www.notion.so/Marjan-Radovic-2e8a1d8f95598034a937ea87c5a7f8dc?pvs=21) | Spiraltrapp fra bakke til tak på østsiden av bygget til 3A. Deretter fastmontert stige videre opp til 3C. | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Kim Andre Pettersen (https://www.notion.so/Kim-Andre-Pettersen-1a5a1d8f95598017b0a4cd7a371cda44?pvs=21) | Uploaded FDV | Applied |  | GoO priced in APA | Retrofit not completed |  | Done | NORGESNETT | Planned | Completed |  | Default | 3x Solis 110K-5G-PRO |  | Roof OK | Yes | Ikke søknadspliktig. | Approved | 7359992930260260 (https://www.notion.so/7359992930260260-2dfa1d8f955980cf8cceeb9358704627?pvs=21), 5706567337624214 (https://www.notion.so/5706567337624214-2fca1d8f955980a0b17de433b5427b5e?pvs=21) | Norconsult AS (https://www.notion.so/Norconsult-AS-22aa1d8f955980318108df778e1c40bb?pvs=21) | Received | To be started | PVC | 2024 | 880x575W LONGi | Done | Not started |  | Installed | Kjetil |  |  |  |  | 0 | 2,886,215
Signed | Lindebergveien 16, 2016 Frogner |  | 375.84 | 2026-02-27 | 2026-09-30 | 2026-02-27 | 2026-08-17 |  |  | To be approved | 🟩 33 days (on-going) | 33 | 🟥 171 days | 171 | ❌ ERROR / Check Date | -137 | 🟩 153 days (on-going) | 153 | 🟩 120 days | 120 | 0.38 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2608 | 0 | 2,263.385620915033 | 2.263385620915 | 🟩 OK! | 299.16864 | 299,168.64 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,257,298 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346.298 | 0 | 0 |  | 2025 | -375.84 | 375.84 | 346.298 | 0.92139740315 | 346.298 | 0 | 0 | 346.298 | 0.92139740315 | 6.006007875692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.91 | 0 | 2.26 | 0 | 5.084610472542 | 0.92139740315 | 1,911,000 | 5.084610472542 | 0 | 0 | 0 | 0 | 0 | 1.91 | 0 | 0 | 0 | 0 |  | 0 | 1,911,000 | [9 empty] | Lindebergveien 16 |  | No | Does not qualify | 500A | Rognerud Eiendom AS (https://www.notion.so/Rognerud-Eiendom-AS-2a8a1d8f955980ba879dcfd3c04b5a9c?pvs=21) | Yes - all PPAs | 2016 | Frogner | Signed |  |  | Ole Bjørn | 400 V | Solar as a Service | 359.52 | 2025-10-30 | Ole Jakob Aas (https://www.notion.so/Ole-Jakob-Aas-314a1d8f955980f5bfb6cf80a48adfca?pvs=21) |  | Future-Suntech AS (https://www.notion.so/Future-Suntech-AS-305a1d8f955980bcb10ccfc449aedcd1?pvs=21) | Glenn Frode Olsen (https://www.notion.so/Glenn-Frode-Olsen-1a5a1d8f95598004aec4c6cc2ba32604?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | In progress | ELVIA | No status | Completed |  |  | 2x 125kW inverter |  | Roof OK | Yes | Nybygg der kunde har søkt selv med Grønn Strøm som PRO og UTF | Approved |  |  | Received | Not relevant | PVC med forsterket duk og isolasjon | 2026 | 672x535W | Planned | Not started |  | To be installed | Kjetil |  |  |  |  | 200 | 1,711,000
Signed | Sarpsborgveien 9, 1640 Råde |  | 317.9 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 145 days (on-going) | 145 | 🟩 145 days (on-going) | 145 | 0.32 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 1,758.620689655172 | 1.758620689655 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,908,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 |  | 2025 | -317.9 | 317.9 | 255 | 0.802139037433 | 255 | 0 | 0 | 255 | 0.802139037433 | 6.00188738597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.65 | 0 | 1.91 | 0 | 5.199748348537 | 0.802139037433 | 1,653,000 | 5.199748348537 | 0 | 0 | 0 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 |  | 0 | 1,653,000 | [9 empty] | Sarpsborgveien 9 |  |  |  |  | Haber Norge AS (https://www.notion.so/Haber-Norge-AS-2aba1d8f95598027819de48ba2941e24?pvs=21) | No | 1640 | Råde | Signed |  |  | Rikard |  | Solar as a Service |  | 2025-11-07 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started |  | No status | [5 empty] | Not OK | TBD |  | No status |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil | [5 empty] | 1,653,000
Signed - awaiting Sales | Stormåsan 19, 1540 Vestby |  | 1.5 | 2026-03-13 | 2026-06-30 |  |  |  |  | N/A | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 2026-05-01 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟩 OK! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 8,000,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 |  |  | -1.5 | 1.5 | 350 | 0.233333333333 | 350 | 0 | 0 | 350 | 0.233333333333 | 5.333333333333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 7.65 | 0 | 8 | 0 | 2026-01-05 | 0.233333333333 | 7,650,000 | 2026-01-05 | 0 | 0 | 0 | 0 | 0 | 7.65 | 0 | 0 | 0 | 0 |  | 0 | 7,650,000 | [9 empty] | Stormåsan 19 |  |  |  | 1800A | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1540 | Vestby |  |  |  | Ole Bjørn | 400 V | Project Sales |  |  |  | Fastmontert stige fra andre etasje ved kantine. |  |  | Not uploaded | [5 empty] | Not started | ELVIA | No status | Completed |  |  |  |  | Roof OK | Yes |  |  |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant |  |  |  | No status | Not started |  |  | Kjetil | [5 empty] | 7,650,000
Cancelled | , |  | 210 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.21 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | -210 | 210 | 0 | 0 | 0 | 0 | 0 | -906 | -4.314285714286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.91 | 0 | 0 | 0 | 4.314285714286 | 0 | 906 | 4.314285714286 | 0 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0 |  | 0 | 906 | [13 empty] | 500A | God Driv AS (https://www.notion.so/God-Driv-AS-1a8a1d8f955980e0ac76fb889741f4e4?pvs=21) | [6 empty] | Jonas | 400 V | Solar as a Service | 210 |  |  |  | Differ Energy AS (https://www.notion.so/Differ-Energy-AS-1a6a1d8f955980b59abbed97a4b25462?pvs=21) |  | Not uploaded | [5 empty] | Not started | [5 empty] | 1x100 kW Solis 100 kW 400V |  |  | Yes | 14.01.26: Godkjent søknad | Approved | [6 empty] | 320x530W JA Solar JAM60D42 LB |  |  |  |  | Kjetil |  |  |  |  | 70 | 836
Signed - awaiting Sales | , 2052 Jessheim |  | 416.81 | 2026-06-01 | 2026-07-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 127 days (on-going) | 127 | 🟩 127 days (on-going) | 127 | 0.42 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 2,986.393700787402 | 2.986393700787 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,415,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265,490.4 | 0 | 0 |  | 2025 | -416.81 | 416.81 | 289.272 | 0.694014059164 | 379.272 | 90 | 90 | 289.272 | 0.694014059164 | 5.79400686164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2.13 | 0.215925721551 | 2.42 | 0 | 5.099992802476 | 0.909939780715 | 2,125,728 | 5.099992802476 | 90 | 0 | 0 | 90 | 0 | 2.13 | 0 | 0 | 0 | 0 |  | 0 | 2,125,728 | 2025-12-19 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Henrik_Bulls_veg_102.pdf, Deployment/Tilskuddsbrev_Henrik_Bulls_veg_102.pdf | 5.97 |  | 20% |  |  |  | 450 |  | Termoenergi | Yes | Application: Successful |  | Ragde Eiendom AS (https://www.notion.so/Ragde-Eiendom-AS-1a6a1d8f955980a8ab66d2517d08a597?pvs=21) | Pending | 2052 | Jessheim | Signed |  |  | Rikard |  | Solar as a Service |  | 2025-11-25 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Not completed |  |  |  |  | No status | TBD |  | No status |  |  | No status |  |  |  |  | No status | Not started |  |  | Siri | [5 empty] | 2,125,728
To be installed (FID) | , | [9 empty] | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [6 empty] | thing_4f5f004b-0869-5e0a-a30c-807f9567fe50 (https://www.notion.so/thing_4f5f004b-0869-5e0a-a30c-807f9567fe50-31fa1d8f9559806a8397ef8a1a0a2824?pvs=21) | [7 empty] | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) | [6 empty] | Ole Bjørn |  | SaaS | [12 empty] | Not started | ELVIA |  | Completed | [5 empty] | No |  |  | 7359992899914341 (https://www.notion.so/7359992899914341-2bea1d8f955980f1b34acfef23e3bc18?pvs=21) | [6 empty] | Done |  |  | Delivered to installer | Kjetil
In operation (COD) | , |  | 139.1 |  |  | 2025-12-02 |  | 2026-02-26 | 139.1 | N/A | 🟨 86 days | 86 | 🟥 120 days (ongoing) | 120 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.14 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q1 | 2025 - Q4 |  | 0 | 0 |  |  | 0 | 0 | 25 | ⌚ 34 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 139.1 | 20 | 0.143781452193 | 20 | 0 | 0 | 20 | 0.143781452193 | 0.179726815241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.035945363048 | 0.143781452193 | 5 | 0.035945363048 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.14 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | thing_2bb17cf1-68f2-5880-bdff-21e09292b756 (https://www.notion.so/thing_2bb17cf1-68f2-5880-bdff-21e09292b756-2bea1d8f955980bab073e64cfde60df9?pvs=21) |  |  |  |  | No | Does not qualify |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) | [6 empty] | Ole Bjørn | 400 V | SaaS | 139.1 | [11 empty] | Not started | ELVIA | Not relevant | Completed |  |  | 1x Sungrow 125 kW |  | No status | No |  | Not applicable | 7359992899893035 (https://www.notion.so/7359992899893035-304a1d8f9559803e825bcaf8963c6683?pvs=21) |  | No status |  |  |  | 16x580W LONGi LR5-72HTH-580M 216x585W LONGi LR5-72HTH-585M CRE4 | Done |  |  | Delivered to installer | Kjetil |  |  |  |  | 5
In operation (COD) | Stormåsan 19, 1540 Vestby |  | 151.1 |  |  | 2025-12-03 |  | 2026-03-06 | 151.1 | N/A | 🟨 93 days | 93 | 🟥 119 days (ongoing) | 119 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.15 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 26 - Mar |  | 0 |  | 0 | 🟥 SUM! | 123.4487 | 123,448.7 | 2026 - Q1 | 2025 - Q4 |  | 0 | 11,534.974 |  |  | 0 | 0 | 25 | ⌚ 26 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 151.1 | 20 | 0.132362673726 | 20 | 0 | 0 | 20 | 0.132362673726 | 0.165453342158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.033090668432 | 0.132362673726 | 5 | 0.033090668432 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.15 | 0 | 0 | 0 | 0 | 0 | 5 | [5 empty] | Premium | thing_e39f7482-8721-59f0-9257-912594042fde (https://www.notion.so/thing_e39f7482-8721-59f0-9257-912594042fde-2bea1d8f955980c08331cb57845b90b0?pvs=21) | In progress |  | Stormåsan 19 |  | No | Does not qualify | 1250A | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1540 | Vestby |  |  |  | Ole Bjørn | 400 V | SaaS | 148 |  |  | Fastmontert stige med ryggsøyle fra andre etasje ved kantine. |  |  | Uploaded FDV | Not relevant |  | Not relevant | Not relevant |  | Not started | ELVIA | Not relevant | Completed |  |  | 1x Growatt 100 kW |  | No status | No |  | Not applicable | 7359992894562981 (https://www.notion.so/7359992894562981-304a1d8f955980f98c68eb5332e01fce?pvs=21) |  | No status | Not relevant | PVC |  | 140x365W REC 264x375W REC | Done |  |  | Delivered to installer | Kjetil |  |  |  |  | 5
In operation (COD) | Vogellund 35, 1394 Nesbru |  | 137.76 |  |  | 2025-12-03 | 2025-12-17 | 2025-12-17 | 137.76 | N/A | 🟩 14 days | 14 | 🟩 14 days | 14 | 🟩 0 days | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.14 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 25 - Dec | 2512 | 0 |  | 0 | 🟥 SUM! | 107.86608 | 107,866.08 | 2025 - Q4 | 2025 - Q4 |  | 0 | 10,422.9216 |  |  | 0 | 0 | 25 | ⌚ 105 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 |  | 0 | 137.76 | 20 | 0.145180023229 | 20 | 0 | 0 | 20 | 0.145180023229 | 0.181475029036 | 0 | 0 | 0.02 | 20 | 0.03 | 20 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.036295005807 | 0.145180023229 | 5 | 0.036295005807 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.14 | 0 | 0 | 0 | 0.181475029036 | 0 | 5 | [5 empty] | Smart + Monitoring | thing_287194eb-f7b4-52f4-8081-406666dee3ca (https://www.notion.so/thing_287194eb-f7b4-52f4-8081-406666dee3ca-2bea1d8f9559809e8e6ef9e6c9e436a3?pvs=21) |  |  | Vogellund 35 |  |  |  |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1394 | Nesbru |  |  |  | Ole Bjørn | 400 V | SaaS | 137.76 | [5 empty] | N/A | [5 empty] | Not started | ELVIA | Not relevant | Completed |  |  | 1x Sungrow 125 kW |  | No status | No |  | Not applicable | 34613018 (https://www.notion.so/34613018-31ea1d8f9559803fa20bf9bd52cad3dd?pvs=21) |  | No status | Not relevant |  |  | 336x410W REC | Done |  |  | Installed | Kjetil |  |  |  |  | 5
In operation (COD) | Lysaker Torg 5, 1366 Lysaker |  | 32.64 |  |  | 2025-12-03 |  | 2025-12-17 | 32.64 | N/A | 🟩 14 days | 14 | 🟥 119 days (ongoing) | 119 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.03 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 25 - Dec |  | 0 |  | 0 | 🟥 SUM! | 25.6224 | 25,622.4 | 2025 - Q4 | 2025 - Q4 |  | 0 | 2,470.848 |  |  | 0 | 0 | 25 | ⌚ 105 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 |  | 0 | 32.64 | 20 | 0.612745098039 | 20 | 0 | 0 | 20 | 0.612745098039 | 0.765931372549 | 0 | 0 | 0.02 | 20 | 0.03 | 20 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.15318627451 | 0.612745098039 | 5 | 0.15318627451 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.03 | 0 | 0 | 0 | 0.765931372549 | 0 | 5 | [5 empty] | Smart + Monitoring | thing_479beee2-4b0d-5b45-85e4-c8d24f268759 (https://www.notion.so/thing_479beee2-4b0d-5b45-85e4-c8d24f268759-2bea1d8f955980a5b74bd3153486639e?pvs=21) |  |  | Lysaker Torg 5 |  |  |  |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1366 | Lysaker |  |  |  | Ole Bjørn |  | SaaS | 32.64 | [5 empty] | N/A | [5 empty] | Not started | ELVIA |  | Completed | [5 empty] | No |  | Not applicable | 33758664 (https://www.notion.so/33758664-2bea1d8f9559803c84c5f4c807bcef7a?pvs=21) | [6 empty] | Done |  |  | Installed | Kjetil |  |  |  |  | 5 | 0
In operation (COD) | Lysaker Torg 15, 1366 Lysaker |  | 83.84 |  |  | 2025-12-03 | 2025-12-17 | 2025-12-17 | 83.84 | N/A | 🟩 14 days | 14 | 🟩 14 days | 14 | 🟩 0 days | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.08 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 25 - Dec | 2512 | 0 |  | 0 | 🟥 SUM! | 65.73056 | 65,730.56 | 2025 - Q4 | 2025 - Q4 |  | 0 | 6,345.0112 |  |  | 0 | 0 | 25 | ⌚ 105 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 |  | 0 | 83.84 | 20 | 0.238549618321 | 20 | 0 | 0 | 20 | 0.238549618321 | 0.298187022901 | 0 | 0 | 0.02 | 20 | 0.03 | 20 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.05963740458 | 0.238549618321 | 5 | 0.05963740458 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.08 | 0 | 0 | 0 | 0.298187022901 | 0 | 5 | [5 empty] | Smart + Monitoring | thing_56abb5cb-4c0c-53c9-92cf-cfc706a289b4 (https://www.notion.so/thing_56abb5cb-4c0c-53c9-92cf-cfc706a289b4-2bea1d8f9559802ebfb2e8aae8675016?pvs=21) |  |  | Lysaker Torg 15 |  |  |  |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1366 | Lysaker |  |  |  | Ole Bjørn |  | SaaS | 83.84 | [5 empty] | N/A | [5 empty] | Not started | ELVIA | No status | Completed | [5 empty] | No |  | Not applicable | 33758878 (https://www.notion.so/33758878-2bea1d8f9559809497b7f5ab2912f9df?pvs=21) |  | No status |  |  |  |  | Done |  |  | Installed | Kjetil |  |  |  |  | 5 | 0
In operation (COD) | Lysaker Torg 25, 1366 Lysaker |  | 80 |  |  | 2025-12-03 | 2025-12-17 | 2025-12-17 | 80 | N/A | 🟩 14 days | 14 | 🟩 14 days | 14 | 🟩 0 days | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.08 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 25 - Dec | 2512 | 0 |  | 0 | 🟥 SUM! | 62.72 | 62.72 | 2025 - Q4 | 2025 - Q4 |  | 0 | 6,054.4 |  |  | 0 | 0 | 25 | ⌚ 105 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 |  | 0 | 80 | 20 | 0.25 | 20 | 0 | 0 | 20 | 0.25 | 0.3125 | 0 | 0 | 0.02 | 20 | 0.03 | 20 | 0 | 🟩 NoCs: 0 | 0.01 | 0 | 0.03 | 0 | 0.0625 | 0.25 | 5 | 0.0625 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.08 | 0 | 0 | 0 | 0.3125 | 0 | 5 | [5 empty] | Smart + Monitoring | thing_937d58c9-9661-52f1-8c4d-68bf1931fda3 (https://www.notion.so/thing_937d58c9-9661-52f1-8c4d-68bf1931fda3-2bea1d8f9559809cb72ce949706d2fd7?pvs=21) |  |  | Lysaker Torg 25 |  |  |  |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) |  | 1366 | Lysaker |  |  |  | Ole Bjørn |  | SaaS | 80 | [5 empty] | N/A | [5 empty] | Not started | ELVIA | No status | Completed |  |  |  |  | No status | No |  | Not applicable | 33758924 (https://www.notion.so/33758924-2bea1d8f955980d79ad2f4274e5593e9?pvs=21) |  | No status | Not relevant |  |  |  | Done |  |  | Installed | Kjetil |  |  |  |  | 5 | 0
Under deployment | Grev Wedels plass 9, 0151 Oslo | [9 empty] | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Grev Wedels plass 9 |  |  | Does not qualify |  | Storebrand AS (https://www.notion.so/Storebrand-AS-2b1a1d8f955980478cf2ca2b5359f02b?pvs=21) | Not relevant | 151 | Oslo |  |  |  | Ole Bjørn |  | SaaS | [12 empty] | Not started |  |  | Completed | [5 empty] | No | [9 empty] | Done |  |  |  | Kjetil
Cancelled | , |  | 1,257.92 |  |  |  |  | 2024-06-30 | 1,257.92 | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 1.26 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 24 - Jun |  | 0 |  | 0 | 🟥 SUM! | 0 | 0 | 2024 - Q2 |  |  | 0 | 0 |  |  | 0 | 0 |  | ⌚ 640 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 |  | 0 | 1,257.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 1400A | God Driv AS (https://www.notion.so/God-Driv-AS-1a8a1d8f955980e0ac76fb889741f4e4?pvs=21) | [6 empty] | Jonas |  | Solar as a Service | 1,257.92 |  |  |  | Sun-Net Norge AS (https://www.notion.so/Sun-Net-Norge-AS-1a7a1d8f95598088b999cb101c68e1cb?pvs=21) | [7 empty] | Not started | [5 empty] | 14x Huawei og Growatt |  | Roof OK | Yes | 18.12.25: Mangler ferdigattest | Approved | [6 empty] | 3106x404W LONGi LR5-54HIBD |  |  |  |  | Kjetil
Signed - awaiting Sales | , |  | 2.225 |  |  | 2026-06-01 |  | 2026-06-30 |  | To be approved | 🟩 29 days | 29 | ❌ ERROR / Check Date | -60 | ❌ ISD date missing | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 2.23 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Jun |  | 0 |  | 0 | 🟩 OK! | 1,793.35 | 1,793,350 | 2026 - Q2 | 2026 - Q2 |  | 0 | 0 |  |  | 0 | 0 | 18,307,000 | 🔸🕐 -89 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921 | 0 | 0 | 2026 |  | -2.225 | 2.225 | 1,842,000 | 0.827865168539 | 1,842,000 | 0 | 0 | 1,842,000 | 0.827865168539 | 8.227865168539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 16.47 | 0 | 18.31 | 0 | 2026-04-07 | 0.827865168539 | 16,465,000 | 2026-04-07 | 0 | 0 | 0 | 0 | 0 | 16.47 | 0 | 0 | 0 | 0 |  | 0 | 16,465,000 | [21 empty] | Jonas | 400 V | Solar as a Service | [12 empty] | Not started | ELVIA | [8 empty] | 18.12.25: Mangler ferdigattest | Approved | [11 empty] | Kjetil | [5 empty] | 16,465,000
Signed - awaiting Sales | , |  | 197.6 | 2026-05-01 | 2026-08-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 145 days (on-going) | 145 | 🟩 145 days (on-going) | 145 | 0.2 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | -7.532 | 1,244.951724137931 | 1.244951724138 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,243,000 | ❌ COD not set | 0 | 0 | -7.532 | 0 | 0 | 0 | 0 | 144,414.4 | 0 | 0 |  | 2025 | -197.6 | 197.6 | 149.3 | 0.755566801619 | 180.518 | 38.75 | 38.75 | 149.3 | 0.755566801619 | 6.29048582996 | 0 | 0 | 0 | 0 | 0 | -7.532 | 7.532 | 🟩 NoCs: 0 | 2026-09-01 | 0.15798582996 | 1.24 | 0 | 5.53491902834 | 0.913552631579 | 1,093,700 | 5.53491902834 | 38.75 | 0 | 0 | 38.75 | 0 | 2026-09-01 | 0 | 0 | 0 | 0 |  | 0 | 1,093,700 | 2025-12-17 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Furuholtet_10.pdf, Deployment/Tilskuddsbrev_Furuholtet_10.pdf | 6.14 |  | 25% |  |  |  | 155 |  | Løyning / Marianne | Yes | Application: Successful |  | Haber Norge AS (https://www.notion.so/Haber-Norge-AS-2aba1d8f95598027819de48ba2941e24?pvs=21) | Pending |  |  | Signed |  |  | Rikard | 400 V | Solar as a Service | 197.6 | 2025-11-07 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  | 1x Sungrow SG150CX |  | No status | TBD | Ikke søknadsplikt | Approved |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil |  |  |  |  | 53.7 | 1,040,000
Signed - awaiting Sales | , Løken 1960 |  | 207 | 2026-03-24 | 2026-06-26 | 2026-03-24 | 2026-06-01 |  |  | To be approved | 🟩 8 days (on-going) | 8 | 🟥 69 days | 69 | ❌ ERROR / Check Date | -60 | 🟩 145 days (on-going) | 145 | 🟩 137 days | 137 | 0.21 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2606 | -7.523 | 1,866.979310344828 | 1.866979310345 | 🟩 OK! | 0 | 0 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,428,235 | ❌ COD not set | 0 | 0 | -7.523 | 0 | 0 | 0 | 0 | 216,569.6 | 0 | 0 |  | 2025 | -207 | 207 | 238.235 | 1.150893719807 | 270.712 | 40 | 40 | 238.235 | 1.150893719807 | 6.899685990338 | 0 | 0 | 0 | 0 | 0 | -7.523 | 7.523 | 🟩 NoCs: 0 | 1.19 | 0.156893719807 | 1.43 | 0 | 5.748792270531 | 1.307787439614 | 1,190,000 | 5.748792270531 | 40 | 0 | 0 | 40 | 0 | 1.19 | 0 | 0 | 0 | 0 |  | 0 | 1,190,000 | 2025-12-17 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Sandumveien_2.pdf, Deployment/Tilskuddsbrev_Sandumveien_2.pdf | 2026-01-06 |  | 25% |  |  |  | 160 |  | Løyning / Marianne | Yes | Application: Successful | 630A | Haber Norge AS (https://www.notion.so/Haber-Norge-AS-2aba1d8f95598027819de48ba2941e24?pvs=21) | Pending | Løken | 1960 | Signed |  |  | Rikard | 230 V | Solar as a Service | 205.4 | 2025-11-07 |  |  | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Nora Holst Haaland (https://www.notion.so/Nora-Holst-Haaland-32da1d8f955980ffb335c87c182fd6fe?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA |  |  | Not started | Høland og Setskog Elverk | No status | Completed |  |  | 2x Solis 75kV-LV |  | No status | Yes | Ikke søknadsplikt | Approved |  |  | Booked | Not relevant |  |  | 316x655W LONGi LR7-72HVH | No status | Not started |  | To be installed | Kjetil | [5 empty] | 1,190,000
Signed - awaiting Sales | , |  | 120.5 | 2026-03-24 | 2026-06-26 | 2026-03-24 | 2026-06-01 |  |  | To be approved | 🟩 8 days (on-going) | 8 | 🟥 69 days | 69 | ❌ ERROR / Check Date | -60 | 🟩 145 days (on-going) | 145 | 🟩 137 days | 137 | 0.12 | 1.437 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2606 | -27.582 | 1,185.91724137931 | 1.185917241379 | 🟩 OK! | 0 | 0 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 861.97 | ❌ COD not set | 0 | 0 | -27.582 | 0 | 0 | 0 | 0 | 137,566.4 | 0 | 0 |  | 2025 | -120.5 | 120.5 | 168.29 | 1.396597510373 | 171.958 | 31.25 | 31.25 | 168.29 | 1.396597510373 | 7.153278008299 | 0 | 1.437 | 0 | 0 | 0 | -27.582 | 27.582 | 🟩 NoCs: 0 | 0.69 | 0.030439834025 | 0.86 | 0 | 5.756680497925 | 1.427037344398 | 693.68 | 5.756680497925 | 31.25 | 0 | 0 | 31.25 | 0 | 0.69 | 0 | 0 | 0 | 0 |  | 0 | 693.68 | 2025-12-17 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Mausetvegen_4.pdf, Deployment/Tilskuddsbrev_Mausetvegen_4.pdf | 2026-01-06 |  | 25% |  |  |  | 125 |  | Løyning / Marianne | Yes | Application: Successful | 630A | Haber Norge AS (https://www.notion.so/Haber-Norge-AS-2aba1d8f95598027819de48ba2941e24?pvs=21) | Pending | [5 empty] | Rikard | 230 V | Solar as a Service | 131.3 | 2025-11-07 |  |  | Solenergi FUSen AS (https://www.notion.so/Solenergi-FUSen-AS-1a7a1d8f9559808b87f9f872abff2596?pvs=21) | Jens Hetland (https://www.notion.so/Jens-Hetland-32da1d8f955980c38012c24a3a13b82c?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  | 1x Solis 60K-LV |  | No status | Yes | 27.03.2026: Godkjent. | Approved |  |  | No status |  |  |  | 184x650W LONGi LR7-72HVH 650 | No status | Not started |  |  | Kjetil |  |  |  | 1.437 | 0 | 693.68
Signed - awaiting Sales | Eikringen 19, 3036 Drammen |  | 204.48 | 2026-02-11 | 2026-06-30 | 2026-02-11 | 2026-04-13 |  |  | To be approved | 🟩 49 days (on-going) | 49 | 🟥 61 days | 61 | ❌ ERROR / Check Date | -11 | 🟩 114 days (on-going) | 114 | 🟩 65 days | 65 | 0.2 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2604 | 0 | 3,102.552631578948 | 3.102552631579 | 🟩 OK! | 246.490416 | 246,490.416 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,203,691 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.691 | 0 | 0 |  | 2025 | -204.48 | 204.48 | 353.691 | 1.729709507042 | 353.691 | 0 | 0 | 353.691 | 1.729709507042 | 10.777049100156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.85 | 0 | 2026-02-02 | 0 | 9.047339593114 | 1.729709507042 | 1,850,000 | 9.047339593114 | 0 | 0 | 0 | 0 | 0 | 1.85 | 0 | 0 | 0 | 0 |  | 0 | 1,850,000 | [9 empty] | Eikringen 19 |  | Client applies | Applied by client | 630A | Kobbervikdalen Verkstedseiendom AS (https://www.notion.so/Kobbervikdalen-Verkstedseiendom-AS-2e0a1d8f95598012ab6fff1adc43de39?pvs=21) | Yes - all PPAs | 3036 | Drammen | Signed |  | Eikringen 19 og 20 AS (https://www.notion.so/Eikringen-19-og-20-AS-311a1d8f955980d08e22e2d2f47453ad?pvs=21) | Johan | 400 V | SolaaS buy-back | 204.48 | 2025-12-08 |  |  | Isola Solar AS (https://www.notion.so/Isola-Solar-AS-1a7a1d8f95598048a3c5c037d15fbcdd?pvs=21) | Morten Bergan (https://www.notion.so/Morten-Bergan-2efa1d8f955980a387eecace82c5dfbd?pvs=21), Thomas Sørensen (https://www.notion.so/Thomas-S-rensen-1a5a1d8f95598014a5f3f7c3f1ad86fd?pvs=21) | Not uploaded | To be applied |  | GoO priced in APA | Not relevant |  | Not started | GLITRE | No status | Planned |  |  | 2x Solis 110kW |  | Roof OK | Yes | Isola har søkt | Sent |  | Rambøll (https://www.notion.so/Ramb-ll-2fda1d8f9559802481bfdc36b1f90634?pvs=21) | Received | Not relevant |  | 2025 | 284 stk. 720W Huasun bifacial | No status | Not started |  |  | Siri | [5 empty] | 1,850,000
To be installed (FID) | Eikringen 20, 3036 Drammen |  | 159.12 | 2026-02-20 | 2026-04-24 | 2026-02-20 | 2026-04-07 |  |  | Signed APA | 🟩 40 days (on-going) | 40 | 🟨 46 days | 46 | ❌ ERROR / Check Date | -5 | 🟩 41 days (on-going) | 41 | 🟩 1 days | 1 | 0.16 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2604 | 0 | 4,823.90243902439 | 4.823902439024 | 🟩 OK! | 124.7293944 | 124,729.3944 |  | 2026 - Q1 | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,107,780 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197.78 | 0 | 0 |  | 2026 | -159.12 | 159.12 | 197.78 | 1.242961287079 | 197.78 | 0 | 0 | 203.342 | 1.27791603821 | 6.996870286576 | 0 | 0 | 0 | 197.78 | 2026-11-01 | 197.78 | 0 | 🟩 NoCs: 0 | 0.91 | -0.034954751131 | 2026-11-01 | 0 | 5.718954248366 | 1.242961287079 | 910 | 5.718954248366 | 0 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0 |  | 0 | 910 | [5 empty] | NTE |  |  |  | Eikringen 20 | Isola Solar | Client applies | Applied by client | 800A | Kobbervikdalen Verkstedseiendom AS (https://www.notion.so/Kobbervikdalen-Verkstedseiendom-AS-2e0a1d8f95598012ab6fff1adc43de39?pvs=21) | Yes - all PPAs | 3036 | Drammen | Signed | https://drive.google.com/file/d/1KSbewH2scyZi3i5F3HFnhBNIEdEJXArV/view | Eikringen 19 og 20 AS (https://www.notion.so/Eikringen-19-og-20-AS-311a1d8f955980d08e22e2d2f47453ad?pvs=21) | Johan | 400 V | SolaaS buy-back | 95.56 | 2026-02-19 |  |  | Isola Solar AS (https://www.notion.so/Isola-Solar-AS-1a7a1d8f95598048a3c5c037d15fbcdd?pvs=21) | Morten Bergan (https://www.notion.so/Morten-Bergan-2efa1d8f955980a387eecace82c5dfbd?pvs=21), Thomas Sørensen (https://www.notion.so/Thomas-S-rensen-1a5a1d8f95598014a5f3f7c3f1ad86fd?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  | 1x Solis 125kW |  | Roof OK | Yes | Isola har søkt | Sent |  | Rambøll (https://www.notion.so/Ramb-ll-2fda1d8f9559802481bfdc36b1f90634?pvs=21) | Received |  |  | 2025 | 312 x Trina Vertex S+ 510 Wp | No status | Not interested |  |  | Siri | [5 empty] | 910
To be installed (FID) | Bedriftsvegen 76, 3735 Skien |  | 594.72 | 2026-03-06 | 2026-05-29 | 2026-03-06 | 2026-02-01 |  |  | Signed APA | 🟩 26 days (on-going) | 26 | ❌ ERROR / Check Date | -33 | 🟩 59 days (on-going) | 59 | 🟩 105 days (on-going) | 105 | 🟩 79 days | 79 | 0.59 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2602 | 0 | 5,213.495238095238 | 5.213495238095 | 🟩 OK! | 0 | 0 |  | 2026 - Q1 | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 6,494,417 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547.417 | 0 | 0 |  | 2025 | -594.72 | 594.72 | 547.417 | 0.92046172989 | 547.417 | 0 | 0 | 666 | 1.11985472155 | 11.11951842884 | 0 | 0 | 0 | 547.417 | 6.49 | 547.417 | 0 | 🟩 NoCs: 0 | 5.95 | -0.19939299166 | 6.49 | 0 | 9.999663707291 | 0.92046172989 | 5,947,000 | 9.999663707291 | 0 | 0 | 0 | 0 | 0 | 5.95 | 0 | 0 | 0 | 0 |  | 0 | 5,947,000 | [5 empty] | NTE |  |  |  | Bedriftsvegen 76 |  |  | Applied by client | 1500A | Bedriftsvegen Invest AS (https://www.notion.so/Bedriftsvegen-Invest-AS-2e0a1d8f955980f9b7bbc133b6c3fbad?pvs=21) | Yes - not all PPAs | 3735 | Skien | Signed | https://drive.google.com/file/d/1J8R0nJ0YVwbfGGasWSsO2-pWwQjvNzvE/view | Bedriftsvegen 76 AS (https://www.notion.so/Bedriftsvegen-76-AS-317a1d8f9559802ca8bdf538adccf9b0?pvs=21) | Johan | 400 V | SolaaS buy-back | 607.68 | 2025-12-17 |  |  | Isola Solar AS (https://www.notion.so/Isola-Solar-AS-1a7a1d8f95598048a3c5c037d15fbcdd?pvs=21) | Victor Pran (https://www.notion.so/Victor-Pran-2efa1d8f95598028b8eaca1cad11c852?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | LEDE | No status | Completed |  |  | 3 x Solis S6-150k 1 x Solis S6-110k |  | Roof OK | Yes | Isola har søkt. | Approved |  | A. L. Høyer (https://www.notion.so/A-L-H-yer-2ffa1d8f9559802292dece5a2cf41ad5?pvs=21) | Received |  |  |  | 826 x 720W Huasun HS-210-B132-DS720 Bifacial | No status | Not started |  |  | Siri | [5 empty] | 5,947,000
To be installed (FID) | Leiraveien 11, 2000 Lillestrøm |  | 2,230.12 | 2026-03-06 | 2026-07-10 | 2026-03-06 | 2026-04-13 |  |  | Approval in progress | 🟩 26 days (on-going) | 26 | 🟩 38 days | 38 | ❌ ERROR / Check Date | -11 | 🟩 85 days (on-going) | 85 | 🟩 59 days | 59 | 2.23 | 0 | 🟩 All good |  | ❌ End date missing | 💛 Chill |  | 2604 | 0 | 23,039.623529411765 | 23.039623529412 | 🟩 OK! | 1,811.2142592 | 1,811,214.2592 |  | 2026 - Q1 | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 12,808,126 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1,958,368 | 0 | 0 |  | 2026 | -2,230.12 | 2,230.12 | 1,958,368 | 0.878144673829 | 1,958,368 | 0 | 0 | 185.064 | 0.082983875307 | 5.84489713558 | 0 | 0 | 0 | 1,958,368 | 12.81 | 1,958,368 | 0 | 🟨 NoCs: 1 | 10.85 | 0.795160798522 | 12.81 | 0 | 4.865100532707 | 0.878144673829 | 12,849,758 | 5.761913260273 | 0 | 0 | 0 | 0 | 0 | 10.85 | 0 | 0 | 0 | 0 |  | -2,000,000 | 10,849,758 | [9 empty] | Leiraveien 11 |  |  | Does not qualify | 2900A | Oro Eiendom AS (https://www.notion.so/Oro-Eiendom-AS-1a7a1d8f9559808ab717e86d2a8f3c16?pvs=21) | Yes - all PPAs | 2000 | Lillestrøm | Signed | https://drive.google.com/file/d/1CfvGwgD_IqyVjBUm73CMLC1huRuyGibT/view | Leiraveien 11 AS (https://www.notion.so/Leiraveien-11-AS-31aa1d8f95598063b331f83eb7cb7cb6?pvs=21) | Jonas | 400 V | Solar as a Service | 2,230.12 | 2026-01-06 | Truls Martin Johansen (https://www.notion.so/Truls-Martin-Johansen-2e8a1d8f9559800e9ae5e4f909be3f4c?pvs=21) | Via innsiden av bygget i andre etasje | EnergiSmart Norge AS (https://www.notion.so/EnergiSmart-Norge-AS-2d1a1d8f955980149ab4e5ec83567745?pvs=21) | Gunnar Norås (https://www.notion.so/Gunnar-Nor-s-1a5a1d8f955980929af6da7f0b490ecc?pvs=21) | Not uploaded | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  | 12x INVT XG125KTR-PRO-NE (snow melt) |  | Roof OK | Yes | Ikke søknadspliktig | Approved |  | Sørconsult AS (https://www.notion.so/S-rconsult-AS-1a6a1d8f955980f0839fd466daf35453?pvs=21) | Received | Not relevant | PVC |  | 3512x635−645W AIKO-G-MCH72D | Done | Not started |  |  | Kjetil |  |  |  |  | 1,376,306 | 11,473,452
To be installed (FID) | , |  | 517.4 | 2026-07-01 | 2026-12-31 |  |  |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 177 days (on-going) | 177 | 🟩 177 days (on-going) | 177 | 0.52 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 1,491.525423728814 | 1.491525423729 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 2,644,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.2 | 0 | 0 |  | 2025 | -517.4 | 517.4 | -81 | -0.156551990723 | 264 | 345 | 345 | -81 | -0.156551990723 | 5.110166215694 | 0 | 0 | 0 | 0 | 0 | 345 | 0 | 🟩 NoCs: 0 | 2.73 | 0.666795516042 | 2.64 | 0 | 5.266718206417 | 0.510243525319 | 2,725,000 | 5.266718206417 | 0 | 0 | 0 | 0 | 0 | 2.73 | 0 | 345 | 0 | 0 |  | 0 | 2,725,000 | 2025-10-09 | Deployment/Energieffektivisering_med_solcelleanlegg_til_Sndre_Industrivegen_50.pdf | 2026-05-06 |  | 100% |  |  |  | 345 |  |  | Yes | Application: Successful | 2500A | Logistea AS (https://www.notion.so/Logistea-AS-1a8a1d8f955980458a0ef7caf1e1a0fa?pvs=21) | [6 empty] | Johan |  | Solar as a Service |  | 2025-10-06 | [5 empty] | To be applied |  |  |  |  | Not started | [28 empty] | 2,725,000
To be installed (FID) | , |  | 157.18 | [6 empty] | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 145 days (on-going) | 145 | 🟩 145 days (on-going) | 145 | 0.16 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill |  |  | 0 | 951.724137931035 | 0.951724137931 | 🟩 OK! | 0 | 0 |  |  | 2025 - Q4 | 0 | 0 |  |  | 0 | 0 | 1,050,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.6 | 0 | 0 |  | 2025 | -157.18 | 157.18 | 138 | 0.877974296984 | 138 | 0 | 0 | 138 | 0.877974296984 | 6.680239216185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.91 | 0 | 2026-05-01 | 0 | 5.802264919201 | 0.877974296984 | 912 | 5.802264919201 | 0 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0 |  | 0 | 912 | [14 empty] | Haber Norge AS (https://www.notion.so/Haber-Norge-AS-2aba1d8f95598027819de48ba2941e24?pvs=21) | No |  |  | Signed |  |  | Rikard |  | Solar as a Service |  | 2025-11-07 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started |  | No status | [5 empty] | Not OK | TBD |  | No status |  |  | No status |  |  |  |  | No status | Not started |  |  | Kjetil | [5 empty] | 912
In operation (COD) | Orkidehøgda 14, 3050 Mjøndalen |  | 491.7 |  |  | 2026-02-16 | 2026-02-19 | 2026-02-19 | 491.7 | N/A | 🟩 3 days | 3 | 🟩 3 days | 3 | 🟩 0 days | 0 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.49 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 | 2602 | 0 |  | 0 | 🟥 SUM! | 383.0343 | 383,034.3 | 2026 - Q1 | 2026 - Q1 |  | 0 | 23,599.686 |  |  | 0 | 0 |  | ⌚ 41 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 491.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Connectivity, Smart | thing_186cf5b0-ff5e-5b8c-b82d-cfd8633db1c2 (https://www.notion.so/thing_186cf5b0-ff5e-5b8c-b82d-cfd8633db1c2-309a1d8f955980599f1adf757f87bcba?pvs=21) |  |  | Orkidehøgda 14 |  |  | Does not qualify |  | Zeiner Eiendom AS (https://www.notion.so/Zeiner-Eiendom-AS-2fba1d8f9559803eb7bddb12d826a8bc?pvs=21) |  | 3050 | Mjøndalen |  |  |  | Alex | 400 V | SaaS | [5 empty] | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Not started | LEDE |  | Completed |  |  | 1x Growatt 125 kW 2x Growatt 100 kW |  | No status | No |  | Not applicable |  |  | No status | Not relevant |  |  | 894x550W Phono Solar PS550M6H-24/HT | Not relevant |  |  | Sent | Kjetil
In operation (COD) | Måkeveien 1A, 3112 Tønsberg |  | 343.2 |  |  | 2026-02-16 | 2026-02-23 | 2026-02-26 | 341 | N/A | 🟩 10 days | 10 | 🟩 7 days | 7 | 🟩 3 days | 3 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.34 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 | 2602 | 0 |  | 0 | 🟥 SUM! | 298.034 | 298.034 | 2026 - Q1 | 2026 - Q1 |  | 0 | 17,378.68 |  |  | 0 | 0 |  | ⌚ 34 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | -2.2 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Connectivity, Smart | thing_6c960b4b-9ea3-51a9-a028-ac5aa9e67d4a (https://www.notion.so/thing_6c960b4b-9ea3-51a9-a028-ac5aa9e67d4a-309a1d8f955980f098bcc82a10c77f60?pvs=21) | Not started |  | Måkeveien 1A |  | No | Does not qualify |  | Zeiner Eiendom AS (https://www.notion.so/Zeiner-Eiendom-AS-2fba1d8f9559803eb7bddb12d826a8bc?pvs=21) |  | 3112 | Tønsberg |  |  |  | Alex | 400 V | SaaS | 343.2 |  |  |  | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Not started | LEDE | Not relevant | Completed |  |  | 1x Growatt 125 kW 1x Growatt 100 kW |  | No status | No |  | Not applicable |  |  | No status |  |  |  | 620x550W Phono Solar PS550M6H-24/HT | Not relevant |  |  | Delivered to installer | Kjetil
In operation (COD) | Wirgenes vei 2, 3157 Barkåker |  | 148.5 |  |  | 2026-02-16 | 2026-02-23 | 2026-02-26 | 148.5 |  | 🟩 10 days | 10 | 🟩 7 days | 7 | 🟩 3 days | 3 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.15 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 | 2602 | 0 |  | 0 | 🟥 SUM! | 127.413 | 127.413 | 2026 - Q1 | 2026 - Q1 |  | 0 | 8,191.26 |  |  | 0 | 0 |  | ⌚ 34 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 148.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Connectivity, Smart | thing_778f83bf-e404-5f18-a634-8a4d27530ce1 (https://www.notion.so/thing_778f83bf-e404-5f18-a634-8a4d27530ce1-309a1d8f9559804c9231e5f651181b32?pvs=21) |  |  | Wirgenes vei 2 |  | No | Does not qualify |  | Zeiner Eiendom AS (https://www.notion.so/Zeiner-Eiendom-AS-2fba1d8f9559803eb7bddb12d826a8bc?pvs=21) |  | 3157 | Barkåker |  |  |  | Alex | 400 V | SaaS | 148.5 |  |  |  | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Done | LEDE | Not relevant | Completed |  |  | 1x Growatt |  | No status | No |  | Not applicable |  |  | No status | Not relevant |  |  | 341x550W Phono Solar PS550M6H-24/HT | Not relevant |  |  | Sent | Kjetil
In operation (COD) | Storgaten 2B, Tønsberg 3126 |  | 226.6 |  |  | 2026-02-16 | 2026-02-22 | 2026-02-25 | 226.6 | N/A | 🟩 9 days | 9 | 🟩 6 days | 6 | 🟩 3 days | 3 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.23 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 | 2602 | 0 |  | 0 | 🟥 SUM! | 197.8218 | 197,821.8 | 2026 - Q1 | 2026 - Q1 |  | 0 | 11,942.436 |  |  | 0 | 0 |  | ⌚ 35 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 226.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Connectivity, Smart | thing_bbc48303-74c2-5d22-8870-304bfce21cb5 (https://www.notion.so/thing_bbc48303-74c2-5d22-8870-304bfce21cb5-309a1d8f9559800791efc45dc9ead781?pvs=21) |  |  | Storgaten 2B |  | No | Does not qualify |  | Zeiner Eiendom AS (https://www.notion.so/Zeiner-Eiendom-AS-2fba1d8f9559803eb7bddb12d826a8bc?pvs=21) |  | Tønsberg | 3126 |  |  |  | Alex | 400 V | SaaS | 226.6 |  |  |  | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) | Uploaded FDV | Not relevant |  | Not relevant |  |  | Not started | LEDE | Not relevant | Completed |  |  | 2x Growatt 100 kW |  | No status | No |  | Not applicable |  |  | No status | Not relevant |  |  | 412x550W Phono Solar PS550M6H-24/HT | Not relevant |  |  | Installed | Kjetil
In operation (COD) | Hinderveien 2, 3223 Sandefjord |  | 242 |  |  | 2026-02-16 | 2026-02-23 | 2026-02-26 | 242 | N/A | 🟩 10 days | 10 | 🟩 7 days | 7 | 🟩 3 days | 3 | ❌ RLA date missing | 0 | ❌ RLA date missing | 0 | 0.24 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | ❌ Missing | 2026-02-26 | 2602 | 0 |  | 0 | 🟥 SUM! | 213.202 | 213.202 | 2026 - Q1 | 2026 - Q1 |  | 0 | 12,712.04 |  |  | 0 | 0 |  | ⌚ 34 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 |  | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Connectivity, Smart | thing_6be305a2-b23d-51e2-ab60-bbed5f0505a7 (https://www.notion.so/thing_6be305a2-b23d-51e2-ab60-bbed5f0505a7-309a1d8f955980fe8b88d6038bc54b5a?pvs=21) |  |  | Hinderveien 2 |  | No | Does not qualify |  | Zeiner Eiendom AS (https://www.notion.so/Zeiner-Eiendom-AS-2fba1d8f9559803eb7bddb12d826a8bc?pvs=21) |  | 3223 | Sandefjord |  |  |  | Alex | 230 V | SaaS | 242 |  |  |  | BlueTec AS (https://www.notion.so/BlueTec-AS-1a5a1d8f95598075b14ec53d7377cebc?pvs=21) | Harald Kristensen (https://www.notion.so/Harald-Kristensen-1a5a1d8f955980f09dfbd1f424eb9fe9?pvs=21) |  | Not relevant |  | Not relevant |  |  | Not started | LEDE | Not relevant | Completed |  |  | 4x Growatt 50kW |  | No status | No |  | Not applicable |  |  | No status |  |  |  | 440x550W Phono Solar | Not relevant |  |  | Sent | Kjetil
To be installed (FID) | Verkstedveien 11, 6517 Kristiansund N |  | 164.92 | 2026-04-24 | 2026-05-29 | [5 empty] | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 16 days (on-going) | 16 | 🟩 16 days (on-going) | 16 | 0.16 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  |  | 0 | 11.199 | 11.199 | 🟩 OK! | 112.1456 | 112,145.6 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,222,184 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161,265.6 | 0 | 0 |  | 2026 | -164.92 | 164.92 | 179.184 | 1.086490419597 | 179.184 | 0 | 0 | 179.184 | 1.086490419597 | 7.410768857628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-04-01 | 0 | 1.22 | 0 | 6.324278438031 | 1.086490419597 | 1,043,000 | 6.324278438031 | 0 | 0 | 0 | 0 | 0 | 2026-04-01 | 0 | 0 | 0 | 0 |  | 0 | 1,043,000 | [9 empty] | Verkstedveien 11 |  | No | Does not qualify |  | Ziko Gruppen (https://www.notion.so/Ziko-Gruppen-327a1d8f955980c780f1d1ad2c98c6ec?pvs=21), Løkkemyra Utleie AS (https://www.notion.so/L-kkemyra-Utleie-AS-327a1d8f955980c2bfd7eb6f9dfa7449?pvs=21) | Yes - all PPAs | 6517 | Kristiansund N | Signed | https://drive.google.com/file/d/1ESxo00r_fB5tu8-_Wn4jn2_-ROM7eEBc/view?usp=drive_link | Løkkemyra Utleie AS (https://www.notion.so/L-kkemyra-Utleie-AS-327a1d8f955980c2bfd7eb6f9dfa7449?pvs=21) | Johan | 230 V | Solar as a Service | 168.64 | 2026-03-16 | Øystein Fladvad / Elservice (https://www.notion.so/ystein-Fladvad-Elservice-327a1d8f955980e5b152f071b7628487?pvs=21) | Fast tilkomst |  |  |  | To be applied |  | GoO priced in APA |  |  | Not started | Mellom |  | Completed |  |  | 2 x 50 kW Growatt |  | Roof OK | Yes |  | Sent |  |  | No status |  | Bitumen / asfaltpapp | 2025 | 248 stk. 665 Wp Aiko glass-glass | No status |  |  |  | Siri |  |  |  |  | 0 | 1,043,000
To be installed (FID) | Pans veg 2, 3940 Porsgrunn |  | 161.16 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.16 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 16.25 | 16.25 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,065,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 0 |  | 2026 | -161.16 | 161.16 | 195 | 1.209977661951 | 195 | 0 | 0 | 195 | 1.209977661951 | 6.608339538347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.87 | 0 | 2026-07-01 | 0 | 5.398361876396 | 1.209977661951 | 870 | 5.398361876396 | 0 | 0 | 0 | 0 | 0 | 0.87 | 0 | 0 | 0 | 0 |  | 0 | 870 | [9 empty] | Pans veg 2 |  | No | Does not qualify |  | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 3940 | Porsgrunn | Signed |  |  | Rikard |  | Solar as a Service | 161 | 2026-03-20 | [5 empty] | To be applied |  | GoO priced in APA |  |  | Not started | LEDE | No status | Completed |  |  |  |  | No status | Yes | Ikke søknadspliktig | Approved |  |  | No status |  |  |  |  | No status | Not started | [8 empty] | 870
To be installed (FID) | Våleveien 1, 3080 Holmestrand |  | 197.55 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.2 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 14.25 | 14.25 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,218,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 |  | 2026 | -197.55 | 197.55 | 171 | 0.865603644647 | 171 | 0 | 0 | 171 | 0.865603644647 | 6.165527714503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-05-01 | 0 | 1.22 | 0 | 5.299924069856 | 0.865603644647 | 1,047,000 | 5.299924069856 | 0 | 0 | 0 | 0 | 0 | 2026-05-01 | 0 | 0 | 0 | 0 |  | 0 | 1,047,000 | [9 empty] | Våleveien 1 |  | No | Does not qualify |  | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 3080 | Holmestrand | Signed |  |  | Rikard |  | Solar as a Service | 198 | 2026-03-20 |  |  |  |  | Not uploaded | To be applied |  |  |  |  | Not started | LEDE | No status | Completed |  |  |  |  | No status | Yes | Ikke søknadspliktig | Approved |  |  | No status | Not relevant |  |  |  | No status | Not started | [8 empty] | 1,047,000
To be installed (FID) | Vesterveien 737, 4823 Nedenes |  | 144.72 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.14 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 19,583.333333333332 | 19.583333333333 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,016,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 |  | 2026 | -144.72 | 144.72 | 235 | 1.623825317855 | 235 | 0 | 0 | 235 | 1.623825317855 | 7.02045328911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.78 | 0 | 2026-02-01 | 0 | 5.396627971255 | 1.623825317855 | 781 | 5.396627971255 | 0 | 0 | 0 | 0 | 0 | 0.78 | 0 | 0 | 0 | 0 |  | 0 | 781 | [9 empty] | Vesterveien 737 |  | No | Does not qualify |  | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 4823 | Nedenes | Signed |  |  | Rikard |  | Solar as a Service | 145 | 2026-03-20 | [5 empty] | To be applied |  |  |  |  | Not started | GLITRE | No status | Completed |  |  |  |  | Not OK | Yes | 27.03.26: Må søke om unntak | To be applied |  |  | No status |  |  |  |  | No status | Not started | [8 empty] | 781
Under deployment | Braarudveien 7, 1870 Ørje |  | 171.46 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.17 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 13,666.666666666666 | 13.666666666667 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,090,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 |  | 2026 | -171.46 | 171.46 | 164 | 0.956491309927 | 164 | 0 | 0 | 164 | 0.956491309927 | 6.35716785256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0.93 | 0 | 2026-09-01 | 0 | 5.400676542634 | 0.956491309927 | 926 | 5.400676542634 | 0 | 0 | 0 | 0 | 0 | 0.93 | 0 | 0 | 0 | 0 |  | 0 | 926 | [9 empty] | Braarudveien 7 |  | No | Does not qualify | 450A | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 1870 | Ørje | Signed |  |  | Rikard |  | Solar as a Service | 171 | 2026-03-20 | [5 empty] | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | Not OK | Yes | Ikke søknadspliktig | Approved |  |  | No status |  |  |  |  | No status | Not started | [8 empty] | 926
Under deployment | Iseveien 8, 1738 Borgenhaugen |  | 239.18 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.24 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 24.25 | 24.25 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,535,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 0 |  | 2026 | -239.18 | 239.18 | 291 | 1.216656911113 | 291 | 0 | 0 | 291 | 1.216656911113 | 6.417760682331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 1.24 | 0 | 1.54 | 0 | 5.201103771218 | 1.216656911113 | 1,244,000 | 5.201103771218 | 0 | 0 | 0 | 0 | 0 | 1.24 | 0 | 0 | 0 | 0 |  | 0 | 1,244,000 | [9 empty] | Iseveien 8 |  | No | Does not qualify | 800A | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 1738 | Borgenhaugen | Signed |  |  | Rikard |  | Solar as a Service | 239 | 2026-03-20 | [5 empty] | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | Not OK | Yes | Ikke søknadspliktig | Approved |  |  | No status |  |  |  |  | No status | Not started | [8 empty] | 1,244,000
Under deployment | Frøyas gate 1, 2270 Flisa |  | 190.23 | 2026-04-10 | 2026-06-30 |  | 2026-05-04 |  |  | To be approved | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ERROR / Check Date | -32 | 🟩 12 days (on-going) | 12 | 🟩 12 days (on-going) | 12 | 0.19 | 0 | 🟨 Awaiting FID |  | ❌ End date missing | 💛 Chill |  | 2605 | 0 | 13.25 | 13.25 | 🟩 OK! | 0 | 0 |  |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 | 1,186,000 | ❌ COD not set | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 0 | 0 |  | 2026 | -190.23 | 190.23 | 159 | 0.835830310677 | 159 | 0 | 0 | 159 | 0.835830310677 | 6.23455816643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 2026-03-01 | 0 | 1.19 | 0 | 5.398727855754 | 0.835830310677 | 1,027,000 | 5.398727855754 | 0 | 0 | 0 | 0 | 0 | 2026-03-01 | 0 | 0 | 0 | 0 |  | 0 | 1,027,000 | [9 empty] | Frøyas gate 1 |  | No | Does not qualify | 630A | AKA AS (https://www.notion.so/AKA-AS-329a1d8f9559801dac20fb60f5bc7246?pvs=21) | No | 2270 | Flisa | Signed |  |  | Rikard |  | Solar as a Service | 190 | 2026-03-20 | [5 empty] | To be applied |  |  |  |  | Not started | ELVIA | No status | Completed |  |  |  |  | Not OK | Yes | 25.03.26: Generell henvendelse sendt | Sent |  |  | No status |  |  |  |  | No status | Not started | [8 empty] | 1,027,000
Under deployment | Fabrikkveien 36, 4033 Stavanger | [6 empty] | 2026-06-30 |  |  | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 91 days | 91 | 🟩 1 days (on-going) | 1 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Jun |  | 0 | 0 | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q2 |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -89 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2026 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Fabrikkveien 36 | Malling ¦ Stein Randby | No | Client decision: No application | 403A innstilt (630A max) | Nordea Liv Eiendom (https://www.notion.so/Nordea-Liv-Eiendom-334a1d8f95598050aa00ed751ae7f5b7?pvs=21) | Pending | 4033 | Stavanger | Signed | https://drive.google.com/file/d/156w-FMCdGole3j-6kkX54EJZ_59MfoOR/view?usp=drive_link | Fabrikkveien 36 AS (https://www.notion.so/Fabrikkveien-36-AS-334a1d8f955980cbabb8cc289da7acea?pvs=21) | Johan | 400 V | Solar as a Service | 212.8 | 2026-03-31 | [10 empty] | Not started | LNETT | [6 empty] | Roof OK |  |  | Sent
Under deployment | Fabrikkveien 38, 4033 Stavanger | [6 empty] | 2026-06-30 |  |  | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 91 days | 91 | 🟩 1 days (on-going) | 1 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Jun |  | 0 | 0 | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q2 |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -89 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2026 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Fabrikkveien 38 | Malling ¦ Stein Randby | No | Client decision: No application | 750A innstilt (1250A max) | Nordea Liv Eiendom (https://www.notion.so/Nordea-Liv-Eiendom-334a1d8f95598050aa00ed751ae7f5b7?pvs=21) | Pending | 4033 | Stavanger | Signed | https://drive.google.com/file/d/18AyxLQVlr0Cb06NVjRloHbR2X6tNesIl/view?usp=drive_link | Fabrikkveien 38 AS (https://www.notion.so/Fabrikkveien-38-AS-334a1d8f955980b7a4f2d05377a3c869?pvs=21) | Johan | 400 V | Solar as a Service | 425.6 | 2026-03-31 | [10 empty] | Not started | LNETT | [6 empty] | Roof OK |  |  | Sent
Under deployment | Fabrikkveien 41, 4033 Stavanger | [6 empty] | 2026-06-30 |  |  | ❌ FID date missing | 0 | ❌ FID date missing | 0 | ❌ ISD date missing | 0 | 🟩 91 days | 91 | 🟩 1 days (on-going) | 1 | 0 | 0 | 🟧 Est. FID missing |  | ❌ End date missing | 💛 Chill | 26 - Jun |  | 0 | 0 | 0 | 🟥 SUM! | 0 | 0 | 2026 - Q2 |  | 2026 - Q1 | 0 | 0 |  |  | 0 | 0 |  | 🔸🕐 -89 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 2026 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟩 NoCs: 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [9 empty] | Fabrikkveien 41 | Malling ¦ Stein Randby | No | Client decision: No application | 300A innstilt (400A max) | Nordea Liv Eiendom (https://www.notion.so/Nordea-Liv-Eiendom-334a1d8f95598050aa00ed751ae7f5b7?pvs=21) | Pending | 4033 | Stavanger | Signed | https://drive.google.com/file/d/1B01nbJWYSkXjb167JISlW8tOQPtr5Rm_/view?usp=drive_link | Fabrikkveien 41 AS (https://www.notion.so/Fabrikkveien-41-AS-334a1d8f955980e79f68c1d3ccc0fe73?pvs=21) | Johan | 400 V | Solar as a Service | 199.5 | 2026-03-31 | [10 empty] | Not started | LNETT | [6 empty] | Roof OK |  |  | Sent